## West Burton
Cost to date
West Burton Budget Cost | [12 empty] | 2021-12-17 |  |  | 2021-05-01 | June | July | August | September | October | November | December | 2022-01-01 | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
[13 empty] | Month | [24 empty] | App submitted
Item | Sub-Item | Original Budget (£) | Updated budget (£) Jan 2022 | Invoices and forecast total (£) | Pre-submission total (£) | Post-submission total (£) | Variance | Quote 1 | Quote 2 | Quote 3 | Quote 4 | Commissioned consultant work | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
Grid | NGET Application | 66772 | 66973 | 66973 | 66973 | 0 | -201 | [5 empty] | Month 1: 66772; Month 13: 201
| Consultants | 33228 | 31078.22 | 44766.06 | 43850.81 | 915.25 | -11538.06 | 45025 |  |  |  | 45025 | Month 1: 30540.32; Month 12: 537.9; Month 13: 1235.21; Month 14: 621.27; Month 15: 892.34; Month 16: 621; Month 17: 613.95; Month 18: 578.48; Month 19: 3932.7; Month 20: 1181.51; Month 21: 819.34; Month 22: 1166.65; Month 24: 163.13; App submitted 26: 947.01; App submitted 27: 113.25; App submitted 28: 56.63; App submitted 30: 459.3; App submitted 31: 113.25; App submitted 32: 56.63; App submitted 37: 116.19
| Deposit/security | 500000 | 500000 | 0 | 0 | 0 | 500000 | [5 empty] | Month 1: 0
| Auxiliary connection applications | 0 | 3660 | 300 | 300 | 0 | -300 | [5 empty] | Month 1: 0; Month 19: 300
| Network Rail BAPA | 0 | 0 | 80463.42 | 33423.42 | 47040 | [6 empty] | Month 1: 0; Month 20: 1800; App submitted 26: 31623.42; App submitted 34: 1800; App submitted 37: 15000; App submitted 38: 30240
Lease/Option |  | 295000 | 295000 | 189444 | 180462 | 8982 | 105556 | [5 empty] | Month 1: 165332; Month 18: 12500; Month 24: 2630; App submitted 30: 8982
Legal fees - assignment of Broxholme |  | 0 | 850 | 850 | 850 | 0 | [6 empty] | Month 1: 0; Month 12: 850
Planning Application Fee | Performance Agreements | 53000 | 100000 | 167342.25 | 40139.25 | 127203 | -114342.25 | [5 empty] | Month 1: 0; Month 16: 6599.25; Month 20: 9672; Month 24: 6579; App submitted 26: 17289; App submitted 40: 67200; App submitted 41: 60003
| Planning Inspectorate | 597000 | 597000 | 501968 | 7488 | 494480 | 95032 | [5 empty] | Month 1: 0; App submitted 26: 7488; App submitted 29: 39464; App submitted 34: 224375; App submitted 40: 230641
Planning Consultant |  | 344000.19 | 413184.5 | 1121082.24 | 557871.18 | 563211.06 | 777082.05 | [5 empty] | 148830.5 | [9 empty] | 19685 | 19685 | 19685 |  | 19415.19 | 20697.85 | 29800 | 22315.79 | 19500 | 20998.33 | 19938.75 | 12512.5 | 19500 | 18401.69 | 20105.33 | 126800.25 |  | 17630.57 | 28835 | 21409.95 | 35375.95 | 32274.58 | 22710 | 22900.23 | 57568 | 73784.73 | 40000 | 72982.62 | 55712 | 50513.93 | 8798 | 11478 | 1237.5 | 3333.3333 | 3333.3333 | 3333.3333
Pinsent Masons Project Management |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | Month 1: 0
Planning Studies | Heritage Statement | 23750 | 34800 | 382157.15 | 209113.46 | 173043.69 | -358407.15 | 34800 |  |  |  | 34800 | 21800 | [10 empty] | 5000 | 6937.5 |  | 3012.5 | 3750 | 17750 | 1945.21 | 7500 | 16987.5 | 9000 | 4090 | 2527.5 | 5848.75 | 20532.5 | 82432 |  | 7900 | 7500 | 3545.25 | 11369.75 | 7982 | 7250 | 6410 | 22155 | 16583.24 | 12515 | 18260.95 | 14727.5 | 8875 | 4375 | 4719 | 4719 | 4719 | 4719 | 4719
| ALC Classification | 30000 | 30625 | 33029.96 | 33029.96 | 0 | -3029.96 | 29100 | 59537 | 25281.64 | 29625 | 29625 | Month 1: 28125; Month 12: 596.96; Month 13: 1500; Month 16: 1808; Month 17: 1000
| Agricultural circumstances | 0 | 0 | 4000 | 4000 | 0 | [6 empty] | Month 1: 0; App submitted 26: 4000
| Topographical Study | 55000 | 74134.17 | 61299.17 | 61299.17 | 0 | -6299.17 | 77340 | 28500 | 10675 | 46205 | 77340 | Month 1: 41658.71; Month 11: 3550.46; Month 12: 11335; Month 15: 1530; Month 16: 3225
| Flood Risk Assessment | 28750 | 21950 | 64929 | 33510 | 31419 | -36179 | 23750 | 8300 |  |  | 23750 | Month 1: 2250; Month 12: 3250; Month 17: 6960; Month 19: 3720; Month 20: 7600; Month 21: 7350; App submitted 26: 2380; App submitted 30: 720; App submitted 33: 6099; App submitted 40: 8100; App submitted 41: 16500
| Geophysical Survey | 222955 | 208966.5 | 242885 | 242885 | 0 | 131955 | 131955 | 131955 | 131955 | 131955 | 131955 | Month 1: 110930; Month 12: 38137.5; Month 13: 23625; Month 15: 30937.5; Month 16: 1350; Month 17: 5141.25; Month 18: 667.5; Month 19: 10165.5; Month 21: 10905.75; Month 22: 8775; Month 23: 2250
| Geophysical Survey (cable route overlap) | 0 | 0 | 9208 | 9208 | 0 | [6 empty] | Month 1: 0; Month 16: 7099; Month 17: 540; Month 23: 1569
| Trial Trenching | 160000 | 160000 | 817414.43 | 674564.43 | 142850 | -657414.43 | [5 empty] | Month 1: 0; Month 19: 211105.5; Month 20: 242694.5; Month 21: 70766.75; Month 22: 78580; Month 24: 33417.68; Month 25: 38000 |  |  |  |  | 142850
| Air Quality | 2000 | 4375 | 19605 | 7400 | 12205 | -17605 | 4375 |  |  |  | 4375 | Month 1: 0; Month 11: 1650; Month 16: 4500; App submitted 26: 1250; App submitted 34: 1975; App submitted 35: 2955; App submitted 41: 7275
| Minerals and deposits | 1750 | 3750 | 8730 | 6640 | 2090 | -6980 | 3750 |  |  |  | 3750 | Month 1: 2480; Month 17: 1600; App submitted 26: 2560; App submitted 31: 475; App submitted 39: 1615
| Arboricultural Survey | 35000 | 35000 | 0 | 0 | 0 | 35000 | 35000 |  |  |  | 35000 | Month 1: 0
| Highways Survey | 12500 | 45100 | 111805.53 | 75617.39 | 36188.14 | -99305.53 | 6500 | 37600 | 45100 |  | 45100 | Month 1: 15500; Month 12: 2680; Month 13: 8043.39; Month 14: 3026.5; Month 15: 1570; Month 16: 4012.5; Month 17: 4012.5; Month 18: 6000; Month 19: 2000; Month 20: 1420.25; Month 21: 3362.55; Month 23: 5000; Month 25: 5599.7; App submitted 26: 13390; App submitted 31: 2750; App submitted 32: 2288.14; App submitted 33: 1250; App submitted 34: 2500; App submitted 35: 5000; App submitted 36: 3000; App submitted 37: 4000; App submitted 38: 5500; App submitted 39: 3000; App submitted 40: 4900; App submitted 41: 2000
| Abnormal loads | 0 | 7245 | 11220.3 | 7365.3 | 3855 | -11220.3 | 7245 |  |  |  |  | Month 1: 0; Month 14: 1006.5; Month 15: 2268.3; Month 16: 855; Month 20: 1170; Month 21: 112.5; Month 23: 1188; App submitted 26: 765; App submitted 28: 337.5; App submitted 29: 900; App submitted 30: 652.5; App submitted 31: 1380; App submitted 32: 427.5; App submitted 35: 157.5
| Ecological Survey | 173449.85 | 340352.85 | 361523.35 | 340340.35 | 21183 | -188073.5 | 340353 |  |  |  | 340353 | Month 1: 146355.85; Month 12: 27563.5; Month 14: 10695; Month 15: 10060; Month 16: 24732.5; Month 17: 44190.5; Month 18: 26375; Month 19: 19518; Month 23: 6985; Month 25: 17815; App submitted 26: 6050; App submitted 29: 2250; App submitted 34: 11156; App submitted 36: 4074; App submitted 41: 3703
| Environmental Masterplan | 0 | 13882 | 30898.5 | 30898.5 | 0 | -30898.5 | 18000 |  |  |  | 18000 | Month 1: 7990; Month 11: 1964; Month 13: 1500; Month 17: 5735; Month 18: 2212.5; Month 19: 1000; Month 20: 1250; Month 21: 2050; Month 23: 1197; Month 24: 1000; Month 25: 5000
| LVIA | 100000 | 148356.75 | 425420.66 | 274645.38 | 150775.28 | -325420.66 | 161931 |  |  |  | 161931 | 10356.75 | [11 empty] | 17068.28 |  | 19247.5 | 10859 | 11082 | 13852.02 | 10788.75 | 15376.43 | 5510.88 | 3817.5 | 3162.5 | 9300 | 35500 | 108723.77 |  | 9710.25 | 6306 | 2325 | 8230.25 | 5105.5 | 11513 | 7515.97 | 11228 | 5721.06 | 10000 | 19841.25 | 24479 | 5000 | 5000 | 3760 | 3760 | 3760 | 3760 | 3760
| CTMP | 16000 | 0 | 0 | 0 | 0 | 16000 | 0 |  |  |  | 0 | Month 1: 0
| Noise | 9730 | 11575 | 24290 | 18390 | 5900 | -14560 | 11575 |  |  |  | 11575 | Month 1: 3500; Month 11: 3650; Month 16: 5325; App submitted 26: 5915; App submitted 34: 1975; App submitted 41: 3925
| 3D model | 80000 | 20000 | 15750 | 15750 | 0 | 64250 | [5 empty] | Month 1: 0; Month 19: 6000; Month 21: 4000; Month 25: 5750
| Cumulative Impact | 6500 | 0 | 0 | 0 | 0 | 6500 | [5 empty] | Month 1: 0
| Funding Statement | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Month 1: 0
| Glint/Glare | 21250 | 25738.8 | 35664.45 | 25739.95 | 9924.5 | -14414.45 | 21250 |  |  |  | 21250 | Month 1: 1378.2; Month 13: 177.3; Month 15: 10880; Month 16: 873.2; Month 17: 354.6; Month 18: 88.65; Month 24: 11988; App submitted 30: 1312; App submitted 31: 1325; App submitted 32: 1325; App submitted 37: 662.5; App submitted 39: 1104.16; App submitted 40: 2870.84; App submitted 41: 1325
| Legal DCO drafting | 350000 | 350000 | 552302.98 | 91305.2 | 460997.78 | -202302.98 | 350000 |  |  |  | 350000 | Month 1: 0; Month 12: 8234; Month 15: 1920; Month 16: 480; Month 17: 39631.6; Month 18: 1237.2; Month 19: 1432.8; Month 20: 4192; Month 21: 1476; Month 25: 4156.8; App submitted 26: 28544.8; App submitted 27: 72837.2; App submitted 28: 5900.8; App submitted 29: 2962; App submitted 30: 9972.2; App submitted 31: 27693.1; App submitted 32: 137754.82; App submitted 39: 203877.66
| Examination phase costs | 0 | 0 | 152775.33 | 0 | 152775.33 | -152775.33 | [5 empty] | Month 1: 0; App submitted 32: 3761.45; App submitted 33: 13100; App submitted 34: 3560; App submitted 35: 24819; App submitted 37: 44541.88; App submitted 38: 49165; App submitted 39: 9016; App submitted 40: 4812
| Consultation / PR / website | 197000 | 187194.35 | 358004.04 | 206788.56 | 151215.48 | -161004.04 | 196802.5 |  |  |  | 196802.5 | 45154.35 | [9 empty] | 4035.21 | 3520 | 7580 |  | 4220 | 9553.17 | 41703 |  | 55492.83 | 4020 | 7880 | 8520 | 4020 | 2010 |  | 9080 | 38706 |  | 2564 | 2564 | 3264 | 14885.1 | 4744 | 10714 | 5139.63 | 3044 | 12634.75 | 38189 | 10866 | 2566 | 1335
| Statement of Need | 16720 | 11520 | 17550 | 8550 | 9000 | -830 | 11520 |  |  |  | 11520 | Month 1: 2460; Month 17: 2250; Month 24: 3840; App submitted 32: 840; App submitted 35: 4080; App submitted 37: 3120; App submitted 41: 960
| Utilities Digitisation | 0 | 4050 | 4050 | 4050 | 0 | -4050 | 4050 |  |  |  | 4050 | Month 1: 4050
| Oil pipeline investigation | 0 | 10000 | 5000 | 5000 | 0 | -5000 | 10000 |  |  |  | 10000 | Month 1: 5000
| Cable route utilities search | 0 | 13388.06 | 10940 | 10940 | 0 | -10940 | 13388 | 11289 | 29099 |  |  | Month 1: 0; Month 15: 10940
| Electromagnetic fields | 0 | 5590 | 1260 | 1260 | 0 | -1260 | 5590 |  |  |  | 5590 | Month 1: 0; Month 12: 1260
| Contaminated land | 0 | 16065 | 29315 | 29315 | 0 | -29315 | 16065 |  |  |  | 16065 | Month 1: 16065; Month 17: 3000; Month 18: 10250
| Savills WB4 land agent costs | 0 | 4747.5 | 7145.75 | 7145.75 | 0 | -7145.75 | [5 empty] | Month 1: 0; Month 12: 4747.5; Month 24: 2398.25
| Natural England DAS | 0 | 5000 | 2860 | 2860 | 0 | -2860 | 5000 |  |  |  |  | Month 1: 0; Month 20: 1210; App submitted 26: 1650
| Climate change | 0 | 0 | 6935 | 4005 | 2930 | 0 | 0 | 6935 | 0 | 0 | 6935 | Month 1: 0; Month 16: 3285; Month 18: 720; App submitted 37: 1935; App submitted 41: 995
| Cable route engineering design | 0 | 0 | 42451.51 | 22981.37 | 19470.14 | [6 empty] | Month 1: 0; Month 21: 5168.95; Month 25: 14151.67; App submitted 26: 3660.75; App submitted 28: 12369.27; App submitted 32: 4880.7; App submitted 34: 271.15; App submitted 36: 542.3; App submitted 39: 271.15; App submitted 41: 135.57; App submitted 42: 1000
| Construction timescales/waste/worker numbers | 0 | 0 | 1125 | 1125 | 0 | [6 empty] | Month 1: 0; Month 24: 1125
| EDF survey licence | 0 | 0 | 5000 | 5000 | 0 | [6 empty] | Month 1: 0; Month 20: 5000
| SEUK NSIP Membership | 0 | 0 | 20000 | 10000 | 10000 | [6 empty] | Month 1: 0; Month 21: 10000; App submitted 32: 10000
| Protective provisions 3rd party legal costs | 0 | 0 | 87000 | 30000 | 57000 | [6 empty] | Month 1: 0; Month 21: 30000; App submitted 28: 30000; App submitted 39: 2000 | 25000
| National Grid property agreements | 0 | 0 | 0 | 0 | 0 | [6 empty] | Month 1: 0; App submitted 29: 0
| Co-operation agreement | 0 | 0 | 1075.03 | 1075.03 | 0 | [6 empty] | Month 1: 0; Month 23: 1075.03
| Batteries | 0 | 0 | 12721.95 | 0 | 12721.95 | [6 empty] | App submitted 36: 2000; App submitted 37: 2200; App submitted 38: 2921.95; App submitted 39: 5600
| Other |  | 0 | 0 | 0 | 0 | [6 empty] | Month 1: 0
| Mapping | 19000 | 19000 | 19306 | 19306 | 0 | -306 | [5 empty] | Month 1: 19000; Month 13: 306
| Tillbridge survey refund | 0 | 0 | -7938.87 | 0 | -7938.87 | [6 empty] | Month 1: 0; App submitted 38: -7938.87
Professional services | Land referencing (DM) | 394544 | 128939.18 | 298131.76 | 219977.78 | 78153.98 | 96412.24 | 128938.61 | 145000 |  |  | 128938.61 | 14344.18 | [9 empty] | 19505.53 | 7197.7 | 5528.75 | 9938.75 | 13498 | 4460 | 11104.49 | 11748.97 | 27690.72 | 11690.25 | 6899.76 | 3712.03 | 8537.12 | 2783.15 | 18247.71 | 43090.67 |  | 4129.35 | 6319.55 | 1695.35 | 1121.25 | 1952.25 | 1751.75 | 4513.5 | 6884.01 | 5287.04 | 9489.11 | 5782.06 | 2158.81 | 7647.42 | 1422.53 | 8000 |  |  |  |  | 10000
| Land referencing (Savills/Bruton Knowles) | 0 | 150000 | 172982.57 | 59609.41 | 113373.16 | -172982.57 | [5 empty] | 0 | [13 empty] | 14974.37 | 8357.5 | 7500.1 | 5306.35 | 3729.5 | 1681.25 | 2408.75 | 4957.5 | 1335 | 792.5 | 1662.9 | 6903.69 | 5898.75 | 4356.5 | 4900.25 | 6160.5 | 5160 | 7191.25 | 5752.5 | 4387 | 7578.75 | 2208.75 | 7892 | 1603.41 | 3269 | 1840 | 1922.5 | 3252 | 10000 | 10000 | 10000 | 10000
| Cable route landowner payments | 0 | 525000 | 538675.1 | 13500 | 525175.1 | -538675.1 | [5 empty] | Month 1: 0; Month 15: 10000; Month 22: 3000; App submitted 26: 500; App submitted 29: 500; App submitted 33: 1200; App submitted 36: 1475.1; App submitted 37: 2000; App submitted 41: 300000; App submitted 42: 220000
| Cable route legals | 0 | 105000 | 66657 | 0 | 66657 | -66657 | [5 empty] | Month 1: 0; App submitted 29: 3300; App submitted 38: 6657; App submitted 39: 3500; App submitted 40: 20000; App submitted 41: 20000; App submitted 42: 13200
Contingency | 10% of planning costs | 390489 | 344717.398 | 0 | 0 | 0 | 390489 |  |  |  |  | 153976.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Satisfaction of pre-commencement planning conditions |  | 30000 | 30000 | 30000 | 0 | 30000 | 0 | [5 empty] | App submitted 37: 20000; App submitted 38: 10000
Accounting, admin, prof. fees & bank charges |  | 7661 | 30000 | 30000 | 2761 | 27239 | -22339 | [5 empty] | Month 1: 1735; Month 12: 513; Month 25: 513; App submitted 36: 900; App submitted 37: 750; App submitted 38: 1375; App submitted 39: 1875; App submitted 40: 22339
Transaction Cost |  | 30000 | 30000 | 30000 | 0 | 30000 | [6 empty] | App submitted 31: 5000; App submitted 32: 5000; App submitted 33: 5000; App submitted 34: 5000; App submitted 35: 5000; App submitted 36: 5000
Total |  | 4295388 | 5133808.278 | 7298344.62 | 3758309.65 | 3540034.97 | [5 empty] | 1867706.76 | 911607.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54040.2 | 135108.06 | 93387.43 | 25288.02 | 155365.7 | 122442.97 | 233968.99 | 115797.67 | 383876.3 | 347944.02 | 197649.98 | 129131.18 | 58346.15 | 102277.15 | 187034.61 | 505043.36 | 117555.2 | 92390.87 | 105800.8 | 59798.05 | 103257.55 | 235724.92 | 80370.25 | 309052.85 | 152564.89 | 123620.22
Installed Capacity | 624
Total/MW |  | 6883.6346 | 8227.2569 | 11696.0651
[26 empty] | Spend to date | 1374797.27
| Deal Sheet budget 08/07/21 |  |  | 3904899
| Difference to total: |  |  | -3393445.62
7298344.62
3488016.04
3904899
| Disbursements |  |  |  |  | 650000
| Lanpro |  |  | 26221.74 |  | 7948344.62 | [6 empty] | Month 1: 26221.74
| Amet |  |  | 1000
416882.96
2481808.278
Note on J6: Eve Browning: Omnia quote for stages 1-3, half for each project
Note on AA6: Eve Browning: INV-6631
Note on AB6: Eve Browning: INV-6789
Note on AC6: Eve Browning: Invoice INV-6937
Note on AD6: Eve Browning: Invoice INV-7102
Note on AE6: Eve Browning: Invoice INV-7290
Note on AF6: Eve Browning: Invoice INV-7432
Note on AG6: Eve Browning: Invoice INV-7610
Note on AH6: Eve Browning: Invoice INV-7843
Note on AI6: Eve Browning: Invoice INV-8241
Note on AJ6: Eve Browning: Invoice INV-8285
Note on AL6: Eve Browning: Invoice INV-2212-132 Building colours and spec - £163.13
Note on AN6: Eve Browning: Invoice INV-2302-051 Updates to SLDs - £947.01
Note on AO6: Eve Browning: Invoice INV-2303-053 Lessons learned telcon - £113.25
Note on AP6: Eve Browning: Invoice INV-2304-109 Grid connection cost advice - £56.63
Note on AR6: Eve Browning: Invoice INV-2306-102 West Burton Power Station site visit - £459.30
Note on AS6: Eve Browning: Invoice INV-2307-105 Grid connection advice - £113.25
Note on AT6: Eve Browning: Invoice INV-2308-129 Front end engineering design advice - £56.63
Note on AY6: Eve Browning: Invoice INV-2401-135 Project advice - £116.19
Note on AG8: Eve Browning: Invoice 40089169 WB 3 aux connection
Note on AH9: Eve Browning: Exceptional payment - Cowdale Lane North Clearance Costs - £1500 + VAT = £1800 Payment reference: WB70590 North
Note on AN9: Eve Browning: Exceptional payment Cowdale Lane - £26352 + VAT = £31623.42
Note on AV9: Eve Browning: Invoice ref: 6561234/TEL/1225931 WB3 clearance fee for widening of red line - £1500 + VAT = £1800
Note on AY9: Eve Browning: Network Rail legal costs EB estimate
Note on AZ9: Eve Browning: Based upon 10% of NR easement fee being payable upon option signing - £630/MW across whole project
Note on AF10: Eve Browning: EPR - Roythornes Undertaking for WB Substation option agreement - £10,000 Undertaking for WB4 deed of surrender - £2500
Note on AL10: Eve Browning: Invoice INV-12075 Perkins George Mawer & Co Limited Heads of Terms and Option discussions for Sarah Reeve (landowner at West Burton substation site) - £2630
Note on AR10: Eve Browning: Invoice 1749024 - Gowling WLG Surrender impact advice - Beck Lane Farm and part Highfield Farm, Clayworth - £6750 Invoice 51166 Brown & Co Land agent costs - WB Sub - £2232
Note on E12: Eve Browning: £10k Notts + £12200 Lincs up to end stat consultation period
Note on AD12: Eve Browning: LCC Invoice 10143929
Note on AH12: Eve Browning: Lincs CC invoice 10150108 Landscape and council officer fees
Note on AL12: Eve Browning: Nottinghamshire County Council invoice 92816609 Planning advice - £6579
Note on AN12: Eve Browning: Invoice 10160542 Lincs County Council August 2022 - January 2023 costs - £17289
Note on BA12: Eve Browning: LCC estimate - Legal Costs - pre-examination: £10,000 - examination period: £5000 - Landscape consultant costs - up to start of examination: £10000 - examination period: £10000 - Council costs - pre-examination: - Ongoing dialogue with lead and technical officers: £2700 - SoCG: £2700 - Archaeology: £4140 - examination: - Ongoing dialogue with lead and technical officers: £24570 - SoCG: £10620 - Archaeology: £4590 NCC Estimate - Council costs - pre-examination: - Ongoing dialogue with lead and technical officers: £708 - SoCG: £354 - examination: - Ongoing dialogue with lead and technical officers: £708 - SoCG: £354 - Attendance and response to hearing sessions: £1416
Note on BB12: Eve Browning: West Lindsey examination costs?
Note on BC12: Eve Browning: LCC invoice 2004384186 PPA costs Feb 3023 to May 2024 - £60003.00
Note on AQ13: Eve Browning: Invoice 1800004491 Pre-examination fee - £39464
Note on AV13: Eve Browning: Invoice 1800004611 West Burton Solar Project initial examination fee -£224,375
Note on BB13: Eve Browning: Invoice 1800004937 West Burton Solar Project final examination fee £230,641.00
Note on AA14: Eve Browning: Invoice number 005233
Note on AC14: Eve Browning: Invoice 005469 for £17685, invoice 005514 for £1730.19 expenses
Note on AD14: Eve Browning: Invoice 005643, includes monthly expenses invoiced separately
Note on AE14: Eve Browning: Invoice 005820 Invoice 005822 - CEMP -Decommissioning statement - PEIR Socioeconomic chapter - PEIR Waste chapter - PEIR Other environmental matters chapter - £12.5k fee discounted by £2.2k budget saving carried forward Total = £10,300
Note on AF14: Eve Browning: Invoice 006089 - Planning consultancy services, travel expenses, consultation event attendance
Note on AG14: Eve Browning: Invoice 006197
Note on AH14: Eve Browning: Invoice 006303 - expenses Invoice 006300 - consultancy
Note on AI14: Eve Browning: Invoice 006646 Planning consultancy services - £19500 Invoice 006651 Expenses - £438.75
Note on AJ14: Eve Browning: Invoice 006830
Note on AK14: Eve Browning: Invoice 007026 Planning consultancy
Note on AL14: Eve Browning: Invoice 007069 £17520.75 Invoice 29 (Low Carbon UK Solar Investment Company Limited) Aerial LIDAR data on the cable route for Gate Burton, West Burton and Cottam - £880.94
Note on AM14: Eve Browning: Invoice 007392 Planning consultancy - £19500 Invoice 007395 Expenses - £605.33
Note on AN14: Eve Browning: Invoice 007621 Planning consultancy services - £62381.50 Invoice 007689 Planning consultancy services - £64418.75
Note on AP14: Eve Browning: Invoice 8018 Planning consultancy - £16250 Lanpro invoice 8020 Printing of submission documents for PINS - £1380.57
Note on AQ14: Eve Browning: Invoice 008270 Planning consultancy services - £28,835
Note on AR14: Eve Browning: Invoice 008342 Planning consultancy - £21409.95
Note on AS14: Eve Browning: Invoice 008697 Planning consultancy services - £35375.95
Note on AT14: Eve Browning: Invoice 008760 • Progressing Relevant Reps response • Progressing SoCG’s • Attending usual client and other project meetings • Preparing for examination • Updates to document trackers / actions lists / file structures • Reviewing/progressing revisions and additional documents required as a result of RR’s • Supporting on change application for cable route corridor • Procedural Deadline A correspondence £31,139.50 Invoice 008770 Expenses Invoice Report printing & postage - £1135.08
Note on AU14: Eve Browning: Invoice 008968 • Progressing Relevant Reps response • Progressing SoCG’s • Attending usual client and other project meetings • Preparing for examination • Updates to document trackers / actions lists / file structures • Reviewing/progressing revisions and additional documents required as a result of RR’s • Supporting on change application for cable route corridor • Procedural Deadline A correspondence £22710
Note on AV14: Eve Browning: Invoice 009170 Progressing Relevant Reps response • Progressing SoCG’s • Attending usual client and other project meetings • Preparing for examination • Updates to document trackers / actions lists / file structures • Reviewing/progressing revisions and additional documents required as a result of RR’s • Supporting on change application for cable route corridor • Procedural Deadline A correspondence Stage 4 - Pre-Examination £22,710.00 Travelling Costs £190.03
Note on AW14: Eve Browning: Invoice 009371 - Prep for examination - Hearings and deadline 1 requirements £57568
Note on AX14: Eve Browning: Invoice 9555 - Responding to Deadline 1 and preparing for D2 and D3 - West Burton hearings - Regular Project management and meetings £57568 Expenses - £67.98 Gate Burton Energy Park Invoice SIN2401L064000002 Options and Interrelationships reports - £16148.75
Note on AY14: Eve Browning: Lanpro invoice 009751 Planning; - Examination submission for D2, D3 and preparation for hearings and D4 Stage 5 - Examination £40,000.00
Note on AZ14: Eve Browning: Invoice SIN2403L051000002 Low Carbon Inter-relationships and options report final payment - £3500 Lanpro invoice 009972 Planning; • Preparation and submission of Deadline 4; • Preparation and attendance for Issue Specific Hearings; and • Ongoing Project Management. £62228 Volterra - socio-economic recharge - £7065 Hearing expenses - 189.62 £69482.62
Note on BA14: Eve Browning: Invoice 010198 Planning; - Ongoing examination preparation for D5 and rescheduled hearing, responding to ExA questions, SoCGs, D4 and D4a submission responses. £49515 Invoice 010213 Planning: additional hearing • Attendance of Jane, Stephen and Tara: £6197.00
Note on BB14: Eve Browning: Invoice 010455 Expenses Invoice: March - April - Hearing Expenses (Mileage, parking, hotels & subsistence £998.93 Invoice 010428 Ongoing Planning, EIA and PM support around preparation for Deadlines 5 and 6, liaising with the team, clients, Pinsents to input into required documentation as part of the submission, as well as ongoing meetings and attendance at Change Application Hearing on 23rd April. £49515
Note on BC14: Eve Browning: Invoice 010671 Planning; - Final examination submission co-ordination - Project management - Liaison with client and lawyers £8798
Note on BD14: Eve Browning: Invoice 010879 Deer Park changes • Change of Work Plans (allow for up to 4 hours); • Liaise with Historic England to agree the amended details (allow for up to 2 hours); and • Review plans and coordination by planning team (allow for up to 3 hours). £1000 Discharge of conditions work - £3018.75 Late Rule 17 request for additional infomation from ExA regarding Deer Park, preparatino and coordination of without prejudice document, SoCGs for deadline 7 - £7459.25 Total £11478
Note on BE14: Eve Browning: Coordinating, and compiling the fee quotes on requirement discharge for West Burton - £1237.50
Note on AA16: Eve Browning: Invoice number 005235
Note on AC16: Eve Browning: Invoice 005477
Note on AD16: Eve Browning: Invoice 005645
Note on AE16: Eve Browning: Invoice 005950 PEIR/WSI/Environmental statement
Note on AF16: Eve Browning: Invoice 006031 - ES, consultancy, WSI, expenses
Note on AG16: Eve Browning: Invoice 006198 ES, Consultancy, WSI
Note on AH16: Eve Browning: Lanpro invoice 006289 Alison Deegan aerial photo analysis Lanpro invoice 006302 Desk Based Assessment £3,000.00 Consultancy £2,500.00 Heritage Statement scoping £450.00 Environmental Statement Chapter £2,750.00 Written Scheme of Investigation £2,250.00
Note on AI16: Eve Browning: Invoice 006648 - Consultancy £2,500.00 - Environmental Statement £2,500.00 - Written Scheme of Investigation £1,000.00 - AP & LiDAR Interpretation £3,000.00
Note on AJ16: Eve Browning: Invoice 006829 AP and LiDAR Interpretation £3,000.00 Consultancy £650.00 Environmental Statement £440.00
Note on AK16: Eve Browning: Invoice 007027 Consultancy - £1000 DBAs - £432.5 ES - £1095
Note on AM16: Eve Browning: Invoice 007394 Consultancy £260.00 Desk Based Assessments £7,493.75 Environmental Statement £10,732.50 Heritage Statement £440.00 Written Scheme of Investigation £1,606.25
Note on AN16: Eve Browning: Invoice 007619 Consultancy £2,735.00 Desk Based Assessments £9,327.50 Environmental Statement £13,420.00 Heritage Statement £28,205.00 Written Scheme of Investigation £2,025.00 Invoice 007697 Work up to submission - £26,720
Note on AP16: Eve Browning: Invoice 8016 Pre-examination works - £7900
Note on AQ16: Eve Browning: Invoice 008272 Archaeology/heritage pre-examination works - £7500
Note on AR16: Eve Browning: Invoice 008340 Archaeology/heritage pre-examination works - £3545.25
Note on AS16: Eve Browning: Invoice 008699 Archaeology/heritage pre-examination works - £11369.75
Note on AT16: Eve Browning: Invoice 008758 General Project Management (i.e. meetings, comms with Historic England) Statements of Common Ground Responses to Relevant Representations Viewpoint locations for the Inspector Review of issued documents (i.e. Rule 6) Review of other schemes (Tillbridge / Gate Burton) Review of submitted HE documents Consolidation / review of counter arguments (i.e. archaeology / heritage issues) £7982
Note on AU16: Eve Browning: Invoice 008970 - General Project Management (i.e. meetings, comms with Historic England) - Statements of Common Ground - Responses to Relevant Representations - Viewpoint locations for the Inspector - Review of other schemes - Review of Report on the interrelationship with other NSIPs - Review of comparable designated heritage sites (i.e. Ravensdale Deer Park, Derbyshire £7250
Note on AV16: Eve Browning: Invoice 009172 - General Project Management (i.e. meetings, comms with Historic England) - Statements of Common Ground - Responses to Relevant Representations - Viewpoint locations for the Inspector - Review of other schemes - Review of Report on the interrelationship with other NSIPs Archaeology/Heritage Examination Works £6,410.00
Note on AW16: Eve Browning: Invoice 009373 Historic Environment; - General Project Management - Liaison with Lincs LPA - Liaison with Notts LPA - SoCG - Responses to Relevant Representations - Issue specific hearing preparation and attendance - Review of ES documents £22155
Note on AX16: Eve Browning: Invoice 009557 - General project management - Deadline 2 documents - LIR / RR responses - ExQ1 - Liaison with Lincs LPA £15120 Expenses - £1463.24 Total £16583.24
Note on AY16: Eve Browning: Invoice 009753 Historic Environment; - General project management - Change of application report - Prehearing preparation - ExQ1 RR Archaeology/Heritage Examination Works £12,515.00
Note on AZ16: Eve Browning: Invoice 009970 Historic Environment; - General Project Management - WSIs - RRs - CHPSs / SoCG - Hearing £17750 Expenses - £510.95
Note on BA16: Eve Browning: Invoice 010200 Historic Environment; Prep for deadline 5. Response to examiners questions Statement of Common Ground £8875 Invoice 010213 Heritage: additional hearing • Preparation and Attendance of Alice and Emily: £5852.5
Note on BB16: Eve Browning: Invoice 010430 Historic Environment; Update to WSIs Deadline 5 / 6 submissions HE / LCC /NCC /WLDC SoCG / Position Statements ExA second written questions Closing Statements £8875
Note on BC16: Eve Browning: Invoice 010669 Historic Environment; - D6 submissions / Rule 17 - Project review - West Burton 3 – Stow Park post determination work - Liaison with HE £4375
Note on J17: Eve Browning: SES quote, only complete late October, half of total quote of £58.2k
Note on K17: Eve Browning: Half of total quote from Ceres Rural - can complete by mid-August, using digger to dig soil pits, and includes all expenses. Revising quote downwards if third parties used
Note on L17: Eve Browning: Quote from LRA - six month lead time for completion
Note on M17: Eve Browning: Amet Property. Includes £1500 expenses. One report available early August, and one early Sept
Note on Z17: Eve Browning: INV-0896
Note on AA17: Eve Browning: WB substation site INV-0909
Note on AD17: Eve Browning: Additional lab sampling and report amending Invoice INV-0984
Note on AE17: Eve Browning: Daniel Baird peer review Invoice INV-0078
Note on AN18: Eve Browning: Invoice INV-0091 Farming circumstances, ES chapter and team meetings - £4000
Note on J19: Eve Browning: Sensat.Note: £2225 per month to be added for platform from month 4 £12000 added for access point surveys + + £3750 added for 3D CAD production + £17590 survey for WB substation site and access points
Note on K19: Eve Browning: Quote from ALS. Drone survey to define project boundaries, site levels and salient features which might affect the design of the project. Further surveys may be required at a later date to help complete highways design or inform more detailed arboricultural/habitat assessments.
Note on L19: Eve Browning: Half of total quote from Flythru, including updated costs to process output into dwg files
Note on M19: Eve Browning: Combined quote from Sumo and AerialCam. Additional £11k estimate for completing terrestrial surveying at a later date
Note on Y19: Eve Browning: 3D CAD
Note on Z19: Eve Browning: 12k access point topo survey
Note on AC19: Eve Browning: WB substation and access points drone survey Invoice 42860
Note on AD19: Eve Browning: WB substation and access points terrestrial survey Sumo Invoice 43012
Note on J20: Eve Browning: Quote from Delta Simons for initial flood risk screening assessment only is £2250. Secondary quote for further works comes to £21500.
Note on K20: Eve Browning: Missing Broxholme. Quote from Rossi Long, includes FRA report, consultation with EA and proposed mitigation measures
Note on AE20: Eve Browning: Invoice DS033518
Note on AG20: Eve Browning: Invoice DS034012 PEIR chapter
Note on AH20: Eve Browning: Invoice DS034313 £2100 for WB Sub FRA Invoice DS034314 £5500 for WB4 rainfall modelling
Note on AI20: Eve Browning: Invoice DS034656 West Burton 4 rainfall modelling - £7350
Note on AN20: Eve Browning: Invoice 176561 - WFD report - £2200 - Meetings - £180
Note on AR20: Eve Browning: Invoice 91517 SoCG and RR responses - £720
Note on AU20: Eve Browning: Invoice 189755 RR and SoCG work - £2100 Invoice 189306 Pile volume calculations - £3999
Note on BB20: Eve Browning: Mabbett invoice 606020 Examination stage costs - £8100
Note on BC20: Eve Browning: 60 year flood modelling River Till model (covers both Cottam and West Burton sites) • Update the 2008 EA River Till model to reflect the current climate change guidance and rerun – no further changes to existing hydrology or model setup • Produce an updated flood depth grid through the site • Flood maps and report updates £6,700+VAT Tidal Trent model (covers West Burton site and unnamed watercourse) • Site specific updates to 2023 Jacobs/EA Tidal Trent to include topographic survey details • Run site specific model to produce defended flood depths across the site • Flood maps and report updates £4,900+VAT Unnamed Watercourse model • Complete ReFH2 rainfall calculations • Construct a simple, new 2D domain of the unnamed watercourse catchment from existing topographic survey data where available and EA LiDAR elsewhere • Simulation of a range of design rainfall events to produce flood depths across the site • Flood maps and report updates £4,900+VAT Total £16500
Note on J21: Eve Browning: 1145ha at £215 per hectare. 400ha/month surveyed - approx £86k per month for cash flow Original quote from Lanpro £291,600 for WB and £177,750 for Cottam
Note on K21: Eve Browning: Latest estimate from Lanpro 21/12/21
Note on O21: Eve Browning: Confirm this
Note on AA21: Eve Browning: Invoice 005235
Note on AC21: Eve Browning: Invoice 005477
Note on AD21: Eve Browning: Invoice 005645
Note on AE21: Eve Browning: Invoice 005821
Note on AF21: Eve Browning: Invoice 006031
Note on AG21: Eve Browning: Invoice 006293
Note on AI21: Eve Browning: Invoice 006645
Note on AJ21: Eve Browning: Invoice 006836
Note on AK21: Eve Browning: Invoice 007031 Cable route geophys (10ha) - £2250
Note on AD22: Eve Browning: Invoice INV038046
Note on AE22: Eve Browning: Invoice INV038200
Note on AK22: Eve Browning: Invoice INV039185
Note on J23: Eve Browning: Hoped not to be required until post-planning
Note on AG23: Eve Browning: Invoice 006200 Lanpro - for 2200 + 178905.5 trial trenching Invoice SI5199 Leverton Farms - £30k crop loss - West Burton 2
Note on AH23: Eve Browning: Invoice 006289 Archaeological fieldwork (Sept) and project management (August)
Note on AI23: Eve Browning: Invoice 006644 - Archaelogical fieldwork - £43866.75 - Arch. Fieldwork project management - £25300 Invoice SI5232 Leverton Farms Crop loss miscanthus - £1600
Note on AJ23: Eve Browning: Invoice 006831 Archaeological Fieldwork (October Additional) £54,780.00 Archaeological Fieldwork Project Management £8,800.00 Invoice 117 Campions Crop loss - £15000
Note on AL23: Eve Browning: Invoice 007068 (Lanpro) Post-excavation project management and report QA - £9300 Invoice 28 (Low Carbon UK Solar Investment Company Limited) £19004.09 Shared cable route trial trenching Invoice 30 (Low Carbon) £5113.59 Trial trenching additional costs (Landowner costs e.g. license fee, agent fees, trench compensation, grass reseeding works, drainage repairs)
Note on AM23: Eve Browning: Added 38k additional crop loss - WB 2 - worst case of 4 x trench area for12 x future miscanthus harvests (shouldn't all be needed if less damage than expected and also solar should be constructed before then)
Note on BI23: Eve Browning: Estimation of post-trenching final reporting costs
Note on J24: Eve Browning: Tetratech, includes battery fire smoke assessment
Note on AD24: Eve Browning: PEIR and construction dust assessment Invoice 30034718
Note on AN24: Eve Browning: Invoice 784-B031437 / 30052381 ES chapter - £1250
Note on AV24: Eve Browning: Invoice 30066671 Pre-exam fee (50%) - £1975
Note on AW24: Eve Browning: Invoice 30070854 - Detailed BESS fire impact assessment - £1450 - Revised BESS Fire Assessment scenario - £1250 - Attendance at 3 meetings - £355
Note on BC24: Eve Browning: Stage 4: Pre-examination - £1975 Stage 5: Examination - £1950 Additional solar panel fire modelling and risk assessment - £1850 Detailed BESS fire impact assessment - £1500
Note on J25: Quote from Ted Clover. Half of £7500 quote for desktop Minerals Resource Assessment - may be a little more if two separate reports required?
Note on AE25: Eve Browning: Invoice WBSP/002 PEIR
Note on AN25: Eve Browning: Invoice WBSP/003 Minerals ES chapter - £2560
Note on AS25: Eve Browning: Invoice WBSP/004 Preparation of SoCG, additional consideration of cumulative impacts - £475
Note on BA25: Eve Browning: Invoice WBSP/005 Consideration of representations/Inspectors Questions Consideration of amendments to the Scheme Advice relating to Sturton le Steeple Quarry Input into EIP documents as requested Additional Consideration of Cumulative Impacts. £1615
Note on J26: Eve Browning: Lanpro quote
Note on J27: Eve Browning: Quote from Rossi Long for initial work to inform initial consultation with stakeholders
Note on K27: Eve Browning: Quote from Stantec, does not include SoCGs or examination process. CTMP at £400 per land parcel (5x parcels) added in after clarification
Note on L27: Eve Browning: Quote from TPA includes for EIA chapter, transport statement, CTMP, input into CEMP and all drawings and consultation up to planning submission £4700 included for traffic surveys by 360 TSL, split across two projects Additional predicted overspends added due to additional junctions and abnormal loads - fee extension request saved in file
Note on Z27: Eve Browning: Scoping note plus draft CTMP
Note on AA27: Eve Browning: 4515.89 disbursements on invoice number 012966
Note on AB27: Eve Browning: Invoice 013039
Note on AC27: Eve Browning: Invoice 013243
Note on AD27: Eve Browning: Invoice 013346
Note on AE27: Eve Browning: Invoice 013456 PEIR/CTMP Invoice 013550
Note on AF27: Eve Browning: Invoice 013729 Team meetings Trip generation note review of and advice on consultation responses, traffic flow diagrams, ES chapter drafting
Note on AG27: Eve Browning: Invoice 013854 - Team Meetings; • PROW Surveys; • Red Line Review; • ES Chapter Drafting
Note on AH27: Eve Browning: Invoice 013944 • Team Meetings; • PROW Surveys; • Red Line Review; • ES Chapter Drafting.
Note on AI27: Eve Browning: Invoice 014154 Red line review ES chapter drafting PROW survey review
Note on AK27: Eve Browning: Invoice 014284 • Cable Route Accesses; • Cable Route Red Line; • New access on Till Bridge Lane; • ES Chapter Drafting;
Note on AM27: Eve Browning: Invoice 014490 • Draft ES Chapter; • Draft CTMP; • Draft TA; • Draft PROW Management Plan; • Attendance at Meetings. £5599.70
Note on AN27: Eve Browning: Invoice 014638 This invoice covers our work carried in February 2023, including: Draft ES Chapter; Draft CTMP; Draft TA; Draft PROW Management Plan; Attendance at Meetings. - £2000 Invoice 014884 • Additional spend on ES chapter to cover all consultation responses, the details of the cable route corridor and rounds of comments from the Design Team; • The initial quote was for a Transport Statement to support the DCO. However, given the detail required, this turned into a Transport Assessment, which set out the details of all accesses and their effects on the surrounding local highway network; • Multiple meetings, with the whole Design Team, IGP, Wynns, Lanpro, Pinsents and JSM • Changes in the access strategy following the site layout designs which results in relocated and new accesses; • A public rights of way management plan. - £11,390
Note on AS27: Eve Browning: Invoice 015379 SoCG and relevant reps, access assessments to match to Low Carbon - £2750
Note on AT27: Eve Browning: Invoice 015518 This invoice covers our work carried out in July/August 2023: • Response to LCC; • Relevant Reps Response • SoCG - £2250 (professional fees) and £38.14 (disbursements)
Note on AU27: Eve Browning: Invoice 015634 This invoice covers our work carried out in August/September 2023: • Response to LCC; • Relevant Reps Response • SoCG. £1250
Note on AV27: Eve Browning: Invoice 015773 This invoice covers our work carried out in September/October 2023: • Submission of response to LCC; • Relevant Reps Response; • Agreed SoCG. £2500
Note on AW27: Eve Browning: Invoice 015904 This invoice covers our work carried out in October/November 2023: • Attendance at Public Hearing; • Response to Relevant Representations; • Updated documents for Deadline 1 £5000
Note on AX27: Eve Browning: Invoice 015971 This invoice covers our work carried out in November/December 2023: • Update documents for Deadlines 2/3; • Relevant Rep Response for Deadlines 2/3 £3000
Note on AY27: Eve Browning: Invoice 016151 This invoice covers our work carried out in December 2023/January 2024: • Update documents for Deadlines 3; • Update documents for Change Application • Responses to written questions. £4000
Note on AZ27: Eve Browning: Invoice 016315 This invoice covers our work carried out in January/February 2024: • Attendance at Hearing’ • Update documents for Deadline 4; • Responses to written questions. £5500
Note on BA27: Eve Browning: Invoice 016465 This invoice covers our work carried out in February/March 2024: • Attendance at Hearing’ • Responses to written questions £2500
Note on BB27: Eve Browning: Invoice 016594 This invoice covers our work carried out in March/April 2024: • Attendance at Hearings • Responses to written questions • Updated reports £4900
Note on J28: Eve Browning: Half of Wynns quote across both WB and C
Note on AB28: Eve Browning: Invoice 3606
Note on AC28: Eve Browning: Invoice 3627
Note on AD28: Eve Browning: Invoice 3639
Note on AH28: Eve Browning: Invoice 3704
Note on AI28: Eve Browning: Invoice 3737
Note on AK28: Eve Browning: Invoice 3752 Payment for works associated with heavy load access to the proposed West Burton Solar Farm Substations during November 2022 - £1080 Mileage - £108
Note on AN28: Eve Browning: Invoice 3813 Abnormal loads report updates - £765
Note on AP28: Eve Browning: Invoice 3851 Abnormal load advice - £337.50
Note on AQ28: Eve Browning: Invoice 3876 Swept paths for cable route - £900
Note on AR28: Eve Browning: Invoice 3896 Swept paths for cable route - £652.50
Note on AS28: Eve Browning: Invoice 3915 Payment for works associated with heavy load access to the proposed West Burton Solar Farm Substations during July 2023. Additional works on Swept Path Assessments for cable drums. - £1380
Note on AT28: Eve Browning: Invoice 3932 Additional work on swept paths at WB1 - £427.50
Note on AW28: Eve Browning: Invoice 3992 Payment for works associated with heavy load access to the proposed West Burton Solar Farm Substation during November 2023. Additional works on site requirements and comments from Lincolnshire County Council questions from public examination. Agreed hourly rates as per our proposal dated 27.01.2022 (Ref. W/2022/AP/0018). £157.50
Note on J29: Eve Browning: Clarkson and Woods. Half of revised quote inc. bat surveys Additional costs added for otters and water voles/bat tree and building inspections.
Note on AB29: Eve Browning: Substation walkover survey - invoice 77357 Wintering bird survey and half day consultation fee - invoice 747918
Note on AC29: Eve Browning: 1 x wintering bird survey + meeting attendance 15/03 Invoice 747920
Note on AD29: Eve Browning: - Otter and water vole survey - £6472.5 (Invoice 77358) -April Breeding Bird Survey - £9047.50 -April bat detector survey - £7,712.50 -Badger survey - £1500 (Invoice 747922)
Note on AE29: Eve Browning: Invoice 727924 -May (Final) Breeding Bird Survey - £11,236.50 -May (Final) bat detector survey - £7,812.50 -Great crested newt eDNA surveys of up to 35 ponds in relation to cable routes AND array sites (potential to be fewer depending on access and whether they hold water or indeed exist) - £4250+£4050 (visits plus lab analysis) -Preparation of PEIR Ecology chapter – up to £5,600.00 -Input into Landscape and Ecological Management Plan (or similar) – £1,500.00 -April breeding bird survey (WB4) - £2189.00 Invoice 773510 -Watercourse and ditch survey WB4 £502.50 - Building inspection bats and birds £5100 - Expansion of bat report with building and tree inspection mapping £1950
Note on AF29: Eve Browning: Invoice 80081 - 2 x cable route breeding bird surveys - £12990 Invoice 773512 - Cable route phase 1 (50%) - £7500 Invoice 747926 - Pond visits and eDNA: (£2210+£2250+£300) - Public exhibition attendance: £750 - Meeting attendance £375
Note on AG29: Eve Browning: Invoice 747928 - Wintering bird survey report - £2200 - Breeding bird survey report - £2465 - Bat survey report - £2800 - GCN survey report - £870 - Cambridge meeting - £938 Invoice 773514 - 25% of Phase 1 survey of WB cable route (75% total invoiced so far) - £3750 Invoice 80083 - Third and final breeding bird survey of WB cable route - £6495
Note on AK29: Eve Browning: Invoice 773517 Phase 1 cable route (25%) - £3750 Otter and water vole report - £2275 West Burton substation site survey - £960
Note on AM29: Eve Browning: Invoice 747931 Preparation of ES Chapter 3,700.00 BNG Assessment (remaining 50% fee to Cover Proposals Calculations) 2,950.00 Input into LEMP 4,500.00 Preparation of Ecological Protection and Mitigation Scheme 2,800.00 Meetings attendance in Sep/Oct/Nov 645.00 Design support in Sep/Oct/Nov 3,220.00
Note on AN29: Eve Browning: Invoice 7479 ES Chapter Revisions 1,500.00 OLEMP Revisions 1,300.00 Survey of land at West Burton PS and Mapping 1,100.00 Design support in Jan/Feb 2,150.00
Note on AQ29: Eve Browning: Invoice 84312 - GCN eDNA surveys on shared cable route - £1125 - Lab fee per pond - £1125
Note on AV29: Eve Browning: Invoice 84981 Preparation of BNG Assessment Report v2 to include Cable Route Corridor 5,100.00 Invoice 84315 Statement of Common Ground - Natural England (50% budget) 1,000.00 Statement of Common Ground - Environment Agency (comments) 106.00 Statement of Common Ground - Lincolnshire Wildlife Trust (50% budget) 750.00 Statement of Common Ground - Notts Wildlife Trust (50% budget) 750.00 Relevant Representations to Councils (100% budget) 1,150.00 RRs to Other Statutory Consultees (100% budget) 1,150.00 RRs to Members of the Public (100% budget) 1,150.00
Note on AX29: Eve Browning: Invoice 84317 Change Application SEIR 318.00 DL3: Fish EMF Risk Assessment 424.00 DL3: Update iHRA 106.00 DL3: OLEMP Update 53.00 DL3: EA Statement of Common Ground 53.00 DL3: NE SoCG 212.00 DL3: ExQ1 Responses 424.00 DL3: LIR Responses 212.00 DL3: WR Responses Pt 1 265.00 DL3: WR Responses Pt 2 265.00 DL3: WR Responses Pt 3 265.00 Interrelationships Report Updates (split with Cottam) 106.00 OFH1 Written Summary comments 265.00 ISH Attendance 1,000.00 Exclusion of DCO Time Limit document input 106.00
Note on BC29: Eve Browning: Invoice 84319 West Burton Solar Project Examination - Works Jan 2024 to May 8th 2024 Finalisation of SoCG with NE 212.00 Finalisation of SoCG with Lincs WT 318.00 Finalisation of SoCG with EA 636.00 West Burton virtual change application hearing 106.00 Input into Responses to DL4 and DL4ASubmissions 212.00 Input into Responses to DL5 Submissions 212.00 Input into Joint Interrelationships Report 106.00 Input into Technical Note on Cumulative Effects 159.00 Input into ESAddendum on Cumulative Effects 212.00 Input into ExA's 2WQs 212.00 Input into ISH3 Oral Submissions 106.00 Input into Responses to DL2 and DL3 Submissions 212.00 ISH Attendance 1,000.00 Total £3703.00
Note on AA30: Eve Browning: Invoice mumber 005234
Note on AE30: Eve Browning: Invoice 005825 for £5k Invoice 005644 for £735
Note on AF30: Eve Browning: Invoice 006070
Note on AG30: Eve Browning: Invoice 006199
Note on AH30: Eve Browning: Invoice 006301
Note on AI30: Eve Browning: Invoice 006653 Environmental masterplan - £2050
Note on AK30: Eve Browning: Invoice 007028
Note on AL30: Eve Browning: Invoice 007067 Environmental masterplan
Note on AM30: Eve Browning: Invoice 007393 Env masterplan - £5000
Note on AC31: Eve Browning: Invoice 005472
Note on AD31: Eve Browning: Invoice 005825
Note on AE31: Eve Browning: Invoice 005644
Note on AF31: Eve Browning: Invoice 006070 - Consultation, LVIA, meetings, summer photography and processing,travel expenses
Note on AG31: Eve Browning: Invoice 006199
Note on AH31: Eve Browning: Invoice 006301 - LVIA and meetings/public consultations
Note on AI31: Eve Browning: Invoice 006653 LVIA £3,900.88 Meetings/Consultation £1,250.00 Red Line Boundary updates - GIS £360.00
Note on AJ31: Eve Browning: Invoice 006828 LVIA £3,450.00 Meetings/Consultation £367.50
Note on AK31: Eve Browning: Invoice 007028 LVIA - £2750 Meetings - £412.5
Note on AL31: Eve Browning: Invoice 007067 GIS Suite of Figures, Abnormal loads, Land ownership, ALC, DCO Works Plans £5,000.00 Meetings £1,000.00 LVIA £3,300.00
Note on AM31: Eve Browning: Invoice 007393 - GIS Suite of Figures, Abnormal loads, Land ownership, ALC, DCO Works Plans - £5,000.00 - LEMP Masterplan with ecological Mitigation £4,000.00 - LVIA £15,750.00 - Meetings £2,500.00 - Photomasking and montages (winter year 1 and summer year 15) £8,250.00
Note on AN31: Eve Browning: Invoice 007620 Building 3D Model of solar farm + Montage progression £11,500.00 LVIA £24,150.00 Photomasking and montages (winter year 1 and summer year 15) £11,500.00 Invoice 007693 LVIA up to submission - £61573.77
Note on AP31: Eve Browning: Invoice 8017 Stage 4 - pre-examination - £9710.25
Note on AQ31: Eve Browning: Invoice 008271 Stage 4 - Pre-examination - £6306.00
Note on AR31: Eve Browning: Invoice 008341 Pre-examination - £2325
Note on AS31: Eve Browning: Invoice 008698 Pre-examination - £6091.25 Additional winter photography, new viewpoints and drone videos/timelapse - £2139
Note on AT31: Eve Browning: Invoice 008759 Review & input to Statement of Common Ground (1,2 and 4-8), Relevant Reps & Visual Receptor Tables (Lot 5 and 6 responses). Scoping meeting for mapping constraints+ arb implications. Reviewing mapping for possible tree impacts. Review of IDB Offsets. £5105.50
Note on AU31: Eve Browning: Invoice 008969 • Progressing relevant reps and SoCGs • Interrelationship and cumulative effects • Hedgerow Removal: Layby Plans • Landscape and Visual Summary Tables • Inspector Viewpoints: Site Visit • Chapter 23: LVIA Inputs • Timetable Review: Following Postponement • Updates to Permissive Plans on Works Plans £11513
Note on AV31: Eve Browning: Invoice 009171 • Preparation of Supplementary Landscape and Visual Summary Tables • Preparation of Hedgerow Removal Plans and updates to oLEMP plans • Updates to NCC/LCC following LVIA Workshop 4 • Natural England Statement of Common Ground response to legal comments • Forestry Commission Statement of Common Ground response to legal comments RIBA 4 - Stage 4 – Pre-examination £7,225.00 Site Visit Expenses £290.97
Note on AW31: Eve Browning: Invoice 009372 Landscape: - Additional ZTV Production - LVIA Summary Tables - DCO Plans - Attendance at Hearing - LVIA Documents for Deadline 1 - LEMP Updates - Hedgerow Removal Plans £11228
Note on AX31: Eve Browning: Invoice 009556 - Deadline 2: LIR Responses - Deadline 2: Review of LVIA Documents - Deadline 2: Wording correlation between oLEMP and LVIA - Deadline 2: Review of submission matters and correlation with planning team - Deadline 2: Review of Relevant Reps - OFH: Attendance and review and follow up - Addressing Legal comments £5500 Expenses - £221.06 Total £6865.27
Note on AY31: Eve Browning: Invoice 009752 Landscape: - Change application - DCO plan updates - Responses to LIR - Response to D2 & D3 submissions - Hedgerow removal plans update - Review/response to written reps RIBA 5 - Stage 5- Examination £10,000.00
Note on AZ31: Eve Browning: Invoice 009971 Landscape: Prep for and attendance at Hearings. Ongoing DTMs. Inter relationships report / review of additional cumulative sites. £12000 Google fly-through - £7000 Expenses - £841.25
Note on BA31: Eve Browning: Invoice 010199 Landscape: Prep for deadline 5. Response to examiners second questions Statement of Common Ground Technical Note Revision Responses to Actions arising from Hearing £12000 Invoice 010213 Landscape: • Item 1 - Site visit with Chris Jackson and Wendy Wright to review the key aspects of the site and to familiarise Wendy Wright with viewpoint locations; £3543 • Item 2 – Meeting with Chris Jackson, Wendy Wright and Mark Topping to undertake a handover of the document locations and to discuss and review hearing questions; £2047 • Item 3 – Mark Topping and Wendy Wright time to review information and prepare for the hearing: £3800 • Item 4 – Attendance at Hearing; £2475 • Item 5 – Post hearing review and discussion with Chris Jackson, Wendy Wright and Mark Topping; £614 Landscape Total - £12,479
Note on BB31: Eve Browning: Invoice 010429 Finalizing SoCGs with Local Authorities (WLDC & LCC) Preparing responses to Written Representations. Preparation for and attendance at Change Application Hearing Updates to Joint Interrelationships Report following Tillbridge Submission £5000
Note on BC31: Eve Browning: Invoice 010670 Landscape: - Preparation of Closing Statements. - Update to Cumulative Assessment – Sturton Solar. - Finalising WLDC Statement of Common Ground. £5000
Note on J32: Eve Browning: Inlcuded within Highways survey
Note on J33: Eve Browning: Original quote for background monitoring 17450/2+ additional £950 for WB5 monitoring station + £650 for scoping + £1250 for ES chapter
Note on AD33: Eve Browning: PEIR £1650, category 3 £1450. finalised modelling and constraints £1800, meetings £425 Invoice 30034718
Note on AN33: Eve Browning: Invoice 784-B031437 / 30052381 ES chapter - £1250 Cable route assessment - £1250 Additional works including scheme amendments - £2650 Meetings - £765
Note on AV33: Eve Browning: Invoice 30066671 Stage 4 - pre-exam fee - £1975
Note on BC33: Eve Browning: Stage 4 : Pre-exam - £1975 Stage 5: Examination - £1950
Note on AG34: Eve Browning: Invoice 006301
Note on AI34: Eve Browning: Invoice 006653 3D modelling - £4000
Note on AM34: Eve Browning: Invoice 007393 3D model and montage progression - £5750
Note on J36: Eve Browning: IGP to write
Note on J37: Eve Browning: Includes half of scoping document cost, screening cost, glint and glare assessment, EIA chapter, stakeholder consultation and technical support
Note on AC37: Eve Browning: Invoice 708094
Note on AD37: Eve Browning: £207.2 invoice 708107 £656 invoice 708186
Note on AE37: Eve Browning: Cat 3 dwellings Invoice 708239
Note on AF37: Eve Browning: Invoice 708325 Project meeting attendance
Note on AL37: Eve Browning: Invoice 708718 Glint and glare technical report - £7950 ES chapter - £2726 Invoice 708753 Technical support (category 3s?) - £1312
Note on AR37: Eve Browning: Invoice 709185 Technical support (RR and SoCG) - £1312
Note on AS37: Eve Browning: Invoice 709218 Relevant reps and SoCG £1325
Note on AT37: Eve Browning: Further RR and SoCG - £1325
Note on AY37: Eve Browning: Invoice 709595 Technical support during examination - £662.50
Note on BA37: Eve Browning: Invoice 709742 Technical support for West Burton Solar Project (examination phase) - £441.66 Invoice 709791 Technical support for West Burton (Examination responses) - £662.50
Note on BB37: Eve Browning: Examination responses
Note on BC37: Eve Browning: Attendance at mock hearing - £1325
Note on AC38: Eve Browning: 6667706
Note on AD38: Eve Browning: Invoice 6673567
Note on AE38: Eve Browning: 6682051
Note on AF38: Eve Browning: Invoice 6689143
Note on AG38: Eve Browning: Invoice 6694886
Note on AH38: Eve Browning: Invoice 6705960
Note on AI38: Eve Browning: Invoice 6712960
Note on AM38: Eve Browning: Invoice GP/691336/07000 Professional fees - £4156.80
Note on AN38: Eve Browning: Invoice 6737453 Professional fees - £28544.80
Note on AO38: Eve Browning: Invoice 6741183 DCO drafting and review - £72837.20
Note on AP38: Eve Browning: Invoice 6748989 West Burton legal advice - £5900.80
Note on AQ38: Eve Browning: Invoice 6758433 DCO legal advice - £2962.00
Note on AR38: Eve Browning: Invoice 6763835 DCO advice - £6463.60 Invoice 6766250 DCO advice - £3509.20
Note on AS38: Eve Browning: Invoice 6773570 Professional fees - £27693.10
Note on AT38: Eve Browning: Invoice 6777645 Professional fees - £75445.10 Disbursements - £544 Invoice 6776258 Professional fees - £17574.40 Invoice 6776260 Professional fees - £32514.40 Disbursements - £379.22 Invoice 6776303 Professional fees - £11134.80 Disbursements - £162.90
Note on BA38: Eve Browning: Invoice 6815630 Professional fees - £200000 Copying and other incidental expenses £2,929.00 Travelling & Subsistence £592.22 Travelling expenses £356.44 £203877.66
Note on AP39: Eve Browning: Sub-consultant amounts (dependent upon what comes up in relevant reps/examination)
Note on AT39: Eve Browning: Counter Context Invoice 204984 - Lincolnshire Showground hire - £2403.25 - Team accommodation - £1358.20
Note on AU39: Eve Browning: Counter Context invoice 205018 Hire of audio visual equipment - £13100
Note on AV39: Eve Browning: Counter Context invoice 205069 - Team accommodation - £3560
Note on AW39: Eve Browning: Counter Context invoice 205111 Hire of AV equipment - £22900 Team accommodation - £1919
Note on AY39: Eve Browning: Invoice 205206 Venue hire for Hemswell Court - Hire of Hemswell Court Ballroom + Breakout Rooms for two days of Hearings and one day setup - Lunches and refreshments £6135 AV supply for Hemswell Court - AV set up for hearings held 23rd and 24th January, including set up and delivery in line with PINS SLA requirements. £30592 Accommodation for West Burton Hearings - Accommodation on behalf of Applicant team at Hilton Doubletree Lincoln for January and February Hearings £7814.88
Note on AZ39: Eve Browning: Counter Context invoice 205243 Venue hire for Thonock Park - Hire of Thonock Park Solheim Suite + Breakout Rooms (Woodland Suite and Thonock Lounge) for four days of Hearings and one day setup - Refreshments £5590 AV supply for Thonock Park - AV set up for hearings to be held at Thonock Park for 5th- 9th February, including set up and delivery in line with PINS SLA requirements. £42739 Additional accommodation for West Burton Hearings - Accommodation for Matthew Smith, Stephen Flynn, Daniel Baird, Neil Fletcher and Robert Roughan on behalf of Applicant team at Hilton Doubletree Lincoln for February Hearings £836
Note on BA39: Eve Browning: Counter Context invoice 205304 Counter Context invoice 205304 AV supply for virtual hearing - AV set up for hearings to be held virtually for 13th and 14th March (overflow of ISH5), including set up and delivery in line with PINS SLA requirements. £9016
Note on BB39: Eve Browning: Invoice 205365 AV supply for virtual hearing - AV set up for hearings to be held virtually for 23 April (Change Application), including set up and delivery in line with PINS SLA requirements £4812
Note on J40: Eve Browning: Counter Context, up to examination stage. Budget assumes £32k at examination stage
Note on Y40: Eve Browning: Invoice 204033
Note on AA40: Eve Browning: Invoice 204139
Note on AC40: Eve Browning: Invoice 204187
Note on AD40: Eve Browning: Invoice 204213
Note on AE40: Eve Browning: Invoice 204308 Includes £34k for statutory notice advertisements
Note on AG40: Eve Browning: Invoice 204340 Ongoing local community and stakeholder engagement support - £4020 Phase Two consultation Stakeholder Engagement - £595 Drafting and design of consultation and publicity materials to print ready - £3500 Consultation event preparation and facilitation - £4000 Digital engagement platform - £2500 Formal Section 42,46 and 48 notification requirements - £5500 Hire of consultation event venues - £375 Print and distribution of PEIR - £6500 Phase Two Consultation Leaflet and Feedback Form - £9460 Consultation Event Materials - £1500 June event expenses - £283.63 Invoice 204341 Ongoing local community and stakeholder engagement support - £4020 Consultation event preparation and facilitation - £2000 ALC consultation extension - £1380 ALC consultation extension - £9550 Upload and hosting of 360 degree digital photography - £275 July event expenses - £34.20
Note on AH40: Eve Browning: Invoice 204378 - Client liaison, meeting attendance and project management - Weekly media monitoring and reporting - Management, recording and reporting of all stakeholder enquiries and ongoing community liaison - Attendance at PINs and stakeholder meetings - Ad hoc media support
Note on AI40: Eve Browning: Invoice INV-2594 Aberfield Positive Influence - £300 - HSC Benefits statement Invoice 204467 - Counter Context - Ongoing local community and stakeholder engagement support - £4020 - Consultation analysis and production of Consultation Summary Report - £3560
Note on AJ40: Eve Browning: Invoice 204469 - Ongoing local community and stakeholder engagement support - £4020 - Consultation Summary Report - £4500
Note on AK40: Eve Browning: Invoice 204524 Ongoing local community and stakeholder engagement support - Client liaison, meeting attendance and project management - Weekly media monitoring and reporting - Management, recording and reporting of all stakeholder enquiries and ongoing community liaison - Attendance at stakeholder meetings - Ad hoc media support £4020
Note on AL40: Eve Browning: Invoice 204588 Ongoing local community and stakeholder engagement support - Client liaison, meeting attendance and project management - Weekly media monitoring and reporting - Management, recording and reporting of all stakeholder enquiries and ongoing community liaison - Attendance at stakeholder meetings - Ad hoc media support £2010
Note on AN40: Eve Browning: Invoice 204712 Consultation report - £9080
Note on AO40: Eve Browning: Invoice 204760 - Ongoing comms support - £2564 - Development and delivery of acceptance comms strategy and statutory requirements - £1992 - Section 56 print, postage and distribution - £8150 - Placement of S56 notices - £26000
Note on AQ40: Eve Browning: Invoice 204809 Ongoing comms support - £2564.00
Note on AR40: Eve Browning: Invoice 204867 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Support for media enquiries - Media monitoring
Note on AS40: Eve Browning: Invoice 204921 Ongoing comms support - £2564 Relevant representations - £700
Note on AT40: Eve Browning: Invoice 204984 - Ongoing comms support - £2564 - Drafting of Rule 13(6) Notice - £1540 - Publication of Rule 13(6) Notice - £8150 - Logistical support to organise hearings - £2600 - Travel and subsistence expenses - £31.10
Note on AU40: Eve Browning: Invoice 205018 Ongoing comms support - £2564 Attendance at prelim meeting and hearings - £1260 Car parking - £9.20
Note on AV40: Eve Browning: Invoice 205069 - Ongoing comms support - £2564 - Publication of Rule 13(6) notice - £8150
Note on AW40: Eve Browning: Invoice 205111 - Ongoing comms support - £2564 - Attendance at hearings - £2448 - Expenses - £127.63
Note on AX40: Eve Browning: Invoice 205149 Ongoing comms support plus £480 for hearings preparation support and notice drafting - £3044
Note on AY40: Eve Browning: Invoice 205206 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Support for media enquiries - Media monitoring - Drafting and organisation of West Burton Rule 6 Notice £2564 West Burton Rule 6 Notice - Placement of Notice for one week in the Lincolnshire Echo and the Retford Times - Print and Postage of Notice to local information points £9224.75 Attendance at Hearings Account Executive attendance at Hearings. Charged at two days to cover venue check and setup on Monday 22nd, DCO hearing on 23rd and OFH on 24th. £768 Expenses - Train tickets for MOS to attend hearings - Subsistence during hearing days - Taxi to venue for venue check and setup £78
Note on AZ40: Eve Browning: Invoice 205243 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Support for media enquiries - Media monitoring - Drafting and organisation and mailout of West Burton Change Application and Rule 6 Notice £2948 West Burton Change Application Notice and Cover Letter - Print and Postage of Notice to identified consultees - Placement of Notice for one week in the Guardian and the London Gazette - Placement of Notice for two weeks in the Lincolnshire Echo and the Retford Times £25796 West Burton Rule 6 Notice - Placement of Notice for ISH5 (on postponed items of ISH3) for one week in the Lincolnshire Echo and the Retford Times - Print and Postage of Notice to local information points £8250 Attendance at Hearings Account Executive attendance at Hearings. Charged at three days to cover venue check and setup on Monday 5th, CAH hearing on 6th, ISH 3 on 7th and ISH 4 on 8th £1152 Expenses - Train tickets for MOS to attend hearings - Subsistence during hearing days - Taxi to venue for venue check and setup £43
Note on BA40: Eve Browning: Invoice 205304 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Support for media enquiries - Media monitoring - Drafting and organisation and mailout of West Burton Change Application Notification of Hearings Notice -Attendance at Virtual Hearing for West Burton ISH £2566 West Burton Rule 6 Notice - Placement of Notice publicising Change Application virtual hearing for one week in the Lincolnshire Echo and the Retford Times - Print and Postage of Notice to local information points £8300
Note on BB40: Eve Browning: Invoice 205365 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Support for media enquiries - Media monitoring - Attendance at Virtual Hearing for West Burton Change Application £2566
Note on BC40: Eve Browning: Invoice 205445 Single fee for limited support up to determination decision, including: - hosting of communications lines (freephone, freepost, email and website, including renewals where necessary). - handling of limited enquiries and team liaison. £1335
Note on J41: Eve Browning: 12 days at £960/day Additionally up to 10 days required at examination
Note on AE41: Eve Browning: Invoice 0923-2206-1
Note on AL41: Eve Browning: Invoice 0923-2212-1 Final Statement of Need for DCO submission
Note on AT41: Eve Browning: Invoice 0923-2309-1 Relevant representation responses - £840
Note on AW41: Eve Browning: Invoice 0923-2312-1 Relevant representation responses, Issue Specific Heaing preparation and attendance, written summaries and actions arising - £4080
Note on AY41: Eve Browning: Invoice 0923-2402-1 West Burton Solar RRs, FWQ, WRs & DL4 responses, ISH 3 preparation & virtual attendance - £3120
Note on BC41: Eve Browning: Invoice 0923-2405-1 West Burton Solar Examination support including DL4 - DL5 submissions and responses ExQs £960
Note on J42: Eve Browning: Including Broxholme for £250
Note on J44: Eve Browning: Atkins
Note on K44: Eve Browning: Centremaps
Note on AC44: Eve Browning: Invoice UK-CI-036630
Note on J45: Eve Browning: Pager Power
Note on J46: Eve Browning: Delta Simons. Excludes cable route and substation site, which will require to be done at a later date
Note on AE46: Eve Browning: Invoice DS033209
Note on AF46: Eve Browning: West Burton substation and cable search area Envirocheck report and PRA Invoice DS034022
Note on Z47: Eve Browning: Savills Invoice INSU00190063
Note on AL47: Eve Browning: Invoice INSU00292963 Professional fees incurred with The Henry Smith Charity’s land at West Burton 4 for the period to 30/09/2022
Note on AH48: Eve Browning: Invoice 153786
Note on AN48: Eve Browning: Invoice 157399 West Burton DAS advice - £1650
Note on AD49: Eve Browning: Proforma SF.4032395
Note on AF49: Eve Browning: Meeting attendance Invoice 22009769
Note on AY49: Eve Browning: Bureau Veritas invoice 24002226 Daniel Clampin attendance at Issue Specific Hearing for Climate Change - £1935
Note on BC49: Eve Browning: Invoice 24007112 Daniel Clampin Remote attendance at Issue Specific Hearing 5 for Climate Change - £995
Note on AI50: Eve Browning: JSM invoice SI31555
Note on AM50: Eve Browning: Invoice SI400248 Feasibility studies, engineering drawings and advice - £1451.67
Note on AN50: Eve Browning: Invoice SI400528 Cable route engineering advice - £3660.75
Note on AP50: Eve Browning: Invoice SI400859 GPR road survey - £9860.80 Ongoing design advice - £2508.49
Note on AT50: Eve Browning: Invoice SI402427 Bailey bridge/culvert analysis - £1084.60 Invoice SI402521 Feasibility study (May to Aug 2023) - £2169.20 Invoice SI402531 Feasibility study (Feb to May 2023) - £1626.90
Note on AV50: Eve Browning: Invoice SI403463 Cable route queries - £271.15
Note on AX50: Eve Browning: Invoice SI403954 Cable route queries £542.30
Note on BA50: Eve Browning: Invoice SI405312 Cable route advice - connection at West Burton Power Station - £271.15
Note on AL51: Eve Browning: Invoice WBSP-001 Engineering consultancy and advisory service
Note on AH52: Eve Browning: Invoice 1860GV003976 Ecology surveys on EDF land £1500 per access, plus £2000 licence entry fee
Note on AI53: Eve Browning: Invoice INV-3069 Solar Energy UK
Note on AT53: Eve Browning: Invoice INV-3569 NSIP Forum membership - £10000
Note on AI54: Eve Browning: Paid to Pinsent Masons NGET NG Gas NPG WPD Anglian Water Uniper All circa £3k each
Note on AT54: Eve Browning: £2158.20 Canal and Rivers Trust authorised
Note on AW54: Eve Browning: Gross interest paid in - £189.53
Note on AX54: Eve Browning: Gross interest paid in - £66.14
Note on AY54: Eve Browning: Weightmans invoices for negotiating Northern Powergrid's protective provisions: - 02198118 £623.70 - 02176756 £686.07 - 02160111 £83.16
Note on AZ54: Eve Browning: Cadent protective provisions Gowling WLG - £1869.70
Note on BA54: Eve Browning: Pinsent Masons request for payment LO1405 £2000 CMS invoice 1000-0184260 Negotiating EDF protective provisions - £2495.94 CMS invoice 1000-0187466 Negotiating NGET protective provisions - £5922.50 Osborne Clark completion statement AHPK/1236322 Negotiating NGED protective provisions £2500
Note on BB54: Eve Browning: Burges Salmon invoice 100262713 UKAEA protective provisions negotiation £2626 Weightmans invoice 02232691 Northern Powergrid (Yorkshire) protective provisions negotiation £1309.50 CMS invoice 1000-0201948 Cadent Gas protective provisions negotiation £5299.90
Note on BC54: Eve Browning: CMS Cameron McKenna Nabarro Olswang LLP invoice 1000-0201774 Negotiation of EDF protective provisions £629.34 Weightmans LLP invoice 02253177 Negotiation of Northern Powergrid protective provisions £395.01 CMS Cameron McKenna Nabarro Olswang LLP invoice 1000-0206509 Negotiation of NGET protective provisions and side agreement £5299.90
Note on BD54: Eve Browning: CMS Cameron McKenna Nabarro Olswang LLP invoice 1000-0206509 Fees for negotiation of NGET protective provisions - £5299.90 Further cost of £3000 agreed to take up to completion
Note on BE54: Eve Browning: Pinsents request for payment LO1448 UKAEA legal costs - £25000
Note on AQ55: Eve Browning: Invoice INV-2021 (Dalcour Maclaren) Initial payment request for works associated with West Burton Substation - £5344.32 - Subsequently refunded as not required
Note on AK56: Eve Browning: Invoice 6722956
Note on AX57: Eve Browning: Invoice 1533 - Technical review of battery fire safety management plan. Review process includes meetings, document analysis (OBSSMP + Fire note), content recommendations & amendments (OBSSMP + Fire note), ERP content template for OBSSMP £1400 - Expert witness content preparation £600 Total £2000
Note on AY57: Eve Browning: Invoice 1537 Expert witness content preparation Hours x West Burton DCO written submission content preparation, DCO hearing preparation and FRS engagement and meeting - £2200
Note on AZ57: Eve Browning: Invoice 1543 - Flat rate for DCO hearing attendance - £1600 - Mileage - £121.95 - 2 Hours x DCO meeting, submissions and hearing content provision - £400 - Review process includes FRS meeting, FRS engagement, site design review for FRS access and safety requirements - £800 Total £2921.95
Note on BA57: Eve Browning: DCO content provision - £4000 Ad hoc provision - £1600
Note on AA59: Eve Browning: PROW searches
Note on AZ60: Eve Browning: Arch (GeoPhys) £ 539.28 Arch (Trial Trenching) £ 5,625.21 Arch (Landowner Fees) £ 1,513.62 Arch (LIDAR) £ 260.76 Total £ 7,938.87
Note on J61: Eve Browning: Dalcour Maclaren, quote includes expenses and post DCO submission work. Added on 20.10.21 secondary quote for further works + £650 for highways searches + half of addional quote 12.11.21 +12472 additional predicted spend (Rob Jones budget review email)
Note on K61: Eve Browning: RSK estimated between £103k to £188k for each project, this figure is in the middle. Based upon new cable routes
Note on Y61: Eve Browning: Invoice no: UK-CI_006084
Note on AC61: Eve Browning: Invoice UK-CI-036630
Note on AE61: Eve Browning: Invoice UK-CI-049776
Note on AF61: Eve Browning: Invoice UK-CI-058026
Note on AG61: Eve Browning: Invoice UK-CI-065076
Note on AH61: Eve Browning: Invoice UK-CI-069024
Note on AI61: Eve Browning: Invoice UK-CI-079050
Note on AJ61: Eve Browning: Invoice UK-CI-084174 - £3000
Note on AK61: Eve Browning: Invoice UK-CI-094476
Note on AL61: Eve Browning: Invoice UK-CI-099120 Land agency services - £2783.15
Note on AM61: Eve Browning: Invoice UK-CI-109728 Land agency services - £18247.71
Note on AN61: Eve Browning: Invoice UK-CI-115170 Book of reference preparation - £27978.75 Invoice UK-CI-126240 Land agency services - £15111.92
Note on AP61: Eve Browning: Invoice UK-CI-130452 Land agency services - £4129.35
Note on AQ61: Eve Browning: Invoice UK-CI-138000 Land agency services - £6319.55
Note on AR61: Eve Browning: Invoice UK-CI-147336 Land agency services - £1695.35
Note on AS61: Eve Browning: Invoice UK-CI-155274 Land agency services - £1121.25
Note on AT61: Eve Browning: Invoice UK-CI-163056 Land agency services - £1952.25
Note on AU61: Eve Browning: Invoice UK-CI-171402 Land agency services - £1751.75
Note on AV61: Eve Browning: Invoice UK-CI-179844 Land agency services - £4513.50
Note on AW61: Eve Browning: Invoice UK-CI-185634 Land referencing including Book of Reference refresh for deadlines - £6884.01
Note on AX61: Eve Browning: Invoice UK-CI-194028 Land agency services - £5287.04
Note on AY61: Eve Browning: Invoice UK-CI-200220 Land agency services - £9489.11
Note on AZ61: Eve Browning: Invoice UK-CI-208896 Land agency services - £5782.06
Note on BA61: Eve Browning: Invoice UK-CI-216186 Land agency services £2158.81
Note on BB61: Eve Browning: Invoice UK-CI-225510 Atkins Utility refresh - £3388 Land referencing and expenses - £4259.42
Note on BC61: Eve Browning: Invoice UK-CI-234444 Land agency services - £1422.53
Note on BI61: Eve Browning: Thank you for contacting us regarding the service of your s134 Notices. We have reviewed the Section’s requirements and detail our quote below: • HMLR Title Refresh and Registered Company Address checks • Mail merge of s134 documents, including a letter and s134 Notice • Quality assurance reviews of the statutory documents prior to posting • Preparation of site notices • Erection of site notices • Maintenance of site notices for 6 weeks • Removal of site notices • Project management including meetings Our quote assumes that the s134 Notice and associated letter templates will be provided to us. We would use the same notice locations as those at s56 (no more than 5km apart is good practice) and a site notice will be erected for all unregistered land. The cost to prepare and issue the above documentation is £7300.00 excluding expenses. Expenses will include: • HM Land Registry costs • External printing • Postage costs (we would recommend sending recorded) • Mileage Expenses estimate £2700
Note on AC62: Eve Browning: Invoice: INSU00215674
Note on AD62: Eve Browning: Invoice INSU00223397
Note on AE62: Eve Browning: Invoice INSU00230104
Note on AF62: Eve Browning: Invoice INSU00241063 Land agency work, project management, mileage
Note on AG62: Eve Browning: Invoice INSU00246662
Note on AH62: Eve Browning: Invoice INSU00254912 Land agency and project management
Note on AI62: Eve Browning: Invoice INSU00263959
Note on AJ62: Eve Browning: Payment Request for licences - 2022/002WB - £3000 Invoice INSU00273529 - £1957.50
Note on AK62: Eve Browning: Invoice INSU00293463 Land agency services - £1335
Note on AL62: Eve Browning: Invoice INSU00298578 Land agency services - £792.5
Note on AM62: Eve Browning: Invoice INSU00300886 (Savills) Land agency services - £451.25 Invoice UAI-23-08804 (Bruton Knowles) HoTs negotiations - £1211.65
Note on AN62: Eve Browning: Invoice UAI-23-09052 (Bruton Knowles) HoTs issue to landowners - £6903.69
Note on AO62: Eve Browning: Invoice UAI-23-09335 HOTs data processing and plan production - £5898.75
Note on AP62: Eve Browning: Invoice UAI-23-09871 (Bruton Knowles) HoTs negotiation - £4356.50
Note on AQ62: Eve Browning: Invoice UAI-23-09873 HoTs negotiation - £4900.25
Note on AR62: Eve Browning: Invoice UAI-24-10185 HoTs negotiation - £6160.50
Note on AS62: Eve Browning: Invoice UAI-24-10536 Bruton Knowles HoTs negotiation - £5160
Note on AT62: Eve Browning: Invoice UAI-24-10792 HoTs negotiations - £7191.25
Note on AU62: Eve Browning: Invoice UAI-24-10962 Cable route land negotiations - £5752.50
Note on AV62: Eve Browning: Invoice UAI-24-11213 HoTs negotiation - £4375 Expenses - £12
Note on AW62: Eve Browning: Invoice UAI-24-11581 Cable route negotiations and access licences - £7578.75
Note on AX62: Eve Browning: Bruton Knowles invoice UAI-24-11878 Cable route landowner negotiations - £2208.75
Note on AY62: Eve Browning: Invoice UAI-24-12438 Land agency services - £7889 Expenses - £3
Note on AZ62: Eve Browning: Bruton Knowles Invoice UAI-24-12605 Land agency services - £6990.75 Savills refund from client account Unused money for survey access payments returned from client account - £5387.34
Note on BA62: Eve Browning: Invoice UAI-24-13027 Land agency services £3269
Note on BB62: Eve Browning: Invoice UAI-24-13303 Land agency services £1840
Note on BC62: Eve Browning: Invoice UAI-24-13641 Easement negotiations, project meetings - £1922.50
Note on BD62: Eve Browning: Invoice UAI-24-13885 Land agency services - £3132.75 Expenses - 119.25 Total - £3252
Note on AC63: Eve Browning: Paid to Savills client account after Request for Payment
Note on AJ63: Eve Browning: Payment Request: Landowner access payments (surveys and access licences)
Note on AN63: Eve Browning: JAS Martin & Co invoice RDS/sab/V0882 HoTs incentive payment for: - Ann Marie Lobley - £500
Note on AQ63: Eve Browning: Invoice EM/SR/S.59 Perkins George Mawer & Co Option incentive fee - 1.0/2.0 Thomas Carl Sutcliffe
Note on AU63: Eve Browning: FGP Chartered Surveyors Invoice 25242 16.0 Canal and River Trust - agent fee - £1200
Note on AX63: Eve Browning: Fisher German Invoice 2125111 Ref: 15.0 Cottam Farming Agent fees £1418.85 Mileage £56.25 Total £1475.10
Note on AY63: Eve Browning: Invoice 1800050950 27.0 Church Commissioners Incentive for signing the Heads of Terms £1000 Invoice 1800050949 21.0 Church Commissioners Incentive for signing the Heads of Terms - £1000
Note on AQ64: Eve Browning: Invoice 3145405 - Walker Morris Counsel’s fees incurred for provision of an opinion letter on the Cottam/West Burton cable route - £3300
Note on AZ64: Eve Browning: Walker Morris invoice 316319 - Cable reporting - £6500 - Disbursements - Index map search - £52 - Office copy entries - £105
Note on BA64: Eve Browning: Pinsent Masons quote for Network Rail property agreements
Note on C65: David Elvin: Doesn't include costs to date 08/07/21
Note on D65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Forsight contingency
Note on AM67: Eve Browning: Blick Rothenburg invoice 2063633 Annual charge for the year to 31 December 2023 in respect of company registrar services, including maintenance of the companys statutory books, preparation and filing with the Registrar of Companies of the Confirmation Statement and notifications of any changes in respect of the companys officers and registered office, in accordance with the information and particulars supplied to us - £500 Annual confirmation statement filing fee - £13
Note on AX67: Eve Browning: Shakespeare Martineau invoice 100161055 Professional Charges for preparing and filing a UK Trade Mark Application for the WEST BURTON SOLAR PROJECT device - £900
Note on D69: David Elvin: Forsight total incl contingency

## Cottam
2023
Cottam Budget Cost | time axis 2021-01-01 to 2024-09-30
[17 empty] | Month |  |  | Work commences | [19 empty] | App submitted | [13 empty] | Examination close | [5 empty] | Decision due
Item | Consultant | Sub-Item | Arcus | Pegasus | Original Budget (£) | Updated budget (£) Jan 2022 | Invoices and forecast total (£) | Pre-submission total (£) | Post-submission total (£) | Variance - original budget to updated | Quote 1 | Quote 2 | Quote 3 | Quote 4 | Commissioned consultant work | Cost to date (17/12/2021) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Grid |  | NGET Application |  |  | 65000 | 115000 | 65400 | 65400 | 0 | -400 | [5 empty] | 65400
| Omnia | Consultants |  |  | 25000 | 31078.22 | 44669.94 | 42807.68 | 1862.26 | -19669.94 | 45025 |  |  |  | 45025 | 30540.32 | Work commences 12: 537.9; Work commences 13: 1235.21; Work commences 14: 621.27; Work commences 15: 892.34; Work commences 16: 621.27; Work commences 17: 613.95; Work commences 18: 482.07; Work commences 19: 3932.72; Work commences 20: 1181.51; Work commences 21: 819.34; Work commences 22: 1166.65; App submitted 24: 163.13; App submitted 26: 947.01; App submitted 27: 113.25; App submitted 28: 56.63; App submitted 30: 459.3; App submitted 31: 119.55; App submitted 32: 50.33 | 116.19
| National Grid | Deposit/security |  |  | 25000 | 25000 | 18000 | 53737.5 | -35737.5 | 7000 | [5 empty] | 0 | Work commences 12: 3000; Work commences 16: 50737.5; App submitted 27: -50737.5 |  |  | 15000
|  | Auxiliary connection applications |  |  | 0 | 3660 | 53700 | 900 | 52800 | -53700 | [5 empty] | 0 | Work commences 19: 300; Work commences 20: 600 | [6 empty] | 15000 | 37800
| Network Rail | Network Rail BAPA |  |  | 0 | 0 | 88760.73 | 23264.03 | 65496.7 | -88760.73 | [5 empty] | 0 | Work commences 18: 14886.69; Work commences 20: 8377.34; App submitted 26: 29228.32; App submitted 32: 36268.38
Lease/Option |  |  |  |  | 150000 | 151500 | 166128.8 | 160664.4 | 5464.4 | -16128.8 | [5 empty] | 150000 | Work commences 12: 1500; Work commences 14: 768; Work commences 15: 5306.8; Work commences 17: 1578.4; Work commences 19: 1511.2; App submitted 26: 5464.4
Planning Consultant | Lanpro |  |  | 128000 | 400000 | 410397 | 1156885.6233 | 551398.84 | 605486.7833 | -756885.6233 |  |  |  |  | 1156885.6233 | 146043 | [10 empty] | 19685 | 19685 | 19685 |  | 19062.38 | 21135.55 | 29800 | 22548.86 | 19500 | 21700.17 | 20605.08 | 41508.25 | 42804.75 | 107635.8 | 5500 | 18895.5 | 9579.25 | 26860.69 | 53054.5 | 55899.95 | 34147.45 | 34910.72 | 55206 | 65795.76 | 55586 | 52260.95 | 35030.18 | 71111 | 15329 |  |  |  | 12986.5 | 3333.3333
Pinsent Masons Project Management | Pinsent Masons |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
Planning Application Fee | Lincolnshire County Council, Nottinghamshire County Council, West Lindsey District Council | Performance Agreements |  |  | 78000 | 100000 | 162112.25 | 35197.25 | 126915 | -84112.25 | [5 empty] | 0 | Work commences 16: 6423.25; Work commences 20: 9672; App submitted 24: 19102; App submitted 33: 23585 |  |  |  | 33330 | 70000
| Planning Inspectorate | Planning Inspectorate |  |  | 597000 | 597000 | 502852 | 7488 | 495364 | 94148 | [5 empty] | 0 | Work commences 23: 7488; App submitted 26: 35844; App submitted 32: 229760 |  | 229760
Planning Studies | Lanpro | Heritage Statement |  | 4500 | 30000 | 23000 | 382401.86 | 205707.24 | 176694.62 | -352401.86 | 23750 |  |  |  | 23750 | 15000 | [11 empty] | 750 |  | 1943.75 | 3747.5 | 3750 | 17750 | 7234.33 | 11100 | 30487.5 | 12500 | 34695.5 | 30468.25 | 36280.41 |  | 3395 | 5437.5 | 8750 | 8750 | 18685 | 19969.5 | 6654.75 | 6950 | 8771.35 | 16197.5 | 28378.46 | 14535.06 | 11975 | 4090 |  |  | 4718.5 | 4718.5 | 4718.5
| Daniel Baird Soils | ALC Classification |  | 3250 | 45000 | 34000 | 48648 | 38648 | 10000 | -3648 | 29100 | 59537 | 32850 | 33375 | 29100 | 20000 | Work commences 14: 15840; Work commences 16: 1808; Work commences 17: 1000 |  |  | 10000
|  | Agricultural circumstances |  |  | 0 | 0 | 8237.7 | 4000 | 4237.7 | [6 empty] | 0 | App submitted 24: 4000; App submitted 29: 4237.7
|  | Topographical Study |  | 5000 | 45000 | 62900.4 | 65225.4 | 65225.4 | 0 | -20225.4 | 59750 | 31920 | 10675 | 48290 | 59750 | 46341.29 | Work commences 11: 3949.54; Work commences 12: 12609.57; Work commences 18: 2325
| Mabbett / Delta Simons | Flood Risk Assessment |  | 4000 | 50000 | 16900 | 29230 | 18380 | 10850 | 20770 | 26700 | 12150 |  |  | 26700 | 2250 | Work commences 12: 3250; Work commences 17: 6960; Work commences 18: 2000; Work commences 19: 1720; App submitted 24: 2200; App submitted 25: 630; App submitted 30: 720; App submitted 33: 2875 |  |  |  | 3125 | 3500
|  | Geophysical Survey |  |  | 200000 | 264897.75 | 343962.5 | 341937.5 | 2025 | -143962.5 | 246175 | 264897 |  |  | 264897 | 225202.5 | Work commences 12: 3728.25; Work commences 13: 13169.25; Work commences 14: 31500; Work commences 15: 13950; Work commences 16: 2475; Work commences 17: 6844.5; Work commences 18: 19193; Work commences 19: 14400; Work commences 21: 10800; Work commences 22: 675; App submitted 34: 2025
|  | Geophysical Survey (cable route overlap) |  |  | 0 | 0 | 35281.42 | 35281.42 | 0 | [6 empty] | 0 | Work commences 15: 17104; Work commences 16: 1300; Work commences 19: 2000; Work commences 21: 3700; Work commences 22: 675; Work commences 23: 10502.42
|  | Trial Trenching |  |  | 150000 | 160000 | 997574.38 | 831779.38 | 165795 | -847574.38 | [5 empty] | 0 | Work commences 19: 306448.95; Work commences 20: 146829.08; Work commences 21: 195396.25; Work commences 22: 54661; Work commences 23: 32065; App submitted 24: 96379.1; App submitted 33: 500; App submitted 36: 500 | [8 empty] | 164795
| Tetratech | Air Quality |  | 2900 | 5000 | 4375 | 25575 | 6400 | 19175 | -20575 | 4375 |  |  |  | 25575 | 0 | Work commences 11: 650; Work commences 16: 4500; App submitted 24: 1250; App submitted 30: 1250; App submitted 33: 7350; App submitted 34: 3950; App submitted 35: 2700 |  | 1950 |  | 1975
| Ted Clover | Minerals & deposits |  |  | 0 | 3750 | 8190 | 6480 | 1710 | -8190 | 3750 |  |  |  | 3750 | 2000 | Work commences 17: 1520; Work commences 23: 2720; App submitted 24: 240; App submitted 31: 665 |  |  | 1045
|  | Arboricultural Survey |  | 4900 | 50000 | 35000 | 0 | 0 | 0 | 50000 |  |  |  |  | 0 | 0
| TPA | Highways Survey |  | 3500 | 40000 | 57000 | 126226.27 | 94026.27 | 32200 | -86226.27 | 5950 | 26300 | 57000 |  | 57000 | 15700 | Work commences 12: 2755; Work commences 13: 3522.5; Work commences 14: 6947.86; Work commences 15: 1810; Work commences 16: 5985; Work commences 17: 5197.5; Work commences 19: 6000; Work commences 20: 8980; Work commences 21: 11002.5; Work commences 23: 8000; App submitted 24: 18125.91; App submitted 28: 1750; App submitted 29: 1250; App submitted 30: 2250; App submitted 32: 1750; App submitted 33: 1250; App submitted 34: 4000; App submitted 35: 5000; App submitted 36: 6000 | 4000 | 2500 | 2450
| Wynns | Abnormal loads |  |  | 0 | 7245 | 45211.63 | 18723.1 | 26488.53 |  | 7245 |  |  |  |  | 0 | Work commences 14: 1025.25; Work commences 15: 2182.5; Work commences 16: 1912.5; Work commences 17: 1912.5; Work commences 20: 2260; Work commences 21: 3925.35; Work commences 22: 2996.25; App submitted 24: 2508.75; App submitted 26: 1425; App submitted 28: 7707.5; App submitted 29: 3120.52; App submitted 30: 5200.87; App submitted 31: 4334.06; App submitted 32: 2600.43; App submitted 34: 1213.54 |  |  | 886.61
| Clarkson and Woods | Ecological Survey |  | 43500 | 175000 | 306137.15 | 331402.15 | 306821.15 | 24581 | -156402.15 | 306137 |  |  |  | 306137 | 130434.15 | Work commences 12: 24008.5; Work commences 14: 8010; Work commences 15: 8334.5; Work commences 16: 24041; Work commences 17: 39876; Work commences 18: 24442; Work commences 19: 19960; Work commences 23: 23840; App submitted 24: 3875; App submitted 29: 6355; App submitted 30: 2375; App submitted 34: 7802; App submitted 36: 5293 |  |  | 2756
|  | Environmental Masterplan |  |  | 18000 | 17236 | 31592.5 | 31592.5 | 0 | -13592.5 | 25000 |  |  |  | 25000 | 8665 | Work commences 16: 857.5; Work commences 17: 2500; Work commences 18: 1087.5; Work commences 19: 1125; Work commences 20: 10500; Work commences 22: 1000; Work commences 23: 3727.5; App submitted 24: 2130
| Lanpro | LVIA |  | 5600 | 145000 | 141317 | 612346.2 | 409559.18 | 202787.02 | -467346.2 | 143000 |  |  |  | 143000 | 14950 | [12 empty] | 7905 | 2500 | 13998 | 15167.25 | 8050 | 17360.98 | 19446.75 | 24000 | 34200 | 70497.05 | 46519 | 134965.15 |  | 11195 | 1552.5 | 12318.75 | 13256.25 | 15423 | 12044.75 | 11060 | 8453 | 13566.88 | 9443 | 54313.78 | 15280.11 | 8600 | 5000 |  |  | 3760 | 3760 | 3760
|  | CTMP |  |  | 37500 | 0 | 0 | 0 | 0 | 37500 | 0 |  |  |  | 0 | 0
| Tetratech | Noise |  |  | 13000 | 10625 | 36705 | 18520 | 18185 | -23705 | 10625 |  |  |  | 10625 | 3500 | Work commences 11: 2350; Work commences 16: 6675; App submitted 24: 5995; App submitted 34: 3950; App submitted 35: 3850; App submitted 36: 5500 |  | 2910 |  | 1975
|  | 3D model |  |  | 45000 | 0 | 38238 | 38238 | 0 | 6762 |  |  |  |  | 0 | 0 | Work commences 20: 6000; Work commences 21: 23000; Work commences 22: 6363; Work commences 23: 2875
|  | Cumulative Impact |  |  | 6500 | 0 | 0 | 0 | 0 | 6500 |  |  |  |  | 0 | 0
|  | Funding Statement |  |  | 13000 | 0 | 0 | 0 | 0 | 13000 | 0 |  |  |  | 0 | 0
| Pager Power | Glint/Glare |  |  | 28000 | 24222.2 | 36139.7 | 27194.7 | 8945 | -8139.7 | 19170 |  |  |  | 19170 | 2904.2 | Work commences 12: 177; Work commences 15: 8955.2; Work commences 16: 656; Work commences 17: 354.6; Work commences 18: 88.65; Work commences 21: 12001; App submitted 24: 2058.05; App submitted 27: 662.5; App submitted 28: 1657.5; App submitted 29: 1325; App submitted 30: 993.75; App submitted 31: 331.25; App submitted 36: 1987.5 | 1987.5
| Pinsent Masons | Legal DCO drafting |  | 150000 | 350000 | 350000 | 548083.46 | 328004.7 | 220078.76 | -198083.46 |  |  |  |  | 548083.46 | 36001.8 | Work commences 13: 1665.5; Work commences 15: 4295.5; Work commences 16: 4521.6; Work commences 17: 7694.4; Work commences 18: 9476.4; Work commences 19: 4794; Work commences 21: 31556.8; Work commences 22: 37862.8; Work commences 23: 34276; App submitted 24: 155859.9; App submitted 27: 6883.05; App submitted 28: 9099.2 |  | 204096.51
| Counter Context | Examination Phase costs |  |  | 340000 | 340000 | 109120.06 | 0 | 109120.06 | 230879.94 | [5 empty] | 0 | App submitted 32: 7691.06; App submitted 33: 25700; App submitted 36: 60752 | 165 | 14812
| Counter Context | Consultation / PR / website |  | 56000 | 227000 | 189194.35 | 356556 | 197944.96 | 158611.04 | -129556 | 196802.5 |  |  |  | 196802.5 | 45154.35 | [10 empty] | 4035.21 | 3520 | 7580 |  | 4220 | 9553.17 | 41703 |  | 46949.23 | 4020 | 8520 | 7580 | 4020 | 11090 | 47174 | 2564 | 2564 | 3964 | 2564 | 13282 |  | 5257.65 | 4685.9 | 2564 | 11789 | 6587.49 | 40898 | 10816 | 2566 | 1335
| Humbeat | Statement of Need |  |  | 0 | 11520 | 13650 | 8550 | 5100 | -13650 | 11520 |  |  |  | 11520 | 2460 | Work commences 17: 2250; Work commences 23: 3840; App submitted 32: 1320; App submitted 35: 1920 | 1860
|  | Utilities Digitisation |  |  | 0 | 9975 | 9975 | 9975 | 0 | -9975 | 9975 |  |  |  | 9975 | 9975
|  | Cable route utilities |  |  | 0 | 16167 | 17781.6 | 17781.6 | 0 | -17781.6 | 16167 | 17810 |  |  |  | 0 | Work commences 15: 17781.6
|  | Electromagnetic fields |  |  | 0 | 5590 | 1260 | 1260 | 0 | -1260 | 5590 |  |  |  | 5590 | 0 | Work commences 12: 1260
| Delta Simons | Contaminated land |  |  | 0 | 17145 | 29945 | 29945 | 0 | -29945 | 17145 |  |  |  | 17145 | 17145 | Work commences 17: 3000; Work commences 18: 9800
|  | Natural England DAS |  |  | 0 | 5000 | 1210 | 1210 | 0 | -1210 | 5000 |  |  |  |  | 0 | Work commences 20: 1210
| Bureau Veritas | Climate change |  |  | 0 | 0 | 11587 | 4835 | 6752 | -11587 | [5 empty] | 0 | Work commences 16: 1642; App submitted 24: 3193; App submitted 34: 732; App submitted 36: 6020
| JSM | Cable route engineering design |  |  | 0 | 0 | 36771.11 | 26212.55 | 10558.56 | [6 empty] | 0 | Work commences 21: 12060.88; App submitted 24: 14151.67; App submitted 32: 4338.39; App submitted 36: 542.3 | 542.3 |  |  | 135.57 |  | 5000
|  | EDF survey licence |  |  | 0 | 0 | 5000 | 5000 | 0 | [6 empty] | 0 | Work commences 20: 5000
|  | NSIP forum membership |  |  | 0 | 0 | 20000 | 10000 | 10000 | 0 | [5 empty] | 0 | Work commences 21: 10000; App submitted 32: 10000
|  | Construction timescales/waste/worker numbers |  |  | 0 | 0 | 4300 | 4300 | 0 | [6 empty] | 0 | Work commences 21: 3300; Work commences 22: 1000
| Pinsent Masons | Protective provisions third party legal costs |  |  | 0 | 0 | 90000 | 30000 | 60000 | [6 empty] | 0 | Work commences 21: 30000; App submitted 26: 60000
|  | Co-operation agreement |  |  | 0 | 0 | 6450.18 | 6450.18 | 0 | 3225.09 | 2150.06 | 1075.03 | 1075.03 | 1075.03 | 1075.03 | 1075.03 | Month 1: 1075.03; Month 2: 1075.03; Month 3: 1075.03; Work commences 4: 1075.03; Work commences 23: 1075.03
| BST&T | Batteries |  |  | 0 | 0 | 19415.2 | 0 | 19415.2 | [7 empty] | App submitted 33: 8400; App submitted 35: 5600; App submitted 36: 3515.2 | 1400 | 500
| Tribus / Recurrent Energy | Tillbridge survey refund |  |  | 0 | 0 | -137315.72 | 0 | -137315.72 | [43 empty] | -137315.72 | bar: Month 1 to Work commences 4
Professional services | Dalcour Maclaren | Land Referencing (DM) |  |  | 150000 | 129771.36 | 416546.31 | 309492.74 | 107053.57 | -266546.31 | 129771.08 | 145000 |  |  | 129771.08 | 16085.11 | [10 empty] | 18440.58 | 7253.5 | 6053.75 | 31406.75 | 13613.5 | 4878.75 | 10195.5 | 11150.06 | 23905.68 | 16634.11 | 18273.91 | 41580.92 | 35671.07 | 54349.55 | 5994.2 | 18417.62 | 8533.9 | 4060.5 | 2768.95 | 2465.5 | 2361.75 | 2536.5 | 2204.25 | 11492.88 | 9738.19 | 7470.68 | 6438.29 | 4319.67 | 855.12 | 6983.07 |  | 412.5 |  | 10000
| Bruton Knowles | Cable route landowner discussions (Savills) |  |  | 0 | 150000 | 176133.81 | 51136.82 | 124996.99 | -176133.81 | [5 empty] | 0 | Work commences 15: 30251.07; Work commences 16: 1347.5; Work commences 17: 2391.75; Work commences 18: 5132.5; Work commences 19: 4026.5; Work commences 20: 2416.25; Work commences 21: 2578.75; Work commences 23: 2992.5; App submitted 25: 6153.15; App submitted 26: 11610.5; App submitted 27: 8820; App submitted 28: 4291.5; App submitted 29: 5222.75; App submitted 30: 6450.5; App submitted 31: 6266.44; App submitted 32: 7719.02; App submitted 33: 6377.02; App submitted 34: 6101.25; App submitted 35: 8828.5; App submitted 36: 4035.5 | 8758.25 | 5201.61 | 4321.5 | 3029.75 | 1993.75 | 4816 | 10000 | 5000
| Third party agents and legal fees | Cable route landowner payments |  |  | 0 | 525000 | 561570.1 | 13000 | 548570.1 | -561570.1 | [5 empty] | 0 | Work commences 15: 10000; Work commences 22: 3000; App submitted 25: 4900; App submitted 26: 14850; App submitted 27: 3000; App submitted 29: 2550; App submitted 31: 8500; App submitted 32: 2045; App submitted 35: 1000; App submitted 36: 1475.1 |  |  |  | 150000 | 110250 | 250000
| Third party legals working on behalf of IGP | Cable route legals |  |  | 0 | 105000 | 113780.4 | 8396.4 | 105384 | -113780.4 | [5 empty] | 0 | Work commences 16: 5306.8; Work commences 17: 1578.4; Work commences 20: 1511.2; App submitted 29: 3300; App submitted 30: 20900 | 2684 | 3500 | 10000 | 5000 | 60000
Contingency |  | 10% of planning costs |  |  | 308800 | 442090.553 | 0 |  | 0 | 308800 |  |  |  |  | 178464.499 | 0 | 107.503 | 107.503 | 107.503 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  |  |  |  | 200000 | 0 | 0 |  | 0 | 200000
Accounting & admininstration, and bank charges |  |  |  |  | 30000 | 30000 | 30000 | 2263 | 27737 | 0 | [6 empty] | Work commences 12: 513; Work commences 14: 1750; App submitted 25: 513; App submitted 27: 513; App submitted 36: 900 | 750 | 1375 | 1875 | 21811
Satisfaction of pre-commencement planning conditions | [5 empty] | 0 | 0 | 0 | 0 | 0
Transaction Cost |  |  |  |  | 30000 | 30000 | 30000 | 0 | 30000 | 0 | [6 empty] | App submitted 31: 5000; App submitted 32: 5000; App submitted 33: 5000; App submitted 34: 5000; App submitted 35: 5000; App submitted 36: 5000
Total |  |  |  |  | 4071800 | 4958693.983 | 7932516.5633 | 4505129.49 | 3427387.0733 | -3860716.5633 |  |  |  |  | 3294791.1923 | 1006826.75 | 1182.533 | 1182.533 | 1182.533 | 1075.03 |  | 0 | 0 | 0 | 0 | 0 | 49110.33 | 84547.72 | 60816.21 | 102312.88 | 175504.89 | 175294.64 | 192770.5 | 147208.04 | 487120.03 | 301379.16 | 444239.86 | 305261.42 | 292884.52 | 675552.42 | 70864.35 | 213836.35 | -3078.55 | 80516.27 | 107754.67 | 146354.87 | 93739.75 | 368962.23 | 158536.17 | 136964.66 | 136652.19 | 250531.96
Installed Capacity |  | 780
Total/MW |  |  |  |  | 5220.2564 | 6357.3 | 10169.893 | [8 empty] | 1290.8035
[30 empty] | Spend to date | 476914.659
Quoted - excluding examination | bar: Work commences 5 to Work commences 20; Work commences 22 to App submitted 36
Estimate for examination costs
Quoted - including examination
Ecology Quotes |  | Clarkson Woods phase 1 |  |  |  |  | 121000 | [8 empty] | Includes assumptions for surveys and preliminary reports
|  | Clarkson Woods phase 2 |  |  |  |  | 45000 | [8 empty] | Wintering Birds
|  | Clarkson Woods total |  |  |  |  | 166000
|  | Baker Consultants |  |  |  |  | 162150 | [8 empty] | Includes assumptions for all surveys and preliminary reports
|  | Aspect Ecology phase 1 |  |  |  |  | 75000 | [8 empty] | Includes assumptions for surveys and preliminary reports
|  | Aspect Ecology phase 2 |  |  |  |  | 161750 | [8 empty] | Inlcudes assumptions for all further surveys and reports
236750
Disbursements
|  | Lanpro |  | 0
Note on M6: Eve Browning: Omnia quote for stages 1-3, half for each project
Note on AE6: Eve Browning: Invoice INV-6632
Note on AF6: Eve Browning: INV-6790
Note on AG6: Eve Browning: Invoice INV-6938
Note on AH6: Eve Browning: Invoice INV-7103
Note on AI6: Eve Browning: Invoice INV-7291
Note on AJ6: Eve Browning: Invoice INV-7433
Note on AK6: Eve Browning: Invoice INV-7611
Note on AL6: Eve Browning: Invoice INV-7844
Note on AM6: Eve Browning: Invoice INV-8242
Note on AN6: Eve Browning: Invoice INV-8286
Note on AP6: Eve Browning: Invoice INV-2212-133 Cottam 3b substation drawing update, advice on building spec - £163.13
Note on AR6: Eve Browning: Invoice INV-2302-052 SLD updates - £947.01
Note on AS6: Eve Browning: Invoice INV-2303-054 Lessons learned telcon - £113.25
Note on AT6: Eve Browning: Invoice INV-2304-110 Grid connection cost advice - £56.63
Note on AV6: Eve Browning: Invoice INV-2306-103 Site visit - £459.30
Note on AW6: Eve Browning: Invoice INV-2307-106 Grid connection advice - £119.55
Note on AX6: Eve Browning: Invoice INV-2308-130 Front end engineering design advice - £56.63 Credit for mileage incorrectly charged - £6.30
Note on BC6: Eve Browning: Invoice INV-2401-136 Electrical design advice - £116.19
Note on C7: Eve Browning: EB to confirm with Sam expectations on this
Note on AH7: Eve Browning: Mod app Invoice 1135/80203028
Note on AS7: Eve Browning: Remittance from NG ESO Ltd Ref 0080048096 Invoice 0080203028 £60885
Note on AK8: Eve Browning: Invoice 40089052 Cottam 1
Note on AL8: Eve Browning: Invoice 40089353 Corringham (Cottam 2) aux connection application - £300 Invoice 40089354 Blyton (Cottam 3) aux grid application - £300
Note on BI8: Eve Browning: Network Rail legal costs EB estimate
Note on BJ8: Eve Browning: Based upon 10% of NR easement fee being payable upon option signing - £630/MW across whole project
Note on AJ9: Eve Browning: Blyton BAPA
Note on AL9: Eve Browning: Exceptional payment - Blyton Network Rail BAPA VAT - £2977.34 Payment reference: WB70591 VAT Exceptional payment - Blyton Clearance Costs - £1500 +VAT = £1800 Payment reference: WB70591 Exceptional payment - Cottam Power Station Clearance Costs - £1500 +VAT = £1800 Payment reference: IGP Cottam Power Station crossing Exceptional payment - Marton Clearance Costs - £1500 +VAT = £1800 Payment reference: WB70592
Note on AR9: Eve Browning: Exceptional payment Marton crossing - £24356.93 + VAT = £29228.32
Note on AX9: Eve Browning: BAPA - Cottam Power Station (exceptional payment) £30223.65 + VAT = £36268.38
Note on R10: Eve Browning: Pinsent Masons: Property advice - £5820.26 Property advice - £30460.43 Undertakings - £24,000
Note on AD10: Eve Browning: Blyton option variations and assignment
Note on AF10: Eve Browning: Wilkin Chapman option - 2486800
Note on AG10: Eve Browning: Pinsent Masons
Note on AI10: Eve Browning: Invoice 6683352 Pinsent Masons property advice re: Coates
Note on AK10: Eve Browning: Pinsent Masons
Note on AR10: Eve Browning: Pinsent Masons Invoice 6737922 Professional services - £5464.40
Note on C11: Eve Browning: Note: Lanpro issue different invoices for their 'planning', 'landscape' (LVIA) and 'heritage' teams so we get three separate monthly invoices from them. This row is just for planning costs Low Carbon and Tillbridge to invoice for two different sets of Aecom work - amounts being questioned but feature in amounts for Jan 24
Note on I11: David Elvin: Plus examination costs
Note on AE11: Eve Browning: Invoice 005230
Note on AG11: Eve Browning: Invoice 005468 for £17685, invoice 005515 for £1377.38 expenses
Note on AH11: Eve Browning: Invoice 005639 and 005642 (includes monthly expenses)
Note on AI11: Eve Browning: Invoice 005823 £10300 Additional works out of scope: - Construction Environmental Management Plan - Decommissioning Statement - PEIR socio-economic chapter - PEIR waste chapter - PEIR Other Environmental Matters Chapter £12.5k fee discounted by £2.2k budget saving carried forward Invoice 005818 £19500 Planning consultancy services
Note on AJ11: Eve Browning: Invoice 006088 Planning consultancy services, travel expenses, consultation event attendance
Note on AK11: Eve Browning: Invoice 006196
Note on AL11: Eve Browning: Invoice 006297 - planning consultancy Invoice 006304 - expenses
Note on AM11: Eve Browning: Invoice 006641 Planning consultancy - £19500 Invoice 006650 Expenses - 1105.08
Note on AN11: Eve Browning: Invoice 006825 GIS Suite of Figures, Abnormal loads, Land ownership, ALC, DCO Works Plans - £6612 Invoice 006827 Planning consultancy - £34896.25
Note on AO11: Eve Browning: Invoice 007023 Planning consultancy - £42804.75
Note on AP11: Eve Browning: Invoice 007066 £52709.75 Invoice 007396 Expenses - £1027.05 Invoice 007389 - Planning consultancy services to submission - £53899
Note on AQ11: Eve Browning: Invoice 007389 - Planning consultancy services - post-submission - £5500
Note on AR11: Eve Browning: Invoice 007618 Planning consultancy services - £18895.50
Note on AS11: Eve Browning: Invoice 007679 Pre-examination planning - £9579.25
Note on AT11: Eve Browning: Invoice 8007 Planning consultancy - £22580 Lanpro invoice 8012 Printing of documents for PINS - £4280.69
Note on AU11: Eve Browning: Invoice 008267 Planning consultancy services - £53054.50 1. Unanticipated tasks: • ‘Change Application’ (accommodating changes to red line). • TPO plans; S51 materials. 2. Volume of work required: • Volume of work to prepare response to Relevant Reps. • Volume of work preparing draft Statements of Common Ground.
Note on AV11: Eve Browning: Invoice 008339 Planning consultancy services - £55899.95
Note on AW11: Eve Browning: o Closing out RRs still – outstanding inputs from consultants and responding to Pinsents and IGP comments o Progressing SoCGs – some delays due to consultant inputs and finalising after reviews o Attending usual client and LPA meetings o Preparing for examination – looking at programme and resources needed for examination and sessions around this. o Reviewing/progressing revisions and additional documents required as a result of RRs etc. o Supporting on change application for cable route corridor £34147.45
Note on AX11: Eve Browning: Invoice 008757 • Closing out Relevant Reps response • Progressing SoCGs • Attending usual client and other project meetings • Preparing for examination • Updates to document trackers / actions lists / file structures • Reviewing/progressing revisions and additional documents required as a result of RR’s • Supporting on change application for cable route corridor • Procedural Deadline A correspondence • Securing BESS expert on project £33157.50 Invoice 008769 Expenses: Travel for mock trial (June), subsistence, printing, packaging & posting - £1753.22
Note on AY11: Eve Browning: Invoice 008965 • Closing out Relevant Reps response • Progressing SoCGs • Attending usual client and other project meetings • Preparing for examination • Updates to document trackers / actions lists / file structures • Reviewing/progressing revisions and additional documents required as a result of RR’s • Supporting on change application for cable route corridor • Procedural Deadline A correspondence • Securing BESS expert on project £55206
Note on AZ11: Eve Browning: Invoice 009167 • Closing out Relevant Reps response • Progressing SoCGs • Attending usual client and other project meetings • Preparing for examination • Updates to document trackers / actions lists / file structures • Reviewing/progressing revisions and additional documents required as a result of RR’s • Supporting on change application for cable route corridor • Procedural Deadline A correspondence • Securing BESS expert on project Stage 5 - Examination £65,389.75 Travelling Costs £406.01
Note on BA11: Eve Browning: Invoice 009368 Planning: - Prep for examination - Responding to deadline 2 requirements £55586
Note on BB11: Eve Browning: Invoice 09552 Lanpro Planning: - Responding to Deadline 3 - Cottam hearings - Regular Project management and meetings £34736 Travelling costs - £376.20 Invoice SIN2401L064000001 Gate Burton Energy Park Limited £17148.75 Options and interrelationships reports
Note on BC11: Eve Browning: Invoice 009748 Planning: - Examination preparation for D4 Stage 5 - Examination £34,735.00 Travelling Costs £295.18 £35030.18
Note on BD11: Eve Browning: Lanpro invoice 009969 Planning: - Examination prep for D5 - Preparation for Cottam change application - Attendance of meetings, PM, co-ordination of technical disciplines £50695 Volterra - Socio Economic Review Recharge £12,835.00 Invoice SIN2403L051000001 Low Carbon Inter-relationships and options report final payment - £7581
Note on BE11: Eve Browning: Invoice 010195 Planning: - Close out of final submission for D6 for close of Cottam examination including SoCGs, closing statements and final deliverables £15329
Note on BI11: Eve Browning: Coordinating, and compiling the fee quotes on requirement discharge for Cottam - £2986.50 SoS response £10000
Note on C12: Eve Browning: Budgeted £100k for help throughout the rest of Cottam examination but haven't been invoiced yet for this so don't know how much has been incurred to date
Note on C13: Eve Browning: Raise individual POs when they confirm their costs
Note on H13: Eve Browning: £10k Notts + £12200 Lincs up to end stat consultation period
Note on AH13: Eve Browning: LCC invoice 10143931
Note on AL13: Eve Browning: Lincs CC invoice 10150063 Landscape and council officer fees
Note on AP13: Eve Browning: Lincolnshire County Council - invoice 10157832 Costs to submission - £13437 Nottinghamshire County Council - invoice 92816608 Costs to submission - £5665
Note on AY13: Eve Browning: LCC invoice 2004369969 - PPA costs January 2023 - October 2023 - £23585
Note on BF13: Eve Browning: LCC estimate - Legal Costs - examination period: £5000 - Landscape consultant costs - examination period: £10000 - Council costs - examination: - Ongoing dialogue with lead and technical officers: £24570 - SoCG: £10620 - Archaeology: £4590 LCC Invoice 2004382342 PPA for examination period (October 2023-March 2024) - £33330 NCC Estimate - Council costs - pre-examination: - Ongoing dialogue with lead and technical officers: £708 - SoCG: £354 - examination: - Ongoing dialogue with lead and technical officers: £708 - SoCG: £354 - Attendance and response to hearing sessions: £1416
Note on BG13: Eve Browning: West Lindsey examination costs?
Note on C14: Eve Browning: Raise individual PO when PINS confirm their cost
Note on AO14: Eve Browning: To be paid by BACS
Note on AR14: Eve Browning: Invoice 1800004224 Pre-examination fee - £35844
Note on AX14: Eve Browning: Invoice 1800004530 Cottam Solar Project initial examination fee - £229,760
Note on BD14: Eve Browning: Invoice 1800004835 Cottam Solar Project Final Examination Fee - £229760
Note on C15: Eve Browning: Note: Lanpro issue different invoices for their 'planning', 'landscape' (LVIA) and 'heritage' teams so we get three separate monthly invoices from them. This row is just for heritage costs
Note on AF15: Eve Browning: Invoice 005232
Note on AG15: Eve Browning: Invoice 005476
Note on AH15: Eve Browning: Invoice 5641
Note on AI15: Eve Browning: Invoice 005948 PEIR/WSI/Cable routes
Note on AJ15: Eve Browning: Invoice 006030
Note on AK15: Eve Browning: Invoice 006194 Consultancy, ES, WSI and tendering
Note on AL15: Eve Browning: Lanpro invoice 006288 Alison Deegan aerial photo analysis Lanpro invoice 006299 Desk Based Assessment £6,500.00 Consultancy £4,750.00 Environmental Statement Chapter £10,000.00 Heritage Statement Scoping £1,200.00 Written Scheme of Investigation and Tendering £2,000.00
Note on AM15: Eve Browning: Invoice 006643 Consultancy £3,000.00 Environmental Statement £4,000.00 Written Scheme of Investigation and Tendering £2,500.00 AP & LiDAR Interpretation £3,000.00
Note on AN15: Eve Browning: Invoice 006826 AP and LiDAR Interpretation £3,000.00 Consultancy £1,060.00 Desk Based Assessments £5,500.00 Environmental Statement £6,350.00 Production of Heritage Statements, ES Chapter writing, GIS work, ZTVs, site visits, liaison with landscape team, formulating mitigation strategy and attendance at meetings £17,485.50 Written Scheme of Investigation and Tendering £1,300.00
Note on AO15: Eve Browning: Invoice 007025 Consultancy - £1173.75 DBAs - £4962.5 Env. Statement - £14947.5 Heritage works - £5399.5 WSI - £3985
Note on AP15: Eve Browning: Invoice 007064 (Lanpro) Consultancy £487.50 Environmental Statement £17,922.50 Heritage Works £455.00 Written Scheme of Investigation and Tendering £3,900.00 Invoice 26 (Low Carbon) Aerial LIDAR data on the cable route for Gate Burton, West Burton and Cottam - £3520.41 Invoice 007391 Consultancy - £75 ES - £9920
Note on AR15: Eve Browning: Invoice 007616 Consultancy and meetings - £3395
Note on AS15: Eve Browning: Invoice 007688 SoCG - £5437.50
Note on AT15: Eve Browning: Invoice 8004 Archaeology/heritage pre-examination works - £8750
Note on AU15: Eve Browning: Invoice 008269 Archaeology/heritage pre-examination works - £8750
Note on AV15: Eve Browning: Invoice 008337 Archaeology/heritage pre-examination works - £18685.00
Note on AW15: Eve Browning: Invoice 008696 Archaeology/heritage pre-examination works - £6825 Environmental sample processing - £13144.50
Note on AX15: Eve Browning: Invoice 008755 General Project Management (i.e. meetings, comms with Historic England) Statements of Common Ground Responses to Relevant Representations Viewpoint locations for the Inspector Review of issued documents (i.e. Rule 6) Review of other schemes (Tillbridge / Gate Burton) Review of submitted HE documents Consolidation / review of counter arguments (i.e. archaeology / heritage issues) £6654.75
Note on AY15: Eve Browning: Invoice 008967 - General Project Management (i.e. meetings, comms with Historic England) - SoCG - Review of Documents - Review of Preliminary Meeting - Review of issued documents (i.e. Rule 8) - Review of Report on the interrelationship with other NSIPs - Review of other schemes - Shared Cable Route £6950
Note on AZ15: Eve Browning: Invoice 009169 - General Project Management (i.e. meetings, comms with Historic England) - SoCG - Review of Documents - Review of Preliminary Meeting - Review of issued documents (i.e. Rule 8) - Review of Report on the interrelationship with other NSIPs - Geophysical Survey Management Archaeology/Heritage Examination Works £8,656.00 Expenses - Printing & Travel £115.35
Note on BA15: Eve Browning: Invoice 009370 Historic Environment; - General Project Management - Liaison with Lincs LPA - Liaison with Notts LPA - SoCG - Review of ES documents - Deadline 2 documents - Cable route changes £16197.50
Note on BB15: Eve Browning: Invoice 009554 - General project management - Change of application report - Prehearing preparation - ISH2 and ISH3 hearings - Update to IRR report - Deadline 3 documents (SoCG, Evaluation Comparison Report etc) - Review of ISH 2 and 4 summaries - Liaison with Lincs LPA - Update to SoCG £27675 Printing - £703.46 Total £28378.46
Note on BC15: Eve Browning: Invoice 009750 Historic Environment: - General Project Management - WSIs - EX2 - IRR Report - Statement of common ground £14250 Printing - £285.06 Total £14535.06
Note on BD15: Eve Browning: Invoice 009967 Historic Environment; - General Project Management - Comms with LHPT - WSIs - RRs - CHPSs / SoCG - Hearing £11975
Note on BE15: Eve Browning: Invoice 010197 Historic Environment; - Close out of final submission for D6 for close of Cottam examination including SoCGs, closing statements and final deliverables. £4090
Note on M16: Eve Browning: SES quote, only complete late October, half of total quote of £58.2k
Note on N16: Eve Browning: Half of total quote from Ceres Rural - can complete by mid-August, using digger to dig soil pits, and includes all expenses. Revising quote downwards if third parties used
Note on O16: Eve Browning: Quote from LRA, includes battery storage area - six month lead time for completion
Note on P16: Eve Browning: Amet Property. Includes £1500 expenses. One report available early August, and one early Sept
Note on AF16: Eve Browning: Invoice INV-0915
Note on AH16: Eve Browning: Additional lab sampling and report updating Invoice INV-0985
Note on AI16: Eve Browning: Daniel Baird peer review Invoice INV-0077
Note on AP17: Eve Browning: Invoice INV-0087 Meetings - £1000 ES Chapter - £2000 Farming circumstances baseline - £1000
Note on AU17: Eve Browning: Invoice INV-097 Relevant Representations in April and May £2,700.00 Practice Hearing £1,350.00 Train £177.00 Meals & Subsistence £10.70
Note on M18: Eve Browning: Sensat. Note: £2225 per month to be added for platform from month 4 £12000 added for access point surveys + £3750 added for 3D CAD production
Note on N18: Eve Browning: Quote from ALS. Drone survey to define project boundaries, site levels and salient features which might affect the design of the project. Further surveys may be required at a later date to help complete highways design or inform more detailed arboricultural/habitat assessments.
Note on O18: Eve Browning: Half of total quote from Flythru, including updated costs to process output into dwg files
Note on P18: Eve Browning: Combined quote from Sumo and AerialCam. Additional £11k estimate for completing terrestrial surveying at a later date Battery site not included
Note on AC18: Eve Browning: 3D CAD
Note on AD18: Eve Browning: 12k access point survey
Note on AJ18: Eve Browning: Stow village S bends Invoice 43553
Note on C19: Eve Browning: Delta Simons also invoice us for contaminated land (ground conditions) work
Note on M19: Eve Browning: Quote from Delta Simons for initial flood risk screening assessment only is £2700 (Eve added additional £450 for battery site). Secondary quote for further works comes to £21500. Eve added £2k for battery FRA
Note on N19: Eve Browning: Quote from Rossi Long
Note on AI19: Eve Browning: Invoice DS033519
Note on AJ19: Eve Browning: Invoice DS033745 Attendance at public consultation
Note on AK19: Eve Browning: Invoice DS034011
Note on AP19: Eve Browning: Invoice 171883 WFD Report - £2200
Note on AQ19: Eve Browning: Invoice 174708 Meetings £630
Note on AV19: Eve Browning: Invoice 91515 SoCG and RR responses - £720
Note on AY19: Eve Browning: Invoice 189756 RR and SoCG work - £2875
Note on BF19: Eve Browning: Mabbett invoice 606019 Examination fees £3125
Note on BG19: Eve Browning: Modelling 60 year flood
Note on I20: Eve Browning: £291,600 West Burton quote Now includes for cable route survey
Note on M20: Eve Browning: 1145ha at £215 per hectare. 400ha/month surveyed - approx £86k per month for cash flow
Note on N20: Eve Browning: Latest Lanpro estimate 21/12/21
Note on AG20: Eve Browning: Invoice 005476
Note on AH20: Eve Browning: 005641
Note on AI20: Eve Browning: Invoice 005948
Note on AJ20: Eve Browning: Invoice 006030 - £387.5 Invoice 006087 - £18805.5
Note on AK20: Eve Browning: Invoice 006292
Note on AM20: Eve Browning: Invoice 006640
Note on AN20: Eve Browning: Invoice 006835
Note on AZ20: Eve Browning: Lanpro invoice Invoice 009169 Geophysical Survey Normanby by Stow £2,025.00
Note on AG21: Eve Browning: Cable route overlap area. Invoice INV038047
Note on AH21: Eve Browning: Invoice INV038199
Note on AK21: Eve Browning: Lanpro invoice 006292 - project management
Note on AM21: Eve Browning: Invoice 006640 - Lanpro Combined cable route proejct management fee - £3700
Note on AN21: Eve Browning: Invoice 006835
Note on AO21: Eve Browning: Invoice INV039184
Note on M22: Eve Browning: Hoped not to be required until post-planning
Note on AK22: Eve Browning: Invoice 006193 Trial trenching (208078.7+80770.25) and project management (17600)
Note on AL22: Eve Browning: Invoice 006288 - Lanpro Archaeological fieldwork (Sept) and archaeological fieldwork project management (August) (77952.75+15400) Invoice SI8 - Pongo Farms Ltd Crop loss (Cottam 2) - £53476.33
Note on AM22: Eve Browning: Invoice GJ/JW/BR-20/115 - DDM Agriculture £182849k for Cottam 1 crop loss Invoice 006639 - Lanpro Archaeological fieldwork - £3777.75 Arch. Fieldwork project management - £7700 Burial licenses, utility search and liaisons - £1069.5
Note on AN22: Eve Browning: Invoice 006830 Archaeological Fieldwork (October Additional) £46,161.00 Archaeological Fieldwork Project Management £6,450.00 Cottam 2 - Post-Excavation Management and Interim Report QA £2,050.00
Note on AO22: Eve Browning: Invoice 007022 Cottam 1 trenches in C5 - £22465 Project management - £4400 Cottam 1 post-excavation management and report QA - £3150 Cottam 3 - post excavation management and report QA - £2050
Note on AP22: Eve Browning: Invoice 25 (Low Carbon UK Solar Investment Company Limited) £75944.17 - Shared cable route trenches - Low Carbon Invoice 27 (Low Carbon) Landowner costs e.g. license fee, agent fees, trench compensation, grass reseeding works, drainage repairs. £20434.93
Note on AY22: Eve Browning: Invoice INV041235 Letter of reliance for Wessex trenching land south of Torksey Ferry Road - £500
Note on BB22: Eve Browning: Limestone Farming Company Ltd inoivce 9008 Costs to fill in missed Cottam 1 trenches - £500
Note on BK22: Eve Browning: Estimation of post-trenching final reporting costs
Note on C23: Eve Browning: Also invoice us for noise work
Note on I23: Eve Browning: Tetratech, includes battery fire smoke assessment
Note on M23: Eve Browning: Tetratech, includes battery fire smoke assessment
Note on AH23: Eve Browning: PEIR + construction dust assessment Invoice 30034532
Note on AP23: Eve Browning: Invoice 784-B031438 / 30048654 ES Chapter - £1250
Note on AV23: Eve Browning: Invoice 30056498 Air quality SoCG - £1250
Note on AY23: Eve Browning: Invoice 30061129 - Additional solar panel fire modelling and risk assessment - £2450 - Detailed BESS fire impact assessment - £3950 - AQ ES chapter addendum - £950
Note on AZ23: Eve Browning: Invoice 30065904 Stage 4 pre-examination - £3950
Note on BA23: Eve Browning: Invoice 30068500 (1) A revised BESS fire assessment scenario (using new input following discussions with Paul Gregory) - £1250; (2) The revised BESS fire assessment reporting (following discussions with Paul Gregory) £1,450;
Note on BD23: Eve Browning: Invoice 30082428 Air quality responses during examination period - £1950
Note on BF23: Eve Browning: Invoice 30086612 Examination final inputs - £1950
Note on M24: Quote from Ted Clover. Half of £7500 quote for desktop Minerals Resource Assessment - may be a little more if two separate reports required?
Note on AI24: Eve Browning: Invoice CSP/002 PEIR
Note on AO24: Eve Browning: Invoice CSP/003
Note on AP24: Eve Browning: Invoice CSP/004 Preparation of Mineral Resource Assessment as part of Environmental Statement - £240
Note on AW24: Eve Browning: Invoice CSP/005 Preparation of non-technical summary and SoCG - £665
Note on BE24: Eve Browning: Invoice CSP/006 Consideration of representations/Inpectors Questions Consideration of amendments to the Scheme Input into EIP documents as requested Additional consideration of cumulative impacts £1045
Note on M26: Eve Browning: Missing Broxholme. Quote from Rossi Long for initial work to inform initial consultation with stakeholders
Note on N26: Eve Browning: Quote from Stantec not including SoCGs, or examination attendance. CTMP at £400 per land parcel (4 x parcels) added in after clarification
Note on O26: Eve Browning: Quote from TPA includes for EIA chapter, transport statement, CTMP, input into CEMP and all drawings and consultation up to planning submission. £4700 included for traffic surveys by 360 TSL, split across two projects Additional predicted overspends added due to additional junctions and abnormal loads - fee extension request saved in file
Note on AD26: Eve Browning: Scoping note plus draft CTMP
Note on AF26: Eve Browning: Invoice 013040 for £3001.25
Note on AG26: Eve Browning: Invoice 013244
Note on AH26: Eve Browning: Invoice 013345
Note on AI26: Eve Browning: Invoice 013457 PEIR/CTMP Invoice 013551
Note on AK26: Eve Browning: Invoice 013728 Team meetings Trip generation note review of and advice on consultation responses, traffic flow diagrams, ES chapter drafting, green lane review
Note on AL26: Eve Browning: Invoice 013855 • Team Meetings; • PROW Surveys ~£2625; • Red Line Review; • Two new access drawings; • ES Chapter Drafting. Invoice 013943 • Team Meetings; • PROW Surveys; • Red Line Review; • Cable Route Review • ES Chapter Drafting.
Note on AM26: Eve Browning: Invoice 014155 - £11002.5 • Team Meetings; • PROW Surveys; • Cable Route Access Review; • Red Line Updates; • ES Chapter Drafting.
Note on AO26: Eve Browning: Invoice 014285 • Team Meetings; • Access Review; • Trip Generation; • ES Chapter; • TA; • CTMP.
Note on AP26: Eve Browning: Invoice 014425 - £8005 • Team Meetings; • Final Draft ES Chapter; • Final Draft Transport Assessment; • Final Draft CTMP; • Final Draft Public Rights of Way Management Plan. Invoice 014470 - £10120.91 • Additional spend on ES chapter to cover all consultation responses, the details of the cable route corridor and rounds of comments from the Design Team; • The initial quote was for a Transport Statement to support the DCO. However, given the detail required, this turned into a Transport Assessment, which set out the details of almost 50 accesses and their effects on the surrounding local highway network; • Multiple meetings, especially during November and December; • Changes in the access strategy following the site layout designs which results in relocated and new accesses; • A public rights of way management plan.
Note on AT26: Eve Browning: Invoice 014975 -Team meetings - SoCG with NH - Input into SoCG for LCC and NCC £1750
Note on AU26: Eve Browning: Invoice 015123 Relevant reps - £1250
Note on AV26: Eve Browning: Invoice 015380 RR, SoCG, access comparison with Low Carbon - £2250
Note on AX26: Eve Browning: Invoice 015519 This invoice covers our work carried in July/August 2023, including: • Relevant Representations • Cable Route Accesses £1750
Note on AY26: Eve Browning: Invoice 015635 This invoice covers our work carried in August/September 2023, including: • Relevant Representations • Access • BESS Trips • PRoW Response £1250
Note on AZ26: Eve Browning: Invoice 015774 This invoice covers our work carried in September/October 2023, including: • Submission of Documents for Deadline 1 • Relevant Representations • PROW Meetings and Response • BESS Repowering • Cable Route Accesses £4000
Note on BA26: Eve Browning: Invoice 015905 This invoice covers our work carried out in October/November 2023: • Response to Examiners Questions; • Response to Relevant Representations; • Updated documents for Deadline 2 £5000
Note on BB26: Eve Browning: Invoice 015972 This invoice covers our work carried out in December 2023: • Updated documents for Deadline 3; • Relevant Reps Responses for Deadline 3; • Updated documents for Change Application; • Attendance at ISH 4. £6000
Note on BC26: Eve Browning: Invoice 016152 This invoice covers our work carried out in December 2023/January 2024: • Update documents for Deadlines 4; • Responses to written questions. £4000
Note on BD26: Eve Browning: Invoice 016316 This invoice covers our work carried out in January/February 2024: • Update documents for Deadlines 5; • Responses to written questions. £2500
Note on BE26: Eve Browning: TPA Invoice 016509 This invoice covers our work carried out in February/March 2024: • Preparation and attendance at change hearing; • Final updates and responses up to end of examination. £2450
Note on M27: Eve Browning: Half of Wynns quote across both WB and C
Note on AF27: Eve Browning: Invoice 3605
Note on AG27: Eve Browning: Invoice 3626
Note on AH27: Eve Browning: Invoice 3638
Note on AI27: Eve Browning: Invoice 3638
Note on AL27: Eve Browning: Invoice 3703 Cottam 3 site visit
Note on AM27: Eve Browning: Invoice 3714 Site visit for cable drum access
Note on AN27: Eve Browning: Invoice 3736
Note on AP27: Eve Browning: Invoice 3768 £337.50 Invoice 3792 Abnormal loads reports for ES - £2171.25
Note on AR27: Eve Browning: Invoice 3830 Swept paths for cable route - £1425
Note on AT27: Eve Browning: Invoice 3850 - Arrangement and management of bridge assessment engineers - £1500 - Wallace Stone bridge assessments to date - £6095 - Andy Pearce time - £112.50
Note on AU27: Eve Browning: Invoice 3875 Wynns Wallace Stone bridge surveys - £3120.52
Note on AV27: Eve Browning: Invoice 3895 Bridge surveys - £5200.87
Note on AW27: Eve Browning: Invoice 3914 Bridge surveys and works associated with heavy load accesses - £4334.06
Note on AX27: Eve Browning: Invoice 3930 Bridge assessments - £2600.43
Note on AZ27: Eve Browning: Invoice 3965 Bridge assessments - £1213.54
Note on BE27: Eve Browning: Invoice 4095 Additional works on Bridge Assessments for Lincolnshire County Council. As per our proposal dated 20.01.23. Final payment. (Ref/W/2023/AP/0007) £886.61
Note on M28: Eve Browning: Clarkson and Woods. Half of revised quote inc. bat surveys Additional costs added for otters and water voles/bat tree and building inspections
Note on AF28: Eve Browning: 1 x wintering bird survey + half-day consultation fee. Invoice number 747919
Note on AG28: Eve Browning: -Final Wintering Bird survey - £7,762.50 -Meeting attendance 15/03 - £572.50 Invoice 747921
Note on AH28: Eve Browning: -Breeding Bird Survey - £8463.50 -April bat detector survey - £7,102.50 - Badger sett update £1500.00 (Invoice Otter and water vole survey - £6975.00 (Invoice 77359)
Note on AI28: Eve Browning: Invoice 747925 -Final Breeding Bird Survey - £8,463.50 -May (Final) bat detector survey - £7,102.50 - Great crested newt eDNA surveys of 33 ponds in relation to cable routes AND array sites - £5,610.00 and £3600 (visits and lab fees) - Preparation of PEIR Ecology chapter – £5,600.00 -Input into Landscape and Ecological Management Plan (or similar) – £1,500.00 . Invoice 773511 - Inspections of buildings for bats and birds - £6,050.00 - Expansion of bat report with building and tree mapping and analysis - £1,950.00
Note on AJ28: Eve Browning: Invoice 80082 - 2 x cable route breeding bird surveys (£11390) - 2 x shared cable route breeding bird surveys (£4360) Invoice 747927 - eDNA testing (£2210+1575+300) - Meeting attendance £375 Invoice 773513 - Cable route phase 1 survey £7500
Note on AK28: Eve Browning: Invoice 747929 - Wintering bird survey report - £2200 - Breeding bird survey report - £2465 - Bat survey report - £2800 - GCN survey report - £870 - Cambridge meeting attendance - £938 Invoice 773515 - 25% of Phase 1 survey of Cottam cable route (75% invoiced so far) - £3750 Invoice 80084 - Third and final breeding bird survey of Cottam cable route - £5695 - Third and final breeding bird survey of shared cable route - £2180
Note on AO28: Eve Browning: Invoice 773516 Phase 1 cable route (25%) - £3750 Otters and water vole report - £2275 Invoice 747930 ES Chapter - £3700 BNG assessment (50%) - £2950 LEMP - £4500 Ecological protection and mitigation scheme - £2800 Meetings - £645 Design support - £3220
Note on AP28: Eve Browning: Invoice 747932 ES Chapter Revisions 1,500.00 LEMP Revisions 1,300.00 Design support in December 1,075.00
Note on AU28: Eve Browning: Invoice 84311 - GCN eDNA survey of 9 ponds at the Cable Route (50% fee for Cottam) 1,125.00 - Lab fee for 9 eDNA tests (50% fee for Cottam) 1,125.00 - Statement of Common Ground (SoCG) for Notts Wildlife Trust (1/3 budget) 500.00 - SoCG for Lincs WT (1/3 budget) 500.00 - SoCG for NE (50% budget) 1,000.00 - Relevant Representations (RRs) response to Councils (1/3 budget) 385.00 - RRs to Other Statutory Consultees (75% budget) 860.00 - RRs to Members of the Public (75% budget) 860.00
Note on AV28: Eve Browning: Invoice 84313 - Attendance at mock hearing event 1,000.00 - RRs to Councils (remaining 2/3 budget) 800.00 - RRs to Other Statutory Consultees (remaining 25% budget) 287.50 - RRs to Members of the Public (remaining 25% budget) 287.50
Note on AZ28: Eve Browning: Invoice 84314 Updates to Cottam OLEMP 212.00 Open Floor Hearing Responses 106.00 Natural England SoCG additional revisions post PM review 212.00 Normanby by Stow cable route extra land site visit and mapping 980.00 Normanby by Stow alternative cable route land site visit and mapping 980.00 Review of Low Carbon Cumulative Effects comparison report and amendments 212.00 Invoice 84982 Preparation of BNG Assessment Report v2 to include Cable Route Corridor 5,100.00
Note on BB28: Eve Browning: Invoice 84316 Applicant's responses to DL3 Submissions 106.00 DL3: Fish EMF Risk Assessment 424.00 DL3: Update iHRA 265.00 DL3: ISH2 Notes 53.00 DL3: Chapter 9 Addendum 212.00 DL3: OLEMP Update 106.00 DL3: EA Statement of Common Ground 106.00 DL3: NE SoCG 318.00 Interrelationships Report Updates (split with WB) 106.00 Application SEIR 318.00 Site surveys to inform Change Request 424.00 ISH 3&4 Attendance 1,000.00 Applicant's responses to DL2 Submissions 212.00 DL2: ExQ1 Responses 424.00 DL2: LIR Responses 212.00 DL2: WR Responses Pt 1 265.00 DL2: WR Responses Pt 2 265.00 DL2: WR Responses Pt 3 265.00 Chapter 23 and NTS Update 212.00
Note on BE28: Eve Browning: Invoice 84318 Cottam Solar Project Examination - Works Jan 13th 2024 to April 15th 2024 Finalisation of SoCG with EA 636.00 Finalisation of SoCG with NE 212.00 Input into technical note on new cumulative sites 106.00 ExA's 2nd WQs 212.00 BNG Approach Discussions 212.00 Input into West Lindsey SoCG 212.00 Input into Responses to DL3Aand 4 Submissions 371.00 ESAddendum Cumulative Effects 53.00 ExA's 3rd WQs 212.00 Input into Responses to DL5 Submissions 106.00 Section of cable route survey data collation 106.00 Cottam virtual change application hearing 318.00 Total £2756
Note on AH29: Eve Browning: Invoice 005640
Note on AI29: Eve Browning: Invoice 005824
Note on AJ29: Eve Browning: Invoice 006069
Note on AK29: Eve Browning: Invoice 006195
Note on AL29: Eve Browning: Invoice 006298
Note on AN29: Eve Browning: Invoice 006825
Note on AO29: Eve Browning: Invoice 007024 Env masterplan and BNG calcs - £3727.5
Note on AP29: Eve Browning: Invoice 007065 Env. Masterplan and BNG calculations for ecologists - £2130
Note on C30: Eve Browning: Note: Lanpro issue different invoices for their 'planning', 'landscape' (LVIA) and 'heritage' teams so we get three separate monthly invoices from them. This row is just for landscape costs
Note on AF30: Eve Browning: Invoice number 005231
Note on AG30: Eve Browning: Invoice 005471
Note on AH30: Eve Browning: Invoice 005640
Note on AI30: Eve Browning: Invoice 005824
Note on AJ30: Eve Browning: Invoice 006069 LVIA, meetings and consultation, summer photography and processing, expenses
Note on AK30: Eve Browning: Invoice 006195
Note on AL30: Eve Browning: Invoice 006298
Note on AM30: Eve Browning: Invoice 006652 - GIS Suite of Figures, Abnormal loads, Land ownership, ALC, DCO Works Plans £2,700.00 - Landscape Parameter Plans £2,000.00 - LVIA £10,000.00 - Masking for Photomontages £11,500.00 - Meetings/Consultation £4,000.00 - 3D Modelling £4,000.00
Note on AN30: Eve Browning: Invoice 006825 Visualisation Rendering £6,872.05 LEMP Masterplan with ecological Mitigation £2,942.50 LVIA Chapter including revisions to comply with the latest layout £30,107.50 Meetings/Consultation £3,325.00 Photomasking and montages (winter year 1 & summer year 15) £27,250.00
Note on AO30: Eve Browning: Invoice 007024 GIS figures = £6439 LVIA - £35565 Meetings - £1640 Photomasking/montages - £2875
Note on AP30: Eve Browning: Invoice 007065 GIS Figures - revised suite £7,110.00 Photomontages Production £16,882.50 LVIA £51,713.75 Meetings/Consultation £2,472.50 Invoice 007390 - LVIA to submission £47,865.15 - Figures and plans to submission £2,485.00 - Additional Visualisations to submission £3,421.25 - Additional Visualisations post submission £2,745.00
Note on AR30: Eve Browning: Invoice 007617 Additional photography to capture additional viewpoints in winter £3,450.00 Photography to update montages following detailed review 4,370.00 Landscape Visualisations £3,375.00
Note on AS30: Eve Browning: Invoice 007687 Additional landscape mitigation plan - £1552.50
Note on AT30: Eve Browning: Invoice 8006 Stage 4 pre-examination - £12318.75
Note on AU30: Eve Browning: Invoice 008268 Stage 4 pre-examination - £13256.25
Note on AV30: Eve Browning: Invoice 008338 - Stage 4 Pre-examination - £13123 - Additional photography - £2300
Note on AW30: Eve Browning: Invoice 008695 Pre-examination - £8895.75 Additional photography, viewpoints and drone videos - £3749 Credit note 008722 Drone survey refund - £600
Note on AX30: Eve Browning: Invoice 008756 General Project Management (i.e. meetings, comms with Historic England) Statements of Common Ground Responses to Relevant Representations Viewpoint locations for the Inspector Review of issued documents (i.e. Rule 6) Review of other schemes (Tillbridge / Gate Burton) Review of submitted HE documents Consolidation / review of counter arguments (i.e. archaeology / heritage issues) £11060
Note on AY30: Eve Browning: Invoice 008966 • Progressing relevant reps and SoCGs • Interrelationship and cumulative effects • Revisions to documents and plans • Hedgerow Removal Plans and cross checks with OLEMP • LVIA workshops with Lincolnshire £8453
Note on AZ30: Eve Browning: Invoice 009168 Landscape: - Progressing relevant reps and SoCGs - Crossing Schedule Updates: Streets and Private Tracks - Deadline 1 Submission -Pre-Examination: Updates to NCC/LCC following LVIA Workshop 4 - Open Floor Hearing: Landscape response to public feedback Stage 5 Examination £13,228.50 Site Visit Expenses £338.38
Note on BA30: Eve Browning: Invoice 009369 Landscape: - ZTV updates (Fixed & Tracker Panels) - LPA Consultant Meeting - Landscape Cross Sectons - LVIA Documents for Examination - General Review £9443
Note on BB30: Eve Browning: Invoice 009553 - Attendance at Hearing. Team briefings/debriefings and post hearing tasks. - Production of Cumulative Impact ZTVs and supporting text for Hearing. - DCO Plans: GIS Updates and Order Limits Change Review - Deadline 2: Applicant responses to Relevant Reps Meeting - Deadline 3: oLEMP updates in line with other docs - Deadline 2: Response to comments from Local Authorities - Deadline 3: Post Hearing Notes for Skelton, Beneficial Effects, Points of Contention and 4.5m panels - Stage 4 Pre-Examination and preparation for hearing and response to PINS Deadlines £16,142.50 - Stage 5 Examination: Meetings in London for Mock Hearing, Preparation for Hearing (WW and MT), Attendance at hearings, response to written reps, deadline 2 and 3, inspectors comments, interrelationship report, Blyton Racetrack briefing, response to grid route changes, OLEMP changes; £27,884.00 - GIS and Landscape drawings and figure updates: Order limits, DCO Plans, Landscape Sections, hedgerow removal plans £6,242.50 - Meetings held with client, Pinsent Mason, Local Planning Authority £1,567.50 - Variations to ZTV in response to inspectors questions and request by Jan following meeting in London £907.50 Travelling & Printing £1,569.78 Total £54313.78
Note on BC30: Eve Browning: Invoice 009749 Landscape: - Inter-relationships report - Review of reps for D4 - Applicants response to D3 - Statement of common ground - Joint statement - Technical note on new cumulative sites - DCO plan updates - LPA consultation meetings - Fly through - Blyton line of sight assessment Stage 5 Examination £5,000.00 Fly-Through £7,500.00 Additional Meetings £155.00 Blyton Racetrack £2,257.50 Travelling & Printing £367.61 £15280.11
Note on BD30: Eve Browning: Invoice 009968 Landscape: Finalising SoCG, including virtual meetings with LCC/AAH. Review of LPA statement of Landscape effects. Change Application. West Lindsey SoCG. DL3 and DL4 Submission material. £8600
Note on BE30: Eve Browning: Invoice 010196 Landscape: - Close out of final submission for D6 for close of Cottam examination including SoCGs, closing statements and final deliverables. £5000
Note on M31: Eve Browning: Included for in Highways work
Note on C32: Eve Browning: Also invoice us for air quality costs
Note on M32: Eve Browning: Original quote for background monitoring 17450/2 + £650 for scoping + £1250 for ES chapter
Note on AH32: Eve Browning: PEIR £1650, category 3 £1450, modelling £3150, meetings £425 Invoice 30034532
Note on AP32: Eve Browning: Invoice 784-B031438 / 30048654 7 x meetings @ £85 per meeting £595.00 ES Noise Chapter £1,250.00 Cable Route Assesment £1,250.00 Additional works including scheme amendments £2,900.00
Note on AZ32: Eve Browning: Invoice 30065904 Stage 4 pre-examination - £3950
Note on BA32: Eve Browning: Invoice 30072169 Hearing attendance and Blyton race track site visit - £3850
Note on BB32: Eve Browning: S&D Garritt Blyton Park site visit attendance - £950 Invoice 30076110 Tetratech Desk based noise assessment (Blyton Park Driving Centre) - £4550
Note on BD32: Eve Browning: S & D Garritt invoice 7824 - Initial analysis of Tetratech Acoustic Report & Modelling - Formal response dated 22nd February 2024 including all correspondence and discussion. £960 Tetratech invoice 30082428 Noise responses during examination period - £1950
Note on BF32: Eve Browning: Invoice 30086612 Examination final inputs - £1950
Note on AL33: Eve Browning: Invoice 006298
Note on AM33: Eve Browning: Invoice 006652 Building 3D Model of solar farm + Montage progression - £23000
Note on AN33: Eve Browning: Invoice 006825
Note on AO33: Eve Browning: Invoice 007024 3D model - £2875
Note on M35: Eve Browning: IGP to write
Note on M36: Eve Browning: Includes half of scoping document cost, screening cost, glint and glare assessment, EIA chapter, stakeholder consultation and technical support. Additional £420 for Ragwhistle scoping work
Note on AG36: Eve Browning: Invoice 708104 for £8738, invoice 708108 for £217.20
Note on AH36: Eve Browning: Invoice 708187
Note on AI36: Eve Browning: Invoice 708238 Category 3 work
Note on AJ36: Eve Browning: Invoice 708326 Attendance at project meeting
Note on AM36: Eve Browning: Invoice 708589 Draft ES chapter - £2726 Invoice 708590 Technical report - £9275
Note on AP36: Eve Browning: Invoice 708711 Report update with the legal review comments for Cottam Solar Project
Note on AS36: Eve Browning: Invoice 708887 SoCG - £662.50
Note on AT36: Eve Browning: Invoice 708985 SoCG - £662.5 Invoice 709015 Blyton race track assessment - £995
Note on AV36: Eve Browning: Invoice 709142 Relevant rep responses - £993.75
Note on AW36: Eve Browning: Invoice 709216 Technical support - £331.25
Note on BB36: Eve Browning: Invoice 709585 Technical support for Cottam Solar Project during examination period - £1987.50
Note on BC36: Eve Browning: Blyton race track summary and examination responses
Note on AE37: Eve Browning: Invoice 6662396
Note on AG37: Eve Browning: Invoice 6667702
Note on AH37: Eve Browning: Invoice 6673571
Note on AI37: Eve Browning: Invoice 6682011
Note on AJ37: Eve Browning: Invoice 6689289
Note on AK37: Eve Browning: Invoice 6694884
Note on AM37: Eve Browning: Invoice 6705968 - £31556.80
Note on AN37: Eve Browning: Invoice 6713114 £32775 Invoice 6715527 £5087.6
Note on AO37: Eve Browning: Invoice 6719092
Note on AP37: Eve Browning: Invoice 6725701 £116060.8 Invoice 6728417 £39799.1
Note on AS37: Eve Browning: Invoice 6741190 Post-submission work, S56 certificates and advice - £6556.8 Travel and subsistence - £326.25
Note on AT37: Eve Browning: Invoice 6748970 Cottam legal advice - £9099.20
Note on BD37: Eve Browning: Invoice 6815641 Professional fees £200000 Copying and other incidental expenses £2,356.00 Electronic Signature service £50.00 Hotel accommodation £215.83 Travelling & Subsistence £920.12 Travelling expenses £554.56 £204096.51
Note on C38: Eve Browning: Invoiced on same invoice as below and EB splits up manually
Note on AX38: Eve Browning: Counter Context invoice 204983 Hire of Lincolnshire Showground - £4806.50 Team accommodation - £2884.56
Note on AY38: Eve Browning: Counter Context invoice 205017 AV supplier for 3 days w/c 4th Sept - £25700
Note on BB38: Eve Browning: Counter Context invoice 205148 Venue hire Lincolnshire Showground - £4183 Venue hire West Lindsey District Council offices - £1996 Hire of audio-visual equipment - £50,681 Team accommodation - £3892
Note on BC38: Eve Browning: Invoice 205207 Lincolnshire Showground catering charge - £165
Note on BD38: Eve Browning: Counter Context invoice 205242 Virtual Hearing for Change of Application - AV Assistance - AV set up for virtual hearing held 28 February, including set up and delivery in line with PINS SLA requirements. £4812
Note on C39: Eve Browning: Invoiced on same invoice as below and EB splits up manually
Note on D39: Eve Browning: 32k of examination costs added in Dec 2022/Jan 2023 - remove?
Note on M39: Eve Browning: Counter Context, up to examination stage. Budget assumes £32k at examination stage
Note on AC39: Eve Browning: Invoice 204033
Note on AE39: Eve Browning: Invoice 204138
Note on AG39: Eve Browning: Invoice 204186
Note on AH39: Eve Browning: Invoice 204214
Note on AI39: Eve Browning: Invoice 204307 Includes £34k for statutory notice advertisement fees
Note on AK39: Eve Browning: Invoice 204339 Ongoing local community and stakeholder engagement support - £4020 Phase Two consultation Stakeholder Engagement - £595 Drafting and design of consultation and publicity materials to print ready - £3500 Consultation event preparation and facilitation - £4000 Digital engagement platform - £2500 Formal Section 42,46 and 48 notification requirements - £5500 Hire of consultation event venues - £375 Print and distribution of PEIR - £8845 Phase Two Consultation Leaflet and Feedback Form - £9460 Consultation Event Materials - £1500 Mileage for Lincolnshire County Council meeting on 06/06/22 - £41.40 June event expenses - £283.63 Invoice 204342 Ongoing local community and stakeholder engagement support - £4020 Consultation event preparation and facilitation - £2000 Upload and hosting of 360 degree digital photography - £275 July event expenses - £34.20
Note on AL39: Eve Browning: Invoice 204379 - Client liaison, meeting attendance and project management - Weekly media monitoring and reporting - Management, recording and reporting of all stakeholder enquiries and ongoing community liaison - Attendance at PINs and stakeholder meetings - Ad hoc media support
Note on AM39: Eve Browning: Invoice 204468 - Ongoing local community and stakeholder engagement support - £4020 - Consultation Summary Report - £4500
Note on AN39: Eve Browning: Invoice 204465 - Ongoing local community and stakeholder engagement support - £4020 - Consultation analysis and production of Consultation Summary Report - £3560
Note on AO39: Eve Browning: Invoice 204523 Ongoing local community and stakeholder engagement support - Client liaison, meeting attendance and project management - Weekly media monitoring and reporting - Management, recording and reporting of stakeholder enquiries and ongoing community liaison - Ad hoc media support £4020
Note on AP39: Eve Browning: Invoice 204587 Ongoing local community and stakeholder engagement support - Client liaison, meeting attendance and project management - Weekly media monitoring and reporting - Management, recording and reporting of stakeholder enquiries and ongoing community liaison - Ad hoc media support £2010 Invoice 204589 Consultation Report Collation of consultation methodology, analysis and response to produce Consultation Report. £9080
Note on AQ39: Eve Browning: As per quote 202690 Invoice 204669 S56 notifications - £47174
Note on AR39: Eve Browning: Invoice 204711 Pre-examination comms - £2564
Note on AS39: Eve Browning: Invoice 204759 Ongoing comms support - £2564
Note on AT39: Eve Browning: Invoice 204808 Ongoing comms support - £2564 Relevant reps summarising - £1400
Note on AU39: Eve Browning: Invoice 204866 Ongoing comms support - £2564
Note on AV39: Eve Browning: Invoice 204920 - Ongoing comms support - £2564 - Drafting of Rule 13(6) notice - £2568 - Publication of Rule 13(6) - £8150
Note on AX39: Eve Browning: Invoice 204983 Ongoing communications support - £2564 Logistical support to organise hearings - £2600 Travel and subsistence expenses - £93.65
Note on AY39: Eve Browning: Invoice 205017 Ongoing comms support - £2564 Attendance at prelim meetings and hearings - £2100 Car parking - £21.90
Note on AZ39: Eve Browning: Invoice 205068 Ongoing comms support - £2564
Note on BA39: Eve Browning: Invoice 205110 - Ongoing comms support plus £480 for hearings preparation support - £3044 - Publication of Rule 13(6) notice - £8745 Total - £11789
Note on BB39: Eve Browning: Invoice 205148 Ongoing comms support - £2564 Attendance at hearings - £3828 Expenses - £195.49 Total £6587
Note on BC39: Eve Browning: Invoice 205207 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Media monitoring - Support providing Applicant Responses ahead of Cottam Deadline 4 - Management of issue of Change Application Notice, including drafting, design and distribution. £2948 ottam Change Application Notice and Cover Letter - Print and Postage of Notice to identified consultees - Placement of Notice for one week in the Guardian and the London Gazette - Placement of Notice for three weeks in the Lincolnshire Echo and the Retford Times £37950
Note on BD39: Eve Browning: Invoice 205242 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Media monitoring - Management of issue of Change Application Notification of Hearings Notice, including drafting, design and distribution. - Management of Cottam Solar Application Documents request by USB. £2566 Cottam Change Application- Notification of Hearings Notice and Cover Letter - Print and Postage of Notice to Local Information Points - Placement of Notice for one week in the Lincolnshire Echo and the Retford Times £8250
Note on BE39: Eve Browning: Invoice 205305 Ongoing Communications Support, including: - Hosting of communications channels (Freephone, freepost, email) - Hosting of website - Meeting attendance and project team liaison - Media monitoring - Management of issue of Change Application Notification of Hearings Notice, including drafting, design and distribution. - Management of Cottam Solar Application Documents request by USB. £2566
Note on BF39: Eve Browning: Invoice 205366 Single fee for limited support up to determination decision, including: - hosting of communications lines (freephone, freepost, email and website, including renewals where necessary). - handling of limited enquiries and team liaison. £1335
Note on M40: Eve Browning: 12 days at £960/day Additionally up to 10 days required at examination
Note on R40: Eve Browning: Remove 1320
Note on AI40: Eve Browning: Invoice 0903-2206-1 PEIR SoN draft
Note on AO40: Eve Browning: Invoice 0903-2212-1
Note on AX40: Eve Browning: Invoice 0903-2309-1 Relevant representation responses and mock hearing - £1320
Note on BA40: Eve Browning: Invoice 0903-2312-1 Responses to ExA 1st Written Questions - £1920
Note on BC40: Eve Browning: Invoice 0923-2402-1 Cottam Solar Relevant Representations, DL2 responses, DL3 responses, FWQ, DL4 responses - £1860
Note on M42: Eve Browning: Atkins
Note on N42: Eve Browning: Centremaps
Note on AG42: Eve Browning: Invoice UK-CI-036732
Note on M43: Eve Browning: Pager Power
Note on C44: Eve Browning: Also invoice us for flood risk work
Note on M44: Eve Browning: Delta Simons. Includes Ragwhistle but not cable route
Note on AI44: Eve Browning: Invoice DS033208
Note on AJ44: Eve Browning: Cable search area Envirocheck report and PRA Invoice DS034021
Note on AL45: Eve Browning: Invoice 153785
Note on AH46: Eve Browning: Invoice 22008075
Note on AP46: Eve Browning: Invoice 23000586 Completion of ES chapter for Climate Change and associated front end input - £3193
Note on AZ46: Eve Browning: Invoice 23015267 Input into ExAs - 6 hours Senior Consultant Time - £732
Note on BB46: Eve Browning: Input into SoCG - £1010 Input into Statement of Commonality - £1010 RR comments - hourly rate Revisions to docs - hourly rate ExA questions - hourly rate Interrelationships report - £1985 Hearing attendance (full day) - £1985 Hearing attendance (half day) - £995
Note on AM47: Eve Browning: JSM invoice SI31553
Note on AP47: Eve Browning: Invoice SI400190 Feasibility studies, engineering drawings and advice - £14151.67
Note on AX47: Eve Browning: Invoice SI402426 Bailey bridge / culvert analysis - £1084.60 Invoice SI402532 Feasibility study (Mar-Aug 2023) - £3253.79
Note on BB47: Eve Browning: Invoice SI403954 Cable route engineering queries - £542.30
Note on BC47: Eve Browning: Invoice SI404345 Normanby by Stow queries - £542.30
Note on BF47: Eve Browning: Invoice SI406022 Feasibility Studies - railway crossings - £135.57
Note on AL48: Eve Browning: Invoice 1860GV003977 Ecology surveys on EDF land £1500 per access, plus £2000 licence entry fee
Note on AM49: Eve Browning: Solar Energy UK invoice INV-3070
Note on AX49: Eve Browning: Invoice INV-3568 NSIP Forum membership - £10000
Note on AM50: Eve Browning: Viking Energy invoice CSP-001 Construction schedule and waste estimation
Note on AN50: Eve Browning: Invoice CSP-002
Note on C51: Eve Browning: Client account that then Pinsent draws down on when third party legal teams request money
Note on AM51: Eve Browning: Payment made to Pinsent Masons for protective provision undertakings for: - NGET - NG Gas - NPG - WPD - Anglian Water - Uniper All circa £3k each
Note on AR51: Eve Browning: Cadent Gas Exolum NETS Network Rail Severn Trent NG Elec Distr Canal and River Trust Environment Agency
Note on AU51: Eve Browning: Invoiced to date: Invoice 02160112 Weightmans Northern Powergrid £441.63
Note on AX51: Eve Browning: £2158.20 Canal and Rivers Trust authorised
Note on AZ51: Eve Browning: Gross interest paid in - £189.89
Note on BA51: Eve Browning: Gross interest paid in - £99.83
Note on BB51: Eve Browning: Gross interest paid in - £99.94
Note on BC51: Eve Browning: £810.81 Weightmans invoice 02198519 - Northern Powergrid legal costs for negotiating protective provisions Weightmans invoice 02232693 - Northern Powergrid legal costs for negotiating protective provisions - £1392.93
Note on BD51: Eve Browning: £5500 Cadent Gas PPs and side agreement legal fees NGED (Osborne Clarke) Contribution to reasonable legal fees in connection with the negotiation and completion of the Asset Protection Agreement and related matters - £9000 Ref: AHPK/1192249
Note on BE51: Eve Browning: vwv invoice BN1-00175149-02 Exolum protective provisions negotiation - £1915
Note on BF51: Eve Browning: CMS Invoice 1000-0184184 Negotiation of EDF protective provisions - £2589.78
Note on BG51: Eve Browning: CMS Cameron McKenna Nabarro Olswang LLP invoice 1000-0201778 Negotiation of EDF protective provisions £1802.34 Weightmans LLP invoice 02253178 Negotiation of Northern Powergrid protective provisions £228.69
Note on AO52: Eve Browning: Invoice 6722956
Note on AY53: Eve Browning: BST&T Consultancy Services Invoice 1527 Technical review of battery fire safety management plan. Hours worked x Review process includes meetings, document analysis (OBFSMP + fire note), content recommendations & amendments - £8400
Note on BA53: Eve Browning: BST&T invoice 1528 Review of OBSSMP Review process includes meetings (LFR engagement), document analysis (OBSSMP + Fire note) , DCO submissions, content recommendations & amendments (OBSSMP + Fire note) £5600
Note on BB53: Eve Browning: Invoice 1532 Expert witness hearing - daily rate Flat rate for DCO planning meeting £ 1,600.00 Mileage Total mileage for Cottam DCO hearing attendance £115.20 Expert witness content preparation Hours x DCO meeting, submissions and hearing content provision £800.00 Technical review of battery fire safety management plan. Review process includes FRS meeting, FRS engagement, ERP content template for OBSSMP, site design review £1000 Total £3515.20
Note on BC53: Eve Browning: Invoice 1536 Expert witness content preparation Hours x Cottam DCO written submission content preparation - £1400
Note on BD53: Eve Browning: Invoice 1544 Written submission content preparation 2.5hrs - £500
Note on C54: Eve Browning: Will we need a PO for this refund?
Note on BC54: Eve Browning: 1. Cable Route Corridor survey costs Archaeology (GeoPhys) £ 3,582.36 Archaeology (Trial Trenching) £ 22,479.47 Archaeology (Landowner Fees) £ 6,048.74 Archaeology (LIDAR) £ 1,042.04 Archaeology (geophys Normanby by Stow) £ 1,012.50 Ecology (Normanby by Stow) £ 530.00 Total £ 34,695.12 2. Cottam survey costs on Tillbridge Principal Site Ecology £ 25,900.15 Arch (GeoPhys) £ 35,635.50 Arch (Trial Trenching) £ 40,259.95 Data Collection £ 825.00 Total £ 102,620.60 Grand Total (1 and 2) £ 137,315.72
Note on M55: Eve Browning: Dalcour Maclaren, quote includes expenses and post DCO submission work. Additional invoice (quote from 20.10.21 + out of scope items added on) + £650 for highways searches + half of addional quote 12.11.21 +12134 additional predicted spend (Rob Jones budget review email)
Note on N55: Eve Browning: RSK estimated between £103k to £188k for each project, this figure is in the middle. Based upon new cable routes
Note on AG55: Eve Browning: Invoice UK-Ci-036732
Note on AH55: Eve Browning: Invoice UK-CI-043782
Note on AI55: Eve Browning: Invoice UK-CI-049692
Note on AJ55: Eve Browning: Invoice UK-CI-058020
Note on AK55: Eve Browning: Invoice UK-CI-065058 Includes previously missed expenses
Note on AL55: Eve Browning: Invoice UK-CI-069048
Note on AM55: Eve Browning: Invoice UK-CI-079014 Land agency services
Note on AN55: Eve Browning: Invoice UK-CI-083466 Book of reference creation
Note on AO55: Eve Browning: Invoice UK-CI-094470
Note on AP55: Eve Browning: Invoice UK-CI-099222 Land agency services - £54,349.55
Note on AQ55: Eve Browning: Invoice UK-CI-109710 Pre and post-submission work - £5994.20
Note on AR55: Eve Browning: Invoice UK-CI-115176 Post-submission S56 notices - £18417.62
Note on AS55: Eve Browning: Invoice UK-CI-126216 Land agency services - £8533.90
Note on AT55: Eve Browning: Invoice UK-CI-130458 Land agency services - £4060.50
Note on AU55: Eve Browning: Invoice - UK-CI-138030 Land agency services - £2768.95
Note on AV55: Eve Browning: Invoice UK-CI-147324 Land agency services - £2465.50
Note on AW55: Eve Browning: Invoice UK-CI-155280 Land agency services - £2361.75
Note on AX55: Eve Browning: Invoice UK-CI-163062 Land agency services - £2536.50
Note on AY55: Eve Browning: Invoice UK-CI-171390 Land agency services - £2204.25
Note on AZ55: Eve Browning: Invoice UK-CI-179862 Land agency services - £11,492.88
Note on BA55: Eve Browning: Invoice UK-CI-185598 Book of Reference updates for deadlines and change application - £9738.19
Note on BB55: Eve Browning: Invoice UK-CI-194040 Land agency services - £7470.68
Note on BC55: Eve Browning: Invoice UK-CI-200178 Land agency services - £6438.29
Note on BD55: Eve Browning: Invoice UK-CI-208914 Land agency services - £4319.67
Note on BE55: Eve Browning: Invoice UK-CI-216222 Land agency services - £855.12
Note on BF55: Eve Browning: Invoice UK-CI-225564 Land agency £938.07 Utilities search report £3535 Utility search map £2510 Total £6983.07
Note on BH55: Eve Browning: Invoice UK-CI-234510 Land referencing - £412.50
Note on BJ55: Eve Browning: Thank you for contacting us regarding the service of your s134 Notices. We have reviewed the Section’s requirements and detail our quote below: • HMLR Title Refresh and Registered Company Address checks • Mail merge of s134 documents, including a letter and s134 Notice • Quality assurance reviews of the statutory documents prior to posting • Preparation of site notices • Erection of site notices • Maintenance of site notices for 6 weeks • Removal of site notices • Project management including meetings Our quote assumes that the s134 Notice and associated letter templates will be provided to us. We would use the same notice locations as those at s56 (no more than 5km apart is good practice) and a site notice will be erected for all unregistered land. The cost to prepare and issue the above documentation is £7300.00 excluding expenses. Expenses will include: • HM Land Registry costs • External printing • Postage costs (we would recommend sending recorded) • Mileage Expenses estimate £2700
Note on AG56: Eve Browning: Invoice INSU00215673
Note on AH56: Eve Browning: Invoice INSU00224477
Note on AI56: Eve Browning: Invoice INSU00230106
Note on AJ56: Eve Browning: Invoice INSU00241036 Land agency work, project management
Note on AK56: Eve Browning: Invoice INSU00246663
Note on AL56: Eve Browning: Invoice INSU00254910 Land agency and project management
Note on AM56: Eve Browning: Invoice INSU00263963
Note on AO56: Eve Browning: Invoice INSU00293464 Our Land Agency Services for work completed on the following; Cottam Solar Project - £1966.25 plus 50% of project management time £1026.25 = £2992.50
Note on AQ56: Eve Browning: Invoice INSU00300887 (Savills) Land Agency services - £213.75 Invoice UAI-23-08803 (Bruton Knowles) HoTs negotiations - £5939.40
Note on AR56: Eve Browning: Invoice UAI-23-09051 (Bruton Knowles) HoTs negotiation - £5261.75 Invoice INSU00309485 (Savills) (dated November 2022?) Land agency- £6348.75
Note on AS56: Eve Browning: Invoice UAI-23-09334 HoTs negotiation, data processing and plan production - £8820
Note on AT56: Eve Browning: Invoice UAI-23-09870 HoTs negotiations - £4291.50
Note on AU56: Eve Browning: Invoice UAI-23-09872 HoTs negotiations - £5222.75
Note on AV56: Eve Browning: Invoice UAI-24-10184 HoTs negotiation - £6450.50
Note on AW56: Eve Browning: Invoice UAI-24-10535 HoTs negotiation - £6266.44
Note on AX56: Eve Browning: Invoice UAI-24-10804 HoTs negotiations - £7719.02
Note on AY56: Eve Browning: Invoice UAI-24-10961 HoTs negotiations - £6374.75 Expenses: £2.27
Note on AZ56: Eve Browning: Invoice UAI-24-11212 Access licences and HoTs negotiations - £6101.25
Note on BA56: Eve Browning: Invoice UAI-24-11580 Cable route negotiations - £8828.50
Note on BB56: Eve Browning: Bruton Knowles invoice UAI-24-11877 Cable route landowner negotiations - £4032.50 Expenses - £3 Total £4035.50
Note on BC56: Eve Browning: Invoice UAI-24-12436 HoTs negotiation and production of option and easement plans - £8758.25
Note on BD56: Eve Browning: Bruton Knowles Invoice UAI-24-12603 Land agency services - £6780.50 Expenses - £3.00 Savills refund from client account Returned leftover amount from client account for survey access fees - £1581.89
Note on BE56: Eve Browning: Invoice UAE-24-13026 Land agency services - £4321.50
Note on BF56: Eve Browning: Invoice UAI-24-13302 Land agency services £3023.75 Expenses £6
Note on BG56: Eve Browning: Invoice UAI-24-13643 Easement negotiation, project meetings, land valuation advice £1993.75
Note on BH56: Eve Browning: Invoice UAI-24-13884 Land agency £939.35 Expenses £23.85 Total £963.20
Note on C57: Eve Browning: How do we do POs for these?
Note on AG57: Eve Browning: Paid to Savills client account after Request for Payment to agree survey access
Note on AN57: Eve Browning: Payment Request: 2022/002C Landowner access payments (surveys and access licences)
Note on AQ57: Eve Browning: Perkins George Mawer and Co Invoice - EM/RW/C6.2 1.0 Angela Shirley Riddle option incentive fee - £250 Invoice - EM/RW/C.62 13.0 Matthew Thomas Winter, Michael Winter & Neil Richard Winter & Tim Winter option incentive fee - £250 Invoice - EM/RW/C.62 7.0/8.0 JMR Farms option incentive fee - £1000 EPR - Adie Pepperdine 37.0 - Williams - legal fees - £1200 EPR - Sills and Betteridge Winter 13.0 - legal fees - £2200
Note on AR57: Eve Browning: George Perkins Mawer invoice EM/AP/S.61 18.0 Alan Searby option incentive fee - £250 EPR - Taylor Vinters 20.0 Winterquay - £5000 EPR - Wilkin Chapman 28.0 Taylor legal fees - £1200 EPR - Burton and Dyson 11.0 Blades agent fees - £1200 11.0 Blades legal fees - £1200 7.0 - JMR agent fees - £1200 7.0 - JMR legal fees - £1200 1.0 - Angela Riddle agent fees - £1200 1.0 - Angela Riddle legal fees - £1200 EPR - G and J Lonsdale (LH Farming Ltd) EPR then invoiced December 2023 - invoice no: 904 36.0 Lonsdale agent fees - £1200
Note on AS57: Eve Browning: JAS Martin & Co invoice RDS/sab/SD1 HoTs incentive payments for: - Southwell and Nottingham Board of Finance - £500 - Ann Marie Lobley - £500 - Mills and Reeve and Buxton - £500 - Mills and Reeve and Buxton - £500 Perkins George Mawer& Co invoice EM/SH/W.62 HoTs incentive payment for: - 26.0 Timothy Leslie Waudby - £1000
Note on AU57: Eve Browning: Invoice from Jas Martin & Co. Southwell & Nottingham Diocesan Board of Finance - Survey access payment £250 (no VAT) - Agent fee £300 (plus VAT) (EPR) Burgess Salmon LLP Client Account Ref: 36.1 - Lonsdale Legal fees - £2000
Note on AW57: Eve Browning: Hall Consultancy (Agribusiness) Ltd - Invoice SI-693 Ref:CM & AM Developments HoTs signing incentive - £2000 Agents fees - 50% at HoTs - £1000 Farmers/landowners time - 50% at HoTs - £500 Hall Consultancy (Agribusiness) Ltd - Invoice SI-691 Ref: Jennifer Anne Taylor HoTs signing incentive - £1000 Agents fees - 50% at HoTs - £1000 Farmers/landowners time - 50% at HoTs - £500 Hall Consultancy (Agribusiness) Ltd - Invoice SI-692 Ref: Charles Marshall HoTs signing incentive - £1000 Agents fees - 50% at HoTs - £1000 Farmers/landowners time - 50% at HoTs - £500
Note on AX57: Eve Browning: Rebecca Andrews Incentive payment - £500 JAS Martin & Co.- Invoice RDS/sab/SDTV SOL Ref: Southwell Diocese Agent fee - £1245 Sills and Betteridge LLP (exceptional payment) Ref: 13.0 Winter Landowner mortgage fee - £300
Note on BA57: Eve Browning: G and J Lonsdale (LH Farming Ltd) - Invoice no: 974 36.0 Lonsdale agent fees - £1000
Note on BB57: Eve Browning: Fisher German Invoice 2125110 Ref: 36.0 Cottam Farming Agent fees £1418.85 Mileage £56.25 Total £1475.10
Note on C58: Eve Browning: Would need to agree an individual PO each time
Note on AH58: Eve Browning: Pinsent Masons HoTs and option review, creation and advice Invoice 6673252
Note on AI58: Eve Browning: Invoice 6683352 Bank consent work
Note on AL58: Eve Browning: Invoice 6699951
Note on AU58: Eve Browning: Invoice 3145398 - Walker Morris Counsel’s fees incurred for provision of an opinion letter on the Cottam/West Burton cable route - £3300
Note on AV58: Eve Browning: Invoice 3147028 - Walker Morris Professional fees in connection with cable reporting for Cottam Solar Project - £20900
Note on BC58: Eve Browning: Walker Morris invoice 313262 - Cable reporting - £2500 - Disbursements - Index map search - £52 - Office copy entries - £132
Note on BD58: Eve Browning: Pinsent Masons quote for Network Rail property agreements
Note on BB59: David Elvin: £6153 added manually as this was the balancing contingency payment for month 1 when reviewing cashflow on 17/05/21
Note on AF61: Eve Browning: Euros - need to adjust for exchange rate? Noel Ryan and Associates - annual accounts
Note on AQ61: Eve Browning: Invoice 2063442 - Blick Rothenburg Annual charge for the year to 31 December 2023 in respect of company registrar services, including maintenance of the companys statutory books, preparation and filing with the Registrar of Companies of the Confirmation Statement and notifications of any changes in respect of the companys officers and registered office, in accordance with the information and particulars supplied to us. £500 Annual confirmation statement filing fee. £13 Total £513
Note on AS61: Eve Browning: Blick Rothenberg invoice 2063875 Bonsdale Solar Farm Ltd Annual charge for the year to 31 December 2023 in respect of company registrar services, including maintenance of the companys statutory books, preparation and filing with the Registrar of Companies of the Confirmation Statement and notifications of any changes in respect of the companys officers and registered office, in accordance with the information and particulars supplied to us. £500 Annual confirmation statement filing fee. £13
Note on BB61: Eve Browning: Shakespeare Martineau invoice 100161053 Professional Charges for preparing and filing a UK Trade Mark Application for the COTTAM SOLAR PROJECT device - £900

## Euston
Euston Budget Cost
|  |  |  | Month |  |  | Option signed |  |  |  | App. Submitted | [10 empty] | Quote
Item | Sub-Item | Total Cost (£) Quoted/to date | Total Cost (£) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Grid | DNO Application | 3000 | 8000 | Month 1: 5000
| Consultant |  | 2000 | Month 1: 500; Month 2: 500; Month 3: 500; Option signed 4: 500
| Deposit/security | 50000 | 50000 | Option signed 4: 50000
Lease/Option |  | 36000 | 40000 | Month 1: 15000; Month 2: 15000; Month 3: 10000
Planning Consultant |  | 18000 | 24000 | 1000 |  | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Planning Application Fee |  | 145000 | 150000 | Option signed 6: 150000
Planning Studies | Heritage Statement | 2500 | 5000 | Option signed 4: 3000; App. Submitted 8: 2000
| ALC Classification | 3500 | 5000 | Option signed 4: 5000 | 3400
| Topographical Study |  | 5000 | Option signed 4: 4000; App. Submitted 8: 1000
| Flood Risk Assessment | 2250 | 4000 | Option signed 4: 3000; App. Submitted 8: 1000 | 1750
| Geophysical Survey | 26000 | 25000 | Option signed 4: 25000
| Trial Trenching | 90000 | 90000 | Option signed 5: 20000; Option signed 6: 20000; Option signed 7: 20000
| Arboricutural Survey |  | 3000 | Option signed 4: 2000; App. Submitted 8: 1000
| Highways Survey | 0 | 5000 | Option signed 4: 3000; App. Submitted 8: 1000; App. Submitted 10: 1000 | incl in FRA
| Ecological Survey | 7500 | 10000 | Option signed 4: 5000; App. Submitted 8: 3000; App. Submitted 10: 2000
| LVIA | 8500 | 7500 | Option signed 4: 5000; App. Submitted 8: 1500; App. Submitted 10: 1000
| CTMP | 3000 | 3000 | Option signed 4: 2000; App. Submitted 8: 1000 | incl in FRA
| Noise | 1500 | 3000 | Option signed 4: 2000; App. Submitted 8: 1000
| 3D model |  | 15000 | Option signed 4: 12500; App. Submitted 8: 2500
| Glint/Glare | 4000 | 7500 | Option signed 4: 5000; App. Submitted 8: 2500
| EIA | 14000 | 15000 | Option signed 4: 5000; Option signed 5: 2000; Option signed 6: 2000; Option signed 7: 2000; App. Submitted 8: 2000; App. Submitted 9: 1000; App. Submitted 10: 1000
| Already spent (awaitng breakdown) | 21000
Contingency | 10% of planning costs |  | 34700 | 100 | 0 | 100 | 8350 | 2400 | 17400 | 2400 | 2150 | 300 | 700 | 200 | 200 | 200 | 200 | 0 | 0 | 0 | 0
Third Party Wayleaves |  | 0 | 20000 | Option signed 4: 10000; Option signed 5: 5000; Option signed 6: 2500; Option signed 7: 2500
Satisfaction of pre-commencement planning conditions |  |  | 15000 | App. Submitted 12: 5000; App. Submitted 13: 5000; App. Submitted 14: 5000
Transaction Cost |  | 3000 | 15000 | App. Submitted 15: 5000; App. Submitted 16: 5000; App. Submitted 17: 5000
Total |  | 438750 | 561700 | 21600 | 15500 | 11600 | 152350 | 31400 | 193900 | 28900 | 23650 | 3300 | 7700 | 2200 | 7200 | 7200 | 7200 | 5000 | 5000 | 5000 | 0
Installed capacity | 65
Total/MW |  | 6750 | 8641.5385
Costs TBC

## Lullington
Lullington Budget Cost | [11 empty] | Planning Submitted | [12 empty] | Planning Committee 26th July |  |  |  |  | Submit Appeal |  |  |  | Hearings |  |  | 21st July Decision
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | time axis 2021-01-31 to 2025-12-01
Grid | DNO Application | 5000 | 20000 |  | 20500 |  | 2021-01-31: 20000; 2023-02-28: 500
| Consultant | 2000 | 0 |  | 0
| Deposit/security | 50000 | 100000 |  | 100000 |  | 2021-03-31: 60000; 2022-12-31: 40000
Lease/Option |  | 40000 | 44282.49 |  | 51899.16 |  | 2021-01-31: 42782.49; 2022-10-31: 1500; 2023-01-31: 1816.67; 2023-04-30: 5800
Planning Consultant |  | 24000 | 54176.96 | 21000 | 54176.96 | Lanpro | 2021-01-31: 2794.75; 2021-02-28: 679; 2021-03-31: 1749; 2021-05-31: 8935.75; 2021-06-30: 4481; 2021-07-31: 331.5; 2021-09-30: 427.75; 2021-10-31: 1160; 2021-11-30: 993; 2022-01-31: 3694; 2022-03-31: 1473.5; 2022-04-30: 318.5; 2022-05-31: 288; 2022-06-30: 390; 2022-07-31: 1950; 2022-08-31: 3442.52; 2022-09-30: 2000; 2022-10-31: 3577; 2022-11-30: 1700; 2022-12-31: 576.23; 2023-01-31: 250; 2023-05-31: 8559.69; 2023-08-31: 4405.77
Planning Application Fee |  | 150000 | 112863 | 111200 | 112863 | South Derbyshire | 2021-06-30: 112863
Planning Studies | Heritage Statement | 3000 | 6682.6 | 2700 | 14671.12 | Lanpro | 2021-03-31: 1839.6; 2022-10-31: 4843; 2023-02-28: 558; 2023-04-30: 7430.52
| ALC Classification | 5000 | 5000 |  | 10788 |  | 2022-09-30: 5000; 2023-01-31: 2025; 2023-04-30: 3763
| Soil Management Plan |  | 450 | 1250 | 450 | Tetra Tech | 2021-07-31: 450
| Topographical Study | 4000 | 5325 | 1375 | 5325 | ALS Surveys | 2021-01-31: 3950; 2021-05-31: 1375
| Flood Risk Assessment | 4000 | 4045.5 | 1950 | 4045.5 | Rossi Long | 2021-05-31: 2133; 2021-12-31: 912.5; 2022-07-31: 1000
| Geophysical Survey | 20000 | 17300 |  | 17300 |  | 2021-01-31: 17300
| Trial Trenching | 60000 | 0 |  | 0
| Arboricutural Survey | 2000 | 2000 |  | 2000 | Lanpro | 2021-06-30: 2000
| Traffic speed survey |  | 750 | 750 | 750 | PCC | 2021-03-31: 750
| Ecological Survey | 8000 | 37472.66 | 38510 | 58302.66 | Tetra Tech | 2021-05-31: 15846.66; 2021-06-30: 9425; 2021-07-31: 4000; 2021-08-31: 1280; 2022-03-31: 4155; 2022-06-30: 1170; 2022-12-31: 1596; 2023-02-28: 2085; 2023-06-30: 15726; 2023-07-31: 3019
| LVIA | 7500 | 36468 | 3700 | 36468 | Liz Lake | 2021-03-31: 3350; 2021-05-31: 11700; 2021-06-30: 4875; 2022-02-28: 510; 2022-04-30: 3000; 2022-07-31: 380; 2022-10-31: 12653
| CTMP | 3000 | 3216.25 | 2600 | 3216.25 | Rossi Long | 2021-04-30: 3216.25
| Noise | 3000 | 2250 | 2250 | 2250 | Tetra Tech | 2021-06-30: 2250
| 3D model | 15000 | 0 |  | 0
| Glint/Glare | 7500 | 3588 | 2904 | 3588 | Pager Power | 2021-04-30: 2964; 2021-05-31: 624
| Communications |  | 8500 | 6750 | 8500 | Thorncliffe | 2021-09-30: 1500; 2021-11-30: 1500; 2022-06-30: 1500; 2022-07-31: 4000
| EIA | 15000 | 45780 |  | 45780 |  | 2021-01-31: 45780
| Planning Lawyer |  |  | 46000 | 143657.8 | Pinsent Masons | 2022-11-30: 2518; 2022-12-31: 9094.8; 2023-04-30: 31799.2; 2023-05-31: 2910; 2023-06-30: 11178; 2023-08-31: 23011.2; 2023-09-30: 36787; 2023-11-30: 4213.4; 2023-12-31: 22146.2
Contingency | 10% of planning costs | 34700 | 0 | N/A | N/A |  | 6982.475 | 67.9 | 768.86 | 618.025 | 4061.441 | 13589.4 | 478.15 | 128 | 192.775 | 116 | 249.3 | 91.25 | 369.4 | 51 | 562.85 | 331.85 | 28.8 | 306 | 733 | 344.252 | 700 | 2107.3 | 421.8 | 1126.703 | 227.5 | 264.3 | 0 | 4299.272 | 1146.969 | 2690.4 | 301.9 | 2741.697 | 3678.7 | 0 | 421.34 | 2214.62
Third Party Wayleaves |  | 20000 | 15000 |  | 20000 |  | 2022-05-31: 10000; 2022-06-30: 5000; 2022-07-31: 2500; 2022-08-31: 2500
Satisfaction of pre-commencement planning conditions |  | 15000 | 15000 |  | 15000 |  | 2022-04-30: 5000; 2022-05-31: 5000; 2022-06-30: 5000
Transaction Cost |  | 15000 | 0 |  | 15000 |  | 2022-06-30: 5000; 2022-07-31: 5000; 2022-08-31: 5000
Total |  | 517700 | 540150.46 | 242939 | 746531.45 |  | 139589.715 | 746.9 | 68457.46 | 6798.275 | 44675.851 | 193860.4 | 5259.65 | 1408 | 2120.525 | 1276 | 2742.3 | 1003.75 | 4063.4 | 561 | 6191.35 | 53331.35 | 15316.8 | 18366 | 15563 | 11286.772 | 7700 | 24680.3 | 4639.8 | 52393.733 | 4319.17 | 3407.3 | 0 | 53091.992 | 12616.659 | 29594.4 | 3320.9 | 30158.667 | 40465.7 | 0 | 4634.74 | 24360.82
Installed capacity | 55
Total/MW |  | 9412.7273 | 9820.9175 | 4417.0727 | 13573.2991
Note on AH4: Lesley Giles: Blick Rothenberg
Note on AF6: Lesley Giles: Grid feasability surveys (not part of grid offer costs)
Note on AJ11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Daniel Baird hearing fee
Note on X20: Lesley Giles EIA re-screening
Note on AD20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Costs were given for an Inquiry, we will pursue a Hearing, should be cheaper
Note on I26: Lesley Giles: £45,780 added to balance total spend on ledger 12/01/2022
Note on AL27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £27,500 added for Gareth to advocate at Hearings
Note on AN27: Lesley Giles: Statutory challenge
Note on AO27: Lesley Giles: PM Statutory challenge
Note on AQ27: Lesley Giles: Pinsent Masons 6784039
Note on AR27: Lesley Giles: 6792373 6799196
Note on E32: Lesley Giles: Not Including £800,000 grid payment in Q3 2022

## Camblesforth
Camblesforth Budget Cost | [11 empty] | Planning Submitted | [12 empty] | Planning Committee Wed 6th |  |  | Discharge Conditions
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | J
Grid | DNO Application | 0 | 0 |  | 0 | 0
| Consultant | 0 | 86800 |  | 86800 | 0 | [23 empty] | 2800 | [6 empty] | 1500 |  |  | 82500
| Deposit/security | 180000 | 180000 | 180000 | 180000 |  | 180000
Lease/Option |  | 40000 | 163439.2 | 40000 | 163439.2 | Walker Morris | 48000 | 20000 | [16 empty] | 2460 | 1750 | 5450 | 7500 |  | 4200 | 12714 | 449 |  | 3013.35 | 3013.35 | 1750 |  | 3198 | 5500 | 19800 |  | 24641.5
Legal/Coorporate |  |  | 2666.19 |  | 2666.19 |  | 500 | 1166.19 | [10 empty] | 500 | [12 empty] | 500
Planning Consultant |  | 24000 | 41988.5 | 21000 | 41988.5 | Lanpro | 1938.5 | 5491.75 | 2533.5 |  | 4942 | 1795.75 | 3158.13 |  | 384.5 | 658 | 428.25 |  | 3209.75 |  | 261.5 | 548 | 3835.5 | 187 | 750 | 3042.87 | 1500 | 3756 | 1000 | 137.5 | 750 |  |  | 750 | 930
Planning Application Fee |  | 150000 | 186651 | 150000 | 186651 | [6 empty] | 171651 | [16 empty] | 15000
Planning Studies | Heritage Statement | 5000 | 10098 | 4400 | 10098 | Lanpro |  | 4400 | [19 empty] | 2978 |  |  | 2720
| ALC Classification | 5000 | 0 | 4300 | 0
| Topographical Study | 5000 | 10035 |  | 10035 | Sensat | [9 empty] | 8500 | [11 empty] | 685 | [12 empty] | 850
| Flood Risk Assessment | 4000 | 3700 | 3000 | 3700 | Delta Simons | [21 empty] | 2950 |  |  |  | 750
| Geophysical Survey | 25000 | 26114 | 30600 | 26114 |  |  | 26114
| Trial Trenching | 75000 | 0 |  | 0
| Arboricutural Survey | 3000 | 3000 |  | 3000 |  |  |  |  | 2000 |  |  |  | 1000
| Highways Survey | 5000 | 4800 | 4100 | 4800 | Delta Simons |  |  | 900 | 3000 | [10 empty] | 900
| Ecological Survey | 10000 | 29685 | 6000 | 29685 | Delta Simons | 2500 | 3450 |  | 2500 |  | 2500 | 2500 |  | 490 | 9420 | [5 empty] | 1000 | [6 empty] | 5325
| LVIA | 7500 | 19933.75 | 9575 | 19933.75 | Liz Lake |  | 2825 |  |  | 4848.75 | [11 empty] | 2460 | [5 empty] | 9800
| CTMP | 3000 | 7190 | 0 | 7190 | [8 empty] | 1000 | [14 empty] | 3400 |  | 1950 | [10 empty] | 840
| Noise | 3000 | 2550 |  | 2550 | Tetra Tech |  |  |  | 2000 |  |  |  | 550
| 3D model | 15000 | 2500 |  | 2500 | [8 empty] | 2500
| Glint/Glare | 7500 | 7500 | 4750 | 7500 | Pager Power |  |  |  | 5000 |  |  |  | 2500
| EIA | 15000 | 0 | 18000 | 0
| CMP |  | 5000 |  | 5000 | [23 empty] | 5000
| Land Contamination |  | 3000 |  | 3000 | [22 empty] | 3000
| Planning Performance Agreement | 10000 | 10068.9 |  | 10068.9 | [25 empty] | 7198 | [6 empty] | 1322 |  |  | 1548.9
15676.85
Contingency | 10% of planning costs | 35700 | 0 |  | N/A |  | 443.85 | 4228.075 | 343.35 | 1450 | 979.075 | 17594.675 | 565.813 | 755 | 87.45 | 1857.8 | 42.825 | 0 | 320.975 | 0 | 116.15 | 154.8 | 629.55 | 18.7 | 75 | 304.287 | 150 | 1336.9 | 3952.5 | 13.75
Third Party Wayleaves |  | 0 | 25000 |  | 25000 |  |  |  |  | 10000 | 5000 | 2500 | 2500 | [17 empty] | 5000
Satisfaction of pre-commencement planning conditions |  | 15000 | 0 |  | 0
Transaction Cost | to date (admin, accounts etc) | 15000 | 15000 |  | 15000 | [18 empty] | 5000 | 5000 | 5000
Total |  | 657700 | 846719.54 | 475725 | 846719.54 |  | 233382.35 | 67675.015 | 3776.85 | 25950 | 15769.825 | 196041.425 | 8723.943 | 8305 | 961.95 | 20435.8 | 471.075 | 0 | 4030.725 | 0 | 1277.65 | 1702.8 | 6925.05 | 5205.7 | 8285 | 10097.157 | 7100 | 22205.9 | 43477.5 | 7151.25
Installed capacity | 65
Total/MW |  | 10118.4615 | 13026.4545 | 7318.8462 | 13026.4545
Note on AM5: Lesley Giles: Success Connections
Note on AP5: Lesley Giles: GEW2 Design costs
Note on I7: Lesley Giles: Retainer paid to Walker Morris for Landlords Legal and Agent fees in Oct 2019
Note on J7: Lesley Giles: DDM Agriculture Land Agent fees Feb 2020 Townend Clegg & co £10,000 Feb 2020
Note on AF7: Lesley Giles: Retainer for Knights
Note on AG7: Lesley Giles: Walker Morris invoice for their work
Note on AJ7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budd Legal
Note on AK7: Lesley Giles: Philips tenancy agreement legal costs
Note on AL7: Lesley Giles: walker morris costs
Note on AN7: Lesley Giles: Knights
Note on AO7: Lesley Giles: £2500 Knights - Aire and Ouse DoV to Lease £3000 Neil Budd - neighbours agreement for the sublease paddock
Note on AP7: Lesley Giles: DDM grass seed on Guy Poskitt's land
Note on AR7: Lesley Giles: 1. Aire and Ouse grass seed 2. Walker Morris No.3158312 3.
Note on AH8: Lesley Giles: Blick Rothenberg
Note on AD11: Lesley Giles: Utility search
Note on AG11: Lesley Giles: centre maps
Note on AQ13: Lesley Giles: ALS surveyor marking out the field boundary.
Note on AG28: Lesley Giles: GPR Survey by RSK
Note on AN28: Lesley Giles: JSM s14018775
Note on AQ28: Lesley Giles: Open Reach A243906
Note on AQ29: Lesley Giles: Guy Poskitt grass seed invoice Nov 2023
Note on AG31: Lesley Giles: 3 x days survey on Drax £5400 and £600 legal costs STA

## Brynrhyd
Brynrhyd Budget Cost | [14 empty] | App. Submitted | [10 empty] | Hearings 15-17th Aug |  | PINS Report | Decision Received 30th |  |  |  | Disharge Conditions
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2021-01-31 | 2021-02-28 | 2021-03-31 | 2021-04-30 | 2021-05-31 | 2021-06-30 | 2021-07-31 | 2021-08-31 | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31
Grid | DNO Application | 0 | 889925 | 20000 | 889925 |  | 2021-01-31: 19925; 2023-03-31: 250000; 2023-06-30: 250000; 2023-08-31: 370000
| Consultant | 500 | 5000 |  | 5000 | WSP | 2021-07-31: 5000
| Deposit/security | 50000 | 250000 | 250000 | 250000 |  | 2022-04-30: 250000
Lease/Option |  | 0 | 151373.46 |  | 151373.46 | Walker Morris | 2021-05-31: 1137.5; 2021-08-31: 4000; 2022-03-31: 5000; 2022-05-31: 213.96; 2022-08-31: 13000; 2022-12-31: 2580; 2023-01-31: 71000; 2023-02-28: 650; 2023-05-31: 5800; 2023-06-30: 39680; 2023-07-31: 6112; 2023-08-31: 2200
Cooperation |  |  | 4668.98 |  | 4668.98 |  | 2021-01-31: 1675; 2022-01-31: 500; 2023-01-31: 500; 2023-06-30: 1993.98
Planning Lawyer |  |  | 31200 | 16200 | 31200 | Ashtons | 2022-08-31: 16200; 2022-09-30: 15000
Planning Consultant |  | 22000 | 79334.22 | 54700 | 79334.22 | Pegasus | 2021-03-31: 26080.32; 2021-06-30: 11400; 2021-07-31: 1520; 2021-09-30: 7350; 2021-10-31: 6394.8; 2022-01-31: 1450; 2022-02-28: 6850; 2022-07-31: 1376.6; 2022-09-30: 5912.5; 2023-01-31: 2000; 2023-05-31: 5000; 2023-06-30: 4000
Planning Application Fee |  | 150000 | 59906.59 |  | 59906.59 | PINS Wales | 2021-03-31: 1360.32; 2021-06-30: 23100; 2021-09-30: 500; 2021-12-31: 250; 2022-08-31: 2760; 2022-12-31: 29703.02; 2023-02-28: 1888.25; 2023-05-31: 345
Planning Studies | Heritage Statement | 5000 | 8063.75 | 6000 | 8063.75 | Pegasus | 2021-03-31: 3000; 2021-06-30: 800; 2021-09-30: 1850; 2021-10-31: 373.75; 2022-08-31: 800; 2023-06-30: 1240
| Outline WSI |  | 600 | 600 | 600 | Gwynedd Archaeological Trust | 2021-09-30: 600
| ALC Classification | 5000 | 6560 | 975 | 6560 |  | 2021-07-31: 975; 2023-06-30: 5585
| Soil Management Plan |  | 5300 | 1800 | 5300 | Askew Land + Soil | 2022-01-31: 1800; 2022-09-30: 1500; 2023-05-31: 2000
| Topographical Study | 4000 | 4872 |  | 4872 | Landmark Survey Wales | 2021-02-28: 4872; 2023-02-28: .
| Flood Risk Assessment | 4000 | 5200 |  | 5200 | Clive Onions | 2021-04-30: 1500; 2021-06-30: 1700; 2023-05-31: 2000
| SAB |  | 40010.6 | 46950 | 40010.6 | Burroughs | 2023-05-31: 4960; 2023-07-31: 25862; 2023-08-31: 9188.6
| Geophysical Survey | 20000 | 14400 | 11950 | 14400 | SUMO | 2021-05-31: 11950; 2021-07-31: 2450
| Trial Trenching | 60000 | 6147 |  | 6147 |  | 2023-05-31: 6147
| Arboricutural Survey | 3000 | 7811 | 4180 | 7811 | Barton Hyett Associates | 2021-05-31: 4180; 2022-08-31: 1706; 2022-09-30: 950; 2023-05-31: 975
| Highways Survey | 5000 | 4220 | 4500 | 4220 | Pegasus | 2021-06-30: 1500; 2022-02-28: 720; 2023-05-31: 2000
| Ecological Survey | 8000 | 40580 | 28880 | 40580 | Clarkson & Woods | 2021-03-31: 4520; 2021-06-30: 4637; 2021-08-31: 4332; 2021-09-30: 4557; 2022-01-31: 4247; 2022-10-31: 13842; 2023-05-31: 4445
| LVIA | 7500 | 34591.25 | 14100 | 34591.25 | Pegasus | 2021-03-31: 9150; 2021-06-30: 12800; 2021-09-30: 1500; 2022-02-28: 8250; 2022-09-30: 2441.25; 2023-06-30: 450
| CTMP | 3000 | 10245 |  | 10245 | Pegasus | 2021-03-31: 3500; 2022-02-28: 2600; 2022-08-31: 445; 2022-09-30: 1500; 2023-06-30: 2200
| Noise | 3000 | 7155 | 2800 | 7155 | ion Acoustics | 2021-03-31: 1300; 2021-05-31: 400; 2021-07-31: 1000; 2022-05-31: 1275; 2022-09-30: 680; 2023-04-30: 2500
| Ground Condition & Coal mining |  | 27906.8 | 3500 | 27906.8 | Integrale | 2021-03-31: 3225; 2021-05-31: 925; 2021-07-31: 1960; 2021-09-30: 695; 2022-07-31: 1435; 2022-09-30: 500; 2023-06-30: 19166.8
| 3D model | 15000 | 0 |  | 0
| Glint/Glare | 7500 | 15178 |  | 15178 | Pager Power | 2021-06-30: 2855; 2022-01-31: 1325; 2022-05-31: 3710; 2022-06-30: 4638; 2022-08-31: 2650
| EIA | 15000 | 0 |  | 0
Contingency | 10% of planning costs | 34500 | 0 |  | N/A |  |  | 487.2 | 5213.564 | 150 | 1745.5 | 5879.2 | 790.5 | 433.2 | 1705.2 | 676.855 | 0 | 25 | 882.2 | 1842 | 0 | 0 | 498.5 | 463.8 | 281.16 | 836.1 | 1348.375 | 1384.2 | 0 | 2970.302 | 200 | 188.825 | 0 | 0 | 0 | 3264.18 | 2586.2 | 918.86 | 0 | 0 | 0 | 0
Third Party Wayleaves |  | 20000 | 20000 |  | 20000 |  | 2023-01-31: 10000; 2023-02-28: 5000; 2023-03-31: 2500; 2023-04-30: 2500
Satisfaction of pre-commencement planning conditions |  | 15000 | 0 |  | 0
Transaction Cost |  | 15000 | 16994 |  | 16994 |  | 2023-04-30: 1994; 2023-05-31: 5000; 2023-06-30: 5000; 2023-07-31: 5000
Total |  | 472000 | 1747242.65 | 467135 | 1782013.571 |  | 21600 | 5359.2 | 57349.204 | 1650 | 20338 | 64671.2 | 13695.5 | 8765.2 | 18757.2 | 7445.405 | 0 | 275 | 10204.2 | 20262 | 5000 | 250000 | 5697.46 | 5101.8 | 3092.76 | 38397.1 | 29832.125 | 15226.2 | 0 | 35253.322 | 83700 | 7727.075 | 252500 | 6994 | 38672 | 332579.96 | 39560.2 | 382307.46 | 0 | 0 | 0 | 0
Installed capacity | 33
Total/MW |  | 14303.0303 | 52946.747 | 14155.6061 | 54000.4112
| Task | Name | Fee | Notes
| Hearing coordination, Liaising with PEDW, provide info requested by Stephen etc | Gareth Roberts | 2500 |  |  | £2k per month during determination | 2021-01-31: 28000
Hearing 1 [landscape]
| Landscape Position Statement | Andy Cook | 3100
| Consolidate Hearing Statement 1 & policy review. | Gareth Roberts | 1000
Hearing 2 [ecology]
| Statement to be prepared by Clarkson & Woods | n/a | n/a
| Pegasus input into Hearing Statement 2 | Gareth Roberts | 300
Hearing 3 [residential amenity, highway safety and conditions)
| Consolidated Hearing statement 3 | Gareth Roberts | 2000
| Transport Input into statement | Tony Jones | 500
| Landscape input into statement | Andy Cook | 700
Attendance at Virtual Hearings
(excludes travel costs and these will probably be limited to mileage to Ashfords office).
| Hearing session 1 | Gareth Roberts | 1200
|  | Andy Cook | 1900
| Hearing session 2 | Gareth Roberts | 1200
| Hearing Session 3 | Gareth Roberts | 1200
|  | Andy Cook | 1900
|  | Tony Jones (transport) | 1500
| Hearing Test event | Gareth Roberts | 175 | PEDW will hold a test event and this is likely to last around 20 mins.
SoCG
| SoCG with NRW – Clarkson & Woods leading | n/a | n/a
| Pegasus input into NRW SoCG. | Gareth Roberts | 300
| SoCG with LPA (including schedule of conditions) | Gareth Roberts | 1900
Other
| Con with Ashfords | All | 875
| Applicant’s closing statement – we understand that Ashford’s will be preparing this. | n/a | n/a
| Printing one set of all documentation for hearing | Pegasus will instruct external printers to undertake this work | At cost
22250
Note on AN4: Lesley Giles: 3rd and 4th grid stage payments
Note on O5: Lesley Giles: WSP
Note on P7: Lesley Giles: £4000 to Walker Morris for Option Variation
Note on AB7: Lesley Giles: Undertaking for Brian Richards solicitor for Option Variaiton £3000
Note on AG7: Lesley Giles: £1000 mount estate fees £70,000 Rees Richards introduction fee
Note on AK7: Lesley Giles: Jenkins crop loss for trial pits £200
Note on AL7: Lesley Giles: jenkins crop loss 800 Landowner legal fees for lease variations Walker Morris legal fees £35,280
Note on AM7: Lesley Giles: £960 Brian Richards crop loss/damages
Note on AN7: Lesley Giles: £1200 to HCR Brian Richards solicitor for cow side letter £1000 Morgan La Roche for Jenkins variation
Note on I8: Lesley Giles: Blick Rothenburg and Noel Ryan & Associates (Accountants & Auditors)
Note on AL8: Lesley Giles: Ansarada payment
Note on Q11: Lesley Giles: Discretionary advise service NRW
Note on T11: Lesley Giles: DNS Variation fee
Note on F18: Lesley Giles: Burroughs quote + assumed £15k for surveys £3k for application fee
Note on O19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Additional geophys by WYAS
Note on V22: Lesley Giles: speed survey
Note on N24: Lesley Giles: RVAA
Note on AL27: Lesley Giles: Hydrogeo
Note on AJ34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ansarada

## Hardwick
Hardwick Budget Cost
[6 empty] | Month |  |  | Option signed |  |  |  | App. Submitted
Item | Sub-Item | Budget | Quote | Notes | Total Cost (£) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Grid | DNO Application |  | 5000
| Consultant |  | 500 | 500 | 500 | Month 1: 500
| Deposit/security |  |  |  |  | Month 1: 50000
Lease/Option |  |  | 15000 | 15000 | 10000
Planning Consultant |  |  | 1000 |  | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Planning Application Fee | [5 empty] | Month 3: 150000
Pre-Application | Planning | 2000 | 5000 - 6000 | Lanpro
| Hydrology (flood risk) | 3000 | 2524 | ESP
| Landscape | 5000 | 5400 | Liz Lake
| Pre-Application consultation fee | 2000 |  | TBC with KLWN Council
| Expenses | 1000
Planning Studies | Heritage Statement | 5000 |  |  |  | Month 1: 3000; Option signed 5: 2000
| ALC Classification | 5000 |  |  |  | Month 1: 5000
| Topographical Study | 4000 | 5450 | ALS, not including underground services - separately quoted |  | Month 1: 4000; Option signed 5: 1000
| Flood Risk Assessment | 4000 |  |  |  | Month 1: 3000; Option signed 5: 1000
| Geophysical Survey | 20000 |  |  |  | Month 1: 25000
| Trial Trenching | 60000 |  |  |  | Month 2: 20000; Month 3: 20000; Option signed 4: 20000
| Arboricultural Survey | 3000 |  |  |  | Month 1: 2000; Option signed 5: 1000
| Highways Survey | 5000 |  |  |  | Month 1: 3000; Option signed 5: 1000; Option signed 7: 1000
| Ecological Survey | 8000 | 1900 | Commissioned to date from Wild Frontier - Phase 1, data search, breeding birds |  | Month 1: 5000; Option signed 5: 3000; Option signed 7: 2000
| LVIA | 7500 |  |  |  | Month 1: 5000; Option signed 5: 1500; Option signed 7: 1000
| CTMP | 3000 |  |  |  | Month 1: 2000; Option signed 5: 1000
| Noise | 3000 |  |  |  | Month 1: 2000; Option signed 5: 1000
| 3D model | 15000 |  |  |  | Month 1: 12500; Option signed 5: 2500
| Glint/Glare | 7500 |  |  |  | Month 1: 5000; Option signed 5: 2500
| EIA | 15000 |  |  |  | Month 1: 5000; Month 2: 2000; Month 3: 2000; Option signed 4: 2000; Option signed 5: 2000; Option signed 6: 1000; Option signed 7: 1000
Contingency | 10% of planning costs | 36227.4 | 1627.4 | 0 | 100 | 8350 | 2400 | 17400 | 2400 | 2150 | 300 | 700 | 200 | 200 | 200 | 200 | 0 | 0 | 0 | 0
Third Party Wayleaves |  | 20000 |  |  |  | Month 1: 10000; Month 2: 5000; Month 3: 2500; Option signed 4: 2500
Satisfaction of pre-commencement planning conditions |  | 15000 |  |  |  | App. Submitted 9: 5000; App. Submitted 10: 5000; App. Submitted 11: 5000
Transaction Cost |  | 15000 |  |  |  | App. Submitted 12: 5000; App. Submitted 13: 5000; App. Submitted 14: 5000
Total |  | 264227.4 | 38401.4 | 15500 | 11600 | 152350 | 31400 | 193900 | 28900 | 23650 | 3300 | 7700 | 2200 | 7200 | 7200 | 7200 | 5000 | 5000 | 5000 | 0
Installed capacity | 43
Total/MW |  | 6144.8233
Total/MW |  |  | 893.0558 |  | #DIV/0!

## Kinmuck
EIA Screening submitted
Kinmuck Budget Cost | [13 empty] | Option signed |  |  |  |  | Public Cons | [5 empty] | Public Cons 26th July |  | Submission 7th Sept | [9 empty] | Decision
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31
Grid | Application | 33540 | 17534.95 | 27950 | 17534.95 | SSEN | 2022-01-31: 27950; 2023-08-31: 1342; 2023-12-31: -11757.05
| Consultant | 20000 | 29522.69 |  | 29522.69 | Omnia | 2022-11-30: 2177.46; 2022-12-31: 6489.92; 2023-01-31: 5638.73; 2023-02-28: 331.69; 2023-05-31: 1748; 2023-06-30: 3131.51; 2023-07-31: 2673; 2023-08-31: 2905.21; 2023-11-30: 120.97; 2023-12-31: 120.97; 2024-01-31: 241.94; 2024-03-31: 483.88; 2024-04-30: 1548.25; 2024-05-31: 1911.16
| Deposit/security | 603845.7 | 603845.7 | 603846 | 603845.7 |  | 2022-03-31: 77310; 2022-09-30: 31778.7; 2023-05-31: 122251; 2023-10-31: 77310; 2024-05-31: 295196
| Third Party Wayleaves | 0 | 0 | 0 | 0
| Soil Resistivity |  |  | 3471 |  | ERM | 2023-09-30: 3471
Lease/Option | Lease/Option | 34000 | 42322.3 |  | 42322.3 |  | 2022-02-28: 4590; 2022-06-30: 4080; 2022-09-30: 7240; 2022-10-31: 7500; 2022-12-31: 7500; 2023-01-31: 1412.3; 2024-04-30: 10000
Legal/Cooperation | Legal/Coorporate | 3000 | 2610 |  | 2610 |  | 2022-01-31: 1000; 2023-11-30: 1610
Planning Application Fee | Planning Application Fee | 105000 | 105000 | 100000 | 100000 |  | 2023-07-31: 100000; 2024-09-30: 5000
Planning Consultant | Planning Consultant | 40000 | 46895.9 | 37810 | 46895.9 | David Bell | 2022-01-31: 1539.1; 2022-10-31: 2380; 2022-12-31: 2660; 2023-01-31: 3796.8; 2023-05-31: 3760; 2023-07-31: 4580; 2023-08-31: 8720; 2023-09-30: 8490; 2023-11-30: 1440; 2023-12-31: 2880; 2024-01-31: 1460; 2024-02-29: 530; 2024-03-31: 1500; 2024-04-30: 1500; 2024-05-31: 970; 2024-06-30: 690
Planning Studies | Heritage Statement | 8000 | 6705 | 4175 | 4705 | CFA Archaeology | 2023-01-31: 1925; 2023-08-31: 200; 2023-10-31: 580; 2023-11-30: 2000; 2024-08-31: 2000
| ALC Classification | 3000 | 3685 | 2640 | 3685 | Pell Frischmann | 2022-10-31: 2640; 2023-07-31: 1045
| Topographical Study | 4000 | 3965 | 1450 | 3965 | Cain Tech | 2022-10-31: 3965
| Flood Risk Assessment | 8000 | 11369 | 5240 | 11369 | ITP Energised | 2022-01-31: 1159; 2023-04-30: 2060; 2023-05-31: 2250; 2023-12-31: 900; 2024-06-30: 5000
| Geophysical Survey/Earth works | 5000 |  |  | 15250 | Gondolin | 2023-04-30: 1250; 2023-06-30: 14000
| Geo-Environmental Phase I | 6000 | 5242.5 | 2250 | 5242.5 | ITP Energised | 2022-01-31: 2137.5; 2022-05-31: 3105
| Trial Trenching | 30000 | 30000 |  | 0 | N/A | 2024-10-31: 30000
| Arboricutural Survey | 6000 | 4000 |  | 2000 | N/A | 2023-07-31: 2000; 2024-08-31: 2000
| Highways Survey | 11000 | 14025 | 6245 | 9025 | Pell Frischmann | 2022-10-31: 550; 2023-01-31: 750; 2023-05-31: 3500; 2023-07-31: 3000; 2023-08-31: 475; 2023-12-31: 750; 2024-08-31: 5000
| Ecological Survey | 22000 | 19975.5 | 10560 | 14975.5 | ITP Energised | 2022-01-31: 2036.5; 2022-08-31: 4418; 2022-09-30: 2186; 2022-10-31: 1100; 2023-06-30: 3520; 2023-08-31: 1715; 2024-08-31: 5000
| CEMP |  | 10850 | 5425 | 10850 | ITP Energised | 2023-07-31: 5425; 2023-08-31: 5425
| LVIA | 15000 | 13787.87 | 5068.15 | 8787.87 | Peter Dunmow | 2023-07-31: 4738.77; 2023-08-31: 3599.1; 2023-12-31: 450; 2024-08-31: 5000
| CTMP | 3000 | 8769.5 |  | 8769.5 | Pell Frischmann | 2023-07-31: 1000; 2023-12-31: 7769.5
| Noise | 8000 | 6250 | 3850 | 6250 | ITP Energised | 2023-04-30: 3750; 2023-05-31: 500; 2024-06-30: 2000
| 3D model photomontage | 0 | 0 | N/A | 0 | N/A
| Air Quality | 0 | 5950 | 4700 | 5950 | Tetra Tech | 2023-05-31: 4700; 2023-06-30: 1250
| PR | 50000 |  | 13080 | 40966.15 | Kane Partnership | 2023-01-31: 7006; 2023-02-28: 4000; 2023-06-30: 2880; 2023-08-31: 10298.26; 2023-11-30: 2074; 2023-12-31: 9907.89; 2024-02-29: 3200; 2024-03-31: 1600
| Battery Safety Management Plan |  |  | 2841.25 | 1920.4 | Lanpro | 2023-08-31: 973.5; 2023-10-31: 463.65; 2023-11-30: 483.25
| Socio Economics |  |  | 2982.5 | 946.85 | Lanpro | 2023-10-31: 483.25; 2023-11-30: 463.6
| EIA | 14000 | 0 |  | 0
Contingency | 10% of planning costs | 16414.5 | 3000 | 20831.69 | N/A |  | 687.21 | 0 | 0 | 0 | 310.5 | 0 | 0 | 441.8 | 218.6 | 1063.5 | 0 | 266 | 1347.78 | 400 | 1471 | 2165 | 2178.877 | 3140.586 | 849 | 152.69 | 646.085 | 2265.739 | 146 | 373 | 310 | 150 | 97 | 769 | 0 | 1900 | 0 | 3000 | 0 | 0 | 0 | 0
Third Party Wayleaves |  | 15000 | 15000 |  | 15000 |  | 2024-04-30: 15000
Satisfaction of pre-commencement planning conditions |  | 0 | 0 |  | 0
Transaction Cost |  | 15000 | 15000 |  | 15000 |  | 2023-12-31: 5000; 2024-01-31: 5000; 2024-02-29: 5000
Total |  | 1023936.3 | 1025305.91 | 864415.59 | 1027389.31 |  | 36509.31 | 4590 | 77310 | 0 | 3415.5 | 4080 | 0 | 4859.8 | 41423.3 | 19198.5 | 2177.46 | 16915.92 | 21876.61 | 4731.69 | 1471 | 9225 | 140887.877 | 27922.096 | 125310.77 | 35805.76 | 12607.085 | 81102.639 | 8337.82 | 16394.31 | 7011.94 | 8880 | 3680.88 | 28817.25 | 298077.16 | 9590 | 0 | 22000 | 5000 | 30000 | 0 | 0
Installed capacity/MW | 105
Total/MW |  | 9751.7743 | 9764.8182
Note on AB5: Lesley Giles: EZQ273
Note on AF5: Sam Aitchison: Credit Note on variable App fee - 80295216
Note on AE6: Lesley Giles: INV-231-081
Note on AF6: Lesley Giles: INV-2311-040
Note on AG6: Lesley Giles: INV-2401-138
Note on AI6: Lesley Giles: INV-2402-192
Note on AJ6: Lesley Giles: INV-2403-168
Note on AK6: Lesley Giles: INV-13000187
Note on T10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ricard Gibbs land agent fee
Note on U10: Lesley Giles: Centremaps
Note on I11: Lesley Giles: Blick Rothernberg
Note on AE11: Lesley Giles: Pinsent Masons 6785919
Note on F13: Lesley Giles: Original Quote £31,810 £6000 increase agreed 17/08/2023 due to delays caused by SSEN changing the substation design
Note on AE13: Lesley Giles: 164/10
Note on AF13: Lesley Giles: 164/12
Note on AG13: Lesley Giles: 164/13
Note on AH13: Lesley Giles: 164/14
Note on AK13: Lesley Giles: 164/16
Note on AL13: Lesley Giles: 164/17
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £2250 for Geo-environmental phase 1 assessment £1,925 Heritage DBA
Note on AB14: Lesley Giles: consultation cost
Note on AB22: Lesley Giles: £475 completion of transport statement
Note on Z23: Lesley Giles: SPP & BEP
Note on AF25: Lesley Giles: 1252
Note on AF30: Lesley Giles: 1048 1044 1043
Note on AH30: Lesley Giles: 1057
Note on AI30: Lesley Giles: 1208

## Welby
Welby Budget Cost | [19 empty] | PRE-APP | [12 empty] | Submitted |  | DECISION
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Variance on quote (remaining spend) | Variance on Budget to Quote | PO Raised? | Consultant | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01
Grid | DNO Application | 13529 | 13529 | 13529 | 13529 | 0 | 0 | Item fully billed |  | 2022-07-01: 5279; 2022-12-01: 6250; 2023-07-01: 2000
| Consultant | 0 | 0 | 8500 | 0 | 8500 | -8500 |  |  | 2024-07-01: 8500
| Deposit/security | 20000 | 20000 | 20000 | 20000 | 0 | 0 | Item fully billed |  | 2022-09-01: 20000
Grid Subtotal |  | 33529 | 33529 | 42029 | 33529 | 8500 | -8500 |  |  | 5279 | 0 | 20000 | 0 | 0 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0
Lease/Option |  |  | 0 |  | 0 | 0 | 0 | N/A
Legal/Coorporate |  | 14400 | 13202 | 13202 | 13202 | 0 | 0 | Item fully billed |  | 2023-02-01: 13202
Property Searches |  | 1491 | 1491 | 1491 | 1491 | 0 | 0 | Item fully billed |  | 2023-04-01: 1491
Utilities Searches |  | 2838 | 2838 | 2838 | 2838 | 0 | 0 | Item fully billed |  | 2023-05-01: 2838
Third Party Wayleaves |  | 50000 | 72000 | 125000 | 800 |  | -53000 |  |  | 2023-06-01: 800
Land Subtotal |  | 68729 | 89531 | 142531 | 18331 | 0 | -53000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13202 | 0 | 1491 | 2838 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning Consultant PM |  | 21150 | 21150 | 21150 | 21149.08 | 0.92 | 0 | Yes | Arcadis | 2023-06-01: 2179.45; 2023-07-01: 3057.75; 2023-08-01: 1087.05; 2023-09-01: 935; 2023-10-01: 681.75; 2023-11-01: 2614; 2023-12-01: 574.93; 2024-01-01: 2034.77; 2024-02-01: 1376.68; 2024-03-01: 3448; 2024-04-01: 1508; 2024-06-01: 1651.7
Planning Application Fee and Design PAD |  | 150000 | 250000 | 292697 | 292648.17 | 48.83 | -42697 | Item fully billed | South Kesteven DC | 2023-08-01: 1504.17; 2024-06-01: 291144
Desktop | Entrust Report | 1296 | 1296 | 1296 | 1296 | 0 | 0 | Item fully billed | Entrust | 2023-01-01: 1115; 2023-02-01: 181
Pre-app | Pre-application support/meetings /app forms/planning statement/sustainability statement | 16650 | 16650 | 16992.01 | 16992.01 | -3.638e-12 | -342.01 | Yes | Arcadis | 2023-06-01: 3225.81; 2023-07-01: 2990.13; 2023-08-01: 1530.7; 2023-09-01: 1179.5; 2023-10-01: 840.75; 2023-11-01: 796.45; 2023-12-01: 1372; 2024-01-01: 992.75; 2024-02-01: 1025.38; 2024-03-01: 1496; 2024-04-01: 312.54; 2024-06-01: 1230
| Kick off meeting | 4500 | 4500 | 4500 | 4499.5 | 0.5 | 0 | Item fully billed | Arcadis | 2023-06-01: 760.5; 2023-07-01: 3739
EIA | EIA Screening | 5500 | 5500 | 5500.01 | 5500.01 | 9.0949e-13 | -0.01 | Item fully billed | Arcadis | 2023-06-01: 863.63; 2023-07-01: 624.76; 2023-08-01: 234; 2023-09-01: 2500; 2023-10-01: 1277.62; 2023-11-01: 0; 2023-12-01: 142; 2024-01-01: -142; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0
| Arcadis contingency - by IGP approval only | 20000 | 20000 | 2471.25 | 2471.25 | 0 | 17528.75 | No | Arcadis | 2023-10-01: 2040; 2023-11-01: 431.25
Planning | LVIA/Mitigation Plan | 34275 | 34275 | 36891.42 | 36891.42 | 0 | -2616.42 | Yes | Arcadis | 2023-06-01: 4681.13; 2023-07-01: 5564.29; 2023-08-01: 3540; 2023-09-01: 5264.13; 2023-10-01: 2488.03; 2023-11-01: 1785.85; 2023-12-01: 972; 2024-01-01: 5155; 2024-02-01: 1173.63; 2024-03-01: 1806.25; 2024-04-01: 2524.3; 2024-06-01: 1936.81
| Public consultation / SCI | 18450 | 18450 | 20454.75 | 20454.75 | 3.638e-12 | -2004.75 | Yes | Arcadis | 2023-06-01: 452; 2023-07-01: 339; 2023-08-01: 678; 2023-09-01: 565; 2023-10-01: 678; 2023-11-01: 1551.95; 2023-12-01: 956.9; 2024-01-01: 2884.55; 2024-02-01: 344.8; 2024-03-01: 5168; 2024-04-01: 3082; 2024-06-01: 3754.55
| Monitor application, advise, respond to objections, liaise with LPA, negotiate planning | 6900 | 6900 | 6900 | 0 | 6900 | 0 | Item fully billed | Arcadis
| Tree Survey and AIA | 7500 | 7500 | 7689.01 | 7689.01 | 0 | -189.01 | Yes | Arcadis | 2023-06-01: 311.5; 2023-07-01: 1775; 2023-08-01: 2437.42; 2023-09-01: 445; 2023-10-01: 0; 2023-11-01: 182.88; 2023-12-01: 993.38; 2024-01-01: 1317.75; 2024-02-01: 0; 2024-03-01: 77.08; 2024-04-01: 0; 2024-06-01: 149
| Heritage DBA and Heritage Statement | 16500 | 20020 | 26689.75 | 26688.88 | 0.87 | -6669.75 | Yes | Arcadis | 2023-06-01: 2373.25; 2023-07-01: 626.25; 2023-08-01: 1602; 2023-09-01: 3480; 2023-10-01: 1446.25; 2023-11-01: 5471.38; 2023-12-01: 1500; 2024-01-01: 3520; 2024-03-01: 6669.75; 2024-04-01: 0
| Heritage Evaluation and Mitigation Planning | 0 | 17670 | 17670 | 17670 | 0 | 0 | Yes | Arcadis | 2024-02-01: 17670
| Geophysical Survey | 30000 | 30000 | 42000 | 41990 | 10 | -12000 | Item fully billed | Wessex Archaeology | 2023-06-01: 6300; 2023-08-01: 17200; 2023-11-01: 18490
| Topographical Survey | 25000 | 25885 | 25885 | 25885 | 0 | 0 | Item fully billed | Midland Surveys | 2023-06-01: 19992; 2023-07-01: 4998; 2023-08-01: 895
| Ecological Surveys and Reports | 36000 | 37855 | 44690 | 37802 | 6888 | -6835 | Yes | Clarkson and Woods | 2023-06-01: 22600; 2023-08-01: 2100; 2024-03-01: 3270; 2024-05-01: 6005; 2024-06-01: 3827
| Transport Desktop | 6360 | 6360 | 12260.01 | 12260.01 | 0 | -5900.01 | Yes | Arcadis | 2023-06-01: 1397.62; 2023-07-01: 1193.75; 2023-08-01: 181.25; 2023-10-01: 0; 2023-11-01: 716.25; 2023-12-01: 666.58; 2024-01-01: 396.5; 2024-02-01: 3330.98; 2024-03-01: 2325.35; 2024-04-01: 483; 2024-06-01: 1568.73
| CTMP and routing plans | 3300 | 3300 | 3300 | 0 | 3300 | 0 | Yes | Arcadis
| FRA and Drainage | 7000 | 7000 | 7000 | 6999.51 | 0.49 | 0 | Yes | Arcadis | 2023-06-01: 4122.12; 2023-07-01: 1259.75; 2023-08-01: 466.13; 2023-09-01: 423; 2023-10-01: 0; 2023-11-01: 0; 2023-12-01: 462; 2024-01-01: 266.5; 2024-02-01: 0; 2024-04-01: 0; 2024-06-01: 0.01
| Glint and Glare | 6500 | 6594 | 8582.75 | 8582.75 | 0 | -1988.75 | Item fully billed | Pager Power | 2023-06-01: 6594; 2023-08-01: 993.75; 2024-02-01: 995
| Noise impact assessment | 11950 | 11950 | 12341.92 | 12341.92 | 1.819e-12 | -391.92 | Yes | Arcadis | 2023-06-01: 799.7; 2023-07-01: 1799.98; 2023-08-01: 1295; 2023-10-01: 2426.9; 2023-11-01: 391.88; 2023-12-01: 0; 2024-01-01: 574.75; 2024-02-01: 549.08; 2024-03-01: 2113.63; 2024-04-01: 928.13; 2024-06-01: 1462.87
| Agricultural Land Survey | 5500 | 5500 | 5329.08 | 5329.08 | 0 | 170.92 | Item fully billed | Amet Property | 2023-08-01: 5329.08
| Trial trenching | 50000 | 120000 | 176773.6 | 84485.3 | 92288.3 | -56773.6 | Yes | Wessex Archaeology | 2024-02-01: 500; 2024-03-01: 83985.3
| Outline CEMP and Minerals Assessment | 6000 | 13800 | 13800 | 13800 | 0 | 0 | Yes | Arcadis | 2023-06-01: 1256; 2023-08-01: -962.5; 2023-10-01: 0; 2023-11-01: 712; 2023-12-01: 445; 2024-01-01: 5394; 2024-02-01: 755.95; 2024-03-01: 3458; 2024-04-01: 1641.42; 2024-06-01: 1100.13
| GIS systems | 8460 | 8460 | 8460.01 | 8460.01 | 0 | -0.01 | Yes | Arcadis | 2023-06-01: 934.5; 2023-07-01: 356; 2023-08-01: 351.8; 2023-09-01: 30.93; 2023-10-01: 0; 2023-11-01: 0; 2023-12-01: 0; 2024-03-01: 3164.78; 2024-04-01: 1767.5; 2024-06-01: 1854.5
| Website & Consultation Letters | 2400 | 3151.55 | 2001.86 | 2001.86 | 0 | 1149.69 | Yes | Thirty47 | 2023-12-01: 400; 2024-01-01: 1301.86; 2024-02-01: 300
| Cable Route Feasibility | 0 | 0 | 271.15 | 271.15 | 0 | -271.15 | Item fully billed | JSM | 2024-01-01: 271.15
| Cable Route Agreement Support | 20000 | 20000 | 7000 | 0 | 7000 | 13000 | Yes | Dalcour Maclaren
Post Submission | Planning support | 0 | 0 | 15000 | 0 | 15000 | -15000 | No | TBC
| GCN DLL | 0 | 0 | 19705.2 |  |  | -19705.2 | No | Natural England
Contingency | 10% of planning costs | 50004.1 | 50000 | 0 | 0 | 0 | 50000
Planning Total |  | 521191 | 773766.55 | 865301.78 | 714158.67 | 131437.91 | -91535.23 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1115 | 181 | 0 | 0 | 0 | 78843.21 | 28323.66 | 40462.85 | 14822.56 | 11879.3 | 33143.89 | 8484.79 | 23967.58 | 28021.5 | 116982.14 | 12246.89 | 6005 | 309679.3 | 0 | 0 | 0 | 0 | 0 | 0
Development Total |  | 673453.1 | 896826.55 | 1049861.78 | 766018.67 | 139937.91 | -153035.23
Satisfaction of pre-commencement planning conditions |  | 15000 | 15000 | 15000 | 0 | 0 | 0
Transaction Cost | to date (admin, accounts etc) | 15000 | 15000 | 15000 | 0 | 0 | 0
Total |  | 703453.1 | 926826.55 | 1079861.78 | 766018.67 | 139937.91 | -153035.23 |  |  | 5279 | 0 | 20000 | 0 | 0 | 6250 | 1115 | 13383 | 0 | 1491 | 2838 | 79643.21 | 30323.66 | 40462.85 | 14822.56 | 11879.3 | 33143.89 | 8484.79 | 23967.58 | 28021.5 | 116982.14 | 12246.89 | 6005 | 309679.3 | 8500 | 0 | 0 | 0 | 0 | 0
Installed capacity | 58
Total/MW |  | 12128.5017 | 15979.7681 | 18618.3066 | 13207.2184
168970.6
Estimate
Actual Cable Route agreement | 92643 |  |  |  | Trial trenching second stage
| 32357 |  |  |  | 92288.3 | 31737.7
60550.6
Note on S9: Natasha Worrall: Feb 23 Deal sheet: £1,200 accounting & admin £13,200 legal fees
Note on F12: Sam Aitchison: PO000396 -Forsters LLP - Cable Route Legals - £23,000 (1 of 3 agreements)
Note on W12: Natasha Worrall: Survey Licenses Holden A1382 Holden 01
Note on W14: Natasha Worrall: 680018394
Note on AA14: Natasha Worrall: 680029334
Note on AB14: Natasha Worrall: 680031831
Note on AC14: Sam Aitchison: 680031831
Note on AD14: Natasha Worrall: 680036521
Note on AE14: Sam Aitchison: Inovice: 680039159
Note on AF14: Natasha Worrall: 680042015
Note on AG14: Sam Aitchison: Invoice 680044281
Note on Y15: Sam Aitchison: Paid on SA Pleo.
Note on F17: Sam Aitchison: Original + CO5 (part)
Note on W17: Natasha Worrall: 680018394
Note on AA17: Natasha Worrall: 680029334
Note on AB17: Natasha Worrall: 680031831
Note on AC17: Sam Aitchison: 680031831
Note on AD17: Natasha Worrall: 680036521
Note on AE17: Sam Aitchison: Inovice: 680039159
Note on AF17: Natasha Worrall: 680042015
Note on AG17: Sam Aitchison: Invoice 680044281
Note on AA19: Natasha Worrall: 680029334
Note on AB19: Natasha Worrall: 680031831
Note on AC19: Sam Aitchison: 680031831 Booked in Error to be credited next month
Note on AD19: Natasha Worrall: 680036521
Note on AE19: Sam Aitchison: Inovice: 680039159
Note on AF19: Natasha Worrall: 680042015
Note on AG19: Sam Aitchison: Invoice 680044281
Note on AB20: Natasha Worrall: Belton Woods Hotel booking for consultation - 5 rooms booked (inc 3 x IGP, 2x Arcadis)
Note on F21: Sam Aitchison: Original+CO4-£142 variace (transferred to SCI) +CO5(part)
Note on W21: Natasha Worrall: 680018394
Note on AA21: Natasha Worrall: 680029334
Note on AB21: Natasha Worrall: 680031831
Note on AC21: Sam Aitchison: 680031831
Note on AD21: Natasha Worrall: 680036521
Note on AE21: Sam Aitchison: Inovice: 680039159
Note on AF21: Natasha Worrall: 680042015
Note on AG21: Sam Aitchison: Invoice 680044281
Note on F22: Sam Aitchison: Original Quote + CO1 + £142 from LVIA - £177.25
Note on W22: Natasha Worrall: 680018394
Note on AA22: Natasha Worrall: 680029334
Note on AB22: Natasha Worrall: 680031831
Note on AC22: Sam Aitchison: 680031831
Note on AD22: Natasha Worrall: 680036521
Note on AE22: Sam Aitchison: Inovice: 680039159
Note on AF22: Natasha Worrall: 680042015
Note on AG22: Sam Aitchison: Invoice 680044281
Note on F24: Sam Aitchison: Original + CO5 part
Note on W24: Natasha Worrall: 680018394
Note on AA24: Natasha Worrall: 680029334
Note on AB24: Natasha Worrall: 680031831
Note on AC24: Sam Aitchison: 680031831
Note on AD24: Natasha Worrall: 680036521
Note on AF24: Natasha Worrall: 680042015
Note on AG24: Sam Aitchison: Invoice 680044281
Note on F25: Sam Aitchison: Original+CO3A+CO3D
Note on W25: Natasha Worrall: 680018394
Note on AA25: Natasha Worrall: 680029334
Note on AB25: Natasha Worrall: 680031831
Note on AC25: Sam Aitchison: 680031831
Note on AD25: Natasha Worrall: 680036521
Note on AE25: Sam Aitchison: Inovice: 680039159
Note on AF25: Natasha Worrall: 680042015
Note on AG25: Sam Aitchison: Invoice 680044281
Note on F26: Sam Aitchison: Change Order 3B
Note on AE26: Sam Aitchison: Inovice: 680039159
Note on W27: Natasha Worrall: 040641 First part of geophys survey and report
Note on Y27: Natasha Worrall: INV041194
Note on AB27: Natasha Worrall: INV041704
Note on W28: Natasha Worrall: 35418
Note on X28: Natasha Worrall: 35824
Note on Y28: Natasha Worrall: 35825
Note on F29: Sam Aitchison: 8212+8414+8771+8743+82123-ES Chapter
Note on G29: Sam Aitchison: £5,180 saving from quote based on lineitems
Note on W29: Natasha Worrall: 82121
Note on Y29: Sam Aitchison: 8414
Note on AF29: Sam Aitchison: 82123 PO000385
Note on AH29: Sam Aitchison: 8771+87431 PO000565+PO000616
Note on AI29: Sam Aitchison: 8212 PO000840
Note on F30: Sam Aitchison: Appriasal+Access Drawings+CTMP
Note on W30: Natasha Worrall: 680018394
Note on AA30: Natasha Worrall: 680029334
Note on AB30: Natasha Worrall: 680031831
Note on AC30: Sam Aitchison: 680031831
Note on AD30: Natasha Worrall: 680036521
Note on AE30: Sam Aitchison: Inovice: 680039159
Note on AF30: Natasha Worrall: 680042015
Note on AG30: Sam Aitchison: Invoice 680044281
Note on W32: Natasha Worrall: 680018394
Note on AB32: Natasha Worrall: 680031831
Note on AC32: Sam Aitchison: 680031831
Note on AD32: Natasha Worrall: 680036521
Note on AG32: Sam Aitchison: Invoice 680044281
Note on W33: Natasha Worrall: Upfront payment agreed due to Welby SPV age
Note on Y33: Natasha Worrall: 709309 Additional cost for resting angle assessment
Note on AE33: Natasha Worrall: Remodel to remove central field 709643
Note on F34: Sam Aitchison: Original + CO5 (Part)
Note on W34: Natasha Worrall:
Note on AA34: Natasha Worrall: 680029334
Note on AB34: Natasha Worrall: 680031831
Note on AC34: Sam Aitchison: 680031831
Note on AD34: Natasha Worrall: 680036521
Note on AE34: Sam Aitchison: Inovice: 680039159
Note on AF34: Natasha Worrall: 680042015
Note on AG34: Sam Aitchison: Invoice 680044281
Note on Y35: Sam Aitchison: INV-1241
Note on F36: Sam Aitchison: Original plus one set of mobilisation costs Potential for increase
Note on AE36: Sam Aitchison: INV041803 (WSI)
Note on AF36: Natasha Worrall: INV042080
Note on F37: Sam Aitchison: oCEMP - Original Quote Mineral Assessemnt - CO2
Note on W37: Natasha Worrall: 680018394
Note on Y37: Natasha Worrall: Arcadis confirmed time erronously booked to code so corrected.
Note on AA37: Natasha Worrall: 680029334
Note on AB37: Natasha Worrall: 680031831
Note on AC37: Sam Aitchison: 680031831
Note on AD37: Natasha Worrall: 680036521
Note on AE37: Sam Aitchison: Inovice: 680039159
Note on AF37: Natasha Worrall: 680042015
Note on AG37: Sam Aitchison: Invoice 680044281
Note on W38: Natasha Worrall: 680018394
Note on AA38: Natasha Worrall: 680029334
Note on AB38: Natasha Worrall: 680031831
Note on AC38: Sam Aitchison: 680031831
Note on AF38: Natasha Worrall: 680042015
Note on AG38: Sam Aitchison: Invoice 680044281
Note on AC39: Natasha Worrall: 1538
Note on AE39: Natasha Worrall: 1595
Note on AD40: Natasha Worrall: SI403958
Note on C57: Sam Aitchison: PO000396 -Forsters LLP - Cable Route Legals - £23,000 (1 of 3 agreements)

## Carlton
Carlton Budget Cost | [25 empty] | EIA S&S |  |  |  |  | Submission | [8 empty] | Decision
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | time axis 2021-01-31 to 2024-06-01
Grid | DNO Application | 7880 | 7880 |  | 7880 |  | 2021-01-31: 7880
| Consultant | 750 | 750 |  | 750 |  | 2021-01-31: 750
| Deposit/security | 50000 | 50000 |  | 50000 |  | 2021-01-31: 50000
Lease/Option |  | 175146.91 | 266509.82 |  | 266509.82 |  | 2021-01-31: 5100; 2021-07-31: 29955.9; 2021-08-31: 10069.08; 2021-11-30: 168268.07; 2022-01-31: 53116.77
Legal/Coorporate |  | 4906 | 0 |  | 0
Planning Consultant |  | 45194 | 49239 |  | 54239 | Graham - Lanpro |  |  |  | 940.5 | 244 | 509.5 | 3410 | 1341.75 | 3206.25 | 1437.25 | 520.7 | 150 | 700 | 564 | 348 |  | 432 |  | 612 | 3257 | 5000 | 2414.69 | 3117.65 | 12283.21 | 5250 | 750 | [5 empty] | 1250 |  | 500 | 1000 |  | 1000 | 1000 | 1000 | 1250
Planning Application Fee |  | 172715 | 246451 |  | 246451 | SELBY | 2023-01-31: 207811; 2023-02-28: 38640
Planning Studies | Heritage Statement & WSI | 2600 | 8195.05 |  | 8195.05 | Lanpro | 2022-07-31: 4805; 2023-06-30: 1690.05; 2023-11-30: 1700
| ALC Classification | 5000 | 6850 |  | 6850 | Land Research Associates | 2021-10-31: 5100; 2021-11-30: 950; 2022-12-31: 800
| Topographical Study | 13600 | 17693.75 |  | 17693.75 |  | 2021-07-31: 13600; 2022-03-31: 1750; 2023-06-30: 2343.75; 2024-04-01: 840
| Flood Risk Assessment | 2250 | 2450 |  | 2450 | Delta Simons | 2021-09-30: 1500; 2021-11-30: 950
| Geophysical Survey | 27755 | 41049.48 |  | 41049.48 |  | 2021-08-31: 27755; 2022-07-31: 13294.48
| Trial Trenching | 50000 | 0 |  | 0
| Coal mining risk report |  | 2500 |  | 2500 | Integrale | 2022-02-28: 2500
| Arboricutural Survey (+conditions) | 3000 | 7558.2 |  | 7558.2 | Lanpro | 2021-12-31: 1225; 2022-02-28: 5333.2; 2022-08-31: 500; 2022-09-30: 500; 2024-03-01: 1250
| Highways Survey | 3200 | 0 |  | 0 |  | 2024-01-01: 950
| Ecological Survey | 38540 | 29185 |  | 29185 | Aspect | 2021-08-31: 8220; 2021-12-31: 8320; 2022-01-31: 1740; 2022-11-30: 2730; 2022-12-31: 2650; 2023-09-30: 445; 2023-10-31: 4120; 2023-12-31: 960
| LVIA | 15810 | 25559 | 24447 | 24334.25 | Liz Lake | 2021-10-31: 3315.5; 2022-08-31: 1870; 2023-01-31: 10650; 2023-02-28: 8223.75; 2023-08-31: 275; 2024-02-01: 4250; 2024-03-01: 9750
| CTMP | 3000 | 450 |  | 450 | TPA | 2022-11-30: 450
| Noise | 2900 | 3400 |  | 3400 | Tetra Tech | 2022-05-31: 2450; 2023-11-30: 950
| 3D model | 15000 | 321.75 |  | 321.75 |  | 2022-12-31: 321.75
| Glint/Glare | 2821 | 5221 | 1243 | 5221 | Pager Power | 2022-08-31: 1243; 2022-09-30: 3978
| EIA |  | 0 |  | 0
| Network Rail | 57057.13 | 13349.58 | 1500 | 13349.58 |  | 2022-05-31: 8849.58; 2022-10-31: 1500; 2023-05-31: 1500; 2023-11-30: 1500; 2024-06-01: 2202.19
| Planning Performance Agreement |  | 0 |  | 0
| Cable Route Engineering & Trial Holes |  |  |  | 6690.57 | JSM | 2023-07-31: 1322; 2023-09-30: 5368.57
| UTX |  | 50684 |  | 33259 |  | 2023-11-30: 15834; 2023-12-31: 17425; 2024-01-01: 5000; 2024-02-01: 9318.75; 2024-06-01: 3106.25
| Landscape DOC | 300 | 300 |  | 300 |  | 2024-06-01: 300
| BMP DOC | 525 |  |  |  |  | 2024-06-01: 525
| Landowner VAT payment |  |  |  | 841.41 |  | 2024-06-01: 841.41
| Data Room | 1994 | 1994 |  | 0 | Ansarada
| Desktop Report Revision |  | 500 |  |  |  | 2024-02-01: 500
Contingency | 10% of planning costs |  | 0 |  | N/A |  | 0 | 0 | 0 | 94.05 | 24.4 | 50.95 | 1701 | 3731.675 | 470.625 | 985.275 | 242.07 | 969.5 | 244 | 839.72 | 209.8 | 0 | 1173.158 | 0 | 1871.148 | 687 | 947.8 | 391.469 | 629.765 | 1605.496 | 22371.1 | 4761.375 | 0 | 0 | 150 | 403.38 | 0 | 152.5 | 44.5 | 462 | 515 | 96
Third Party Wayleaves |  |  | 21981.06 |  | 21981.06 |  | 2021-11-30: 21981.06
Satisfaction of pre-commencement planning conditions |  | 31950 | 31950 |  | 31950
Transaction Cost | to date (admin, accounts etc) |  | 0 |  | 0
Total |  | 733894.04 | 892021.69 | 27190 | 883409.92 |  | 63730 | 0 | 0 | 1034.55 | 268.4 | 560.45 | 48666.9 | 51117.505 | 5176.875 | 10838.025 | 192911.9 | 10664.5 | 55800.77 | 9236.92 | 2307.8 | 0 | 12904.738 | 0 | 20582.628 | 7557 | 10425.8 | 4306.159 | 6927.415 | 17660.456 | 246082.1 | 52375.125 | 0 | 0 | 1650 | 4437.18 | 1322 | 1677.5 | 5858.07 | 5082 | 21499 | 18481
Installed capacity | 65
Total/MW |  | 11290.6775 | 13723.4106 | 418.3077 | 13590.9218
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NR easement Legal and surveyor fees
Note on AN9: Natasha Worrall: 008566
Note on AP9: Natasha Worrall: 008996
Note on AQ9: Natasha Worrall: 008784
Note on AS9: Natasha Worrall: 009949
Note on AT9: Natasha Worrall: 010061 CEMP & PM
Note on AU9: Natasha Worrall: 010382
Note on AV9: Natasha Worrall: 010583
Note on AQ11: Natasha Worrall: 009199
Note on AL13: Lesley Giles: centremaps
Note on AV13: Natasha Worrall: 2414
Note on AU18: Natasha Worrall: 010383 Condition discharge
Note on AS19: Natasha Worrall: 2542
Note on AO20: Natasha Worrall: 410084
Note on AP20: Natasha Worrall: 410117
Note on AR20: Natasha Worrall 410554
Note on AN21: Natasha Worrall: 0021
Note on AT21: Natasha Worrall: 010015
Note on AQ23: Natasha Worrall: 30068507
Note on D27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 57057.13+11411.426VAT. £49806.43 includes VAT for construction BAPA that we are not planning to pay
Note on Y27: James Youngs: £8849.58 + VAT = £10619.50
Note on AD27: James Youngs: Clearance Fee of £1500 + VAT = £1800
Note on AK27: Clearance Payment for new cable crossing route £1500 + VAT = £1800
Note on AQ27: Clearance Payment for increased crossing area of £1500 + VAT = £1800
Note on AX27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PO757
Note on AM29: Natasha Worrall: SI401876
Note on AO29: Natasha Worrall: SI402428
Note on AQ30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6500000496
Note on AR30: Natasha Worrall: 104103
Note on AS30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6500000505B (EPR)
Note on AT30: Natasha Worrall: 650000000505C
Note on AX30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PO 255
Note on AX31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Invoice 010767 (PO: 806)
Note on D32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 630 with VAT
Note on AX32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 630 with VAT (PO684)
Note on AX33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just a payment for missing VAT PO756
Note on AT35: Natasha Worrall: inv-3922

## Tean Leys
Tean Leys Budget Sheet | [15 empty] | Option signed | [16 empty] | Submission
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01
Grid | DNO Application | 15300 | 29888 | 29888 | 29888 | WPD | 2021-10-31: 29888
| Consultant | 14154 | 14154 | 14154 | 14154 |  | 2023-02-28: 14154
| Deposit/security | 50000 | 50000 | 40725.4 | 40393.28 |  | 2023-07-31: 40393.28
Lease/Option |  | 31000 | 31000 | 31000 | 29600 | Roythornes | 2021-11-30: 10000; 2022-09-30: 9600; 2024-04-01: 10000
Legal/Cooperation |  | 500 | 500 | 500 | 500 |  | 2022-01-31: 500
Property Searches |  | 1750 | 1750 | 1750 | bar: 2022-01-31
Planning Application Fee |  | 25000 | 25000 | 25000 | 0 | South Derbyshire
Planning Consultant |  | 23000 | 22200 | 22200 | 7400.75 | Lanpro | 2021-10-31: 510; 2021-11-30: 1000; 2021-12-31: 2388.75; 2022-06-30: 275; 2022-07-31: 727.5; 2022-09-30: 400; 2023-06-30: 400; 2023-07-31: 850; 2023-10-31: 351.5; 2023-11-30: 498
Planning Studies | Planning Constraints Report | 1000 | 1000 | 300 | 1477.5 | Entrust | 2021-10-31: 300; 2023-06-30: 1177.5
| Heritage and Archaeological DBA | 3000 | 3000 | 2950 | 0 | Lanpro
| ALC Classification | 2000 | 2000 | 1500 | 1500 | Land Research Associates | 2023-09-30: 1500
| Topographical Study | 2000 | 2000 | 1250 | 0 | Tower Surveys
| Flood Risk Assessment | 3000 | 0 | 1950 | 0 | Delta Simons
| Geophysical Survey | 7000 | 7000 | 2500 | 0 | Lanpro
| Trial Trenching | 40000 | 40000 | 0 | 0
| Arboricutural Survey | 2500 | 0 | 1995 | 0 | Lanpro
| Highways Survey | 4000 | 4000 | 4650 | 3650 | TPA | 2023-07-31: 3650
| Ecological Survey | 13000 | 13000 | 12285 | 8585 | Clarkson Woods | 2021-10-31: 1325; 2023-07-31: 7260
| LVIA | 14000 | 14000 | 13745 | 2360 | Lanpro | 2022-07-31: 750; 2023-08-31: 1610
| CTMP | 2000 | 2000 | 2000 | 0 | TPA
| Noise | 5500 | 5500 | 5220 | 3290 | Tetra Tech | 2023-09-30: 1645; 2023-10-31: 1645
| Air Quality | 6000 | 5570 | 5570 | 4950 | Tetra Tech | 2023-08-31: 4950
| EIA Screening | 1500 | 1500 | 1500 | 300 | Lanpro | 2021-10-31: 300
| EIA (if required) | 16000 | 0 | 0 | 0 | Lanpro
Contingency | 10% of planning costs | 14550 | 0 | 10461.5 | N/A |  | 243.5 | 100 | 238.875 | 0 | 0 | 0 | 0 | 0 | 27.5 | 147.75 | 0 | 40 | 199.65 | 49.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176 | 656 | 314.5 | 199.65 | 49.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  | 150000 | 140000 |  | 140000 |  | 2023-06-30: 5000; 2023-07-31: 5000; 2023-08-31: 5000; 2023-09-30: 5000; 2023-10-31: 5000; 2023-11-30: 5000; 2023-12-31: 5000; 2024-01-01: 5000; 2024-02-01: 100000
Satisfaction of pre-commencement planning conditions |  | 15000 | 15000 | 15000 | 15000 |  | 2024-02-01: 5000; 2024-03-01: 5000; 2024-04-01: 5000
Transaction Cost |  | 15000 | 15000 | 15000 | 15000 |  | 2024-05-01: 5000; 2024-06-01: 5000; 2024-07-01: 5000
Total |  | 477754 | 445062 | 263093.9 | 318048.53 |  | 32566.5 | 11100 | 2627.625 | 500 | 0 | 0 | 0 | 0 | 302.5 | 1625.25 | 0 | 10040 | 199.65 | 49.8 | 0 | 0 | 14154 | 0 | 0 | 0 | 6577.5 | 58329.28 | 12216 | 8459.5 | 7196.15 | 5547.8 | 5000 | 5000 | 105000 | 5000 | 15000 | 5000 | 5000 | 5000
Installed capacity/MW | 70
Total £/MW |  | 6825.0571 | 6358.0286 | 3758.4843 | 4543.5504
Note on AD6: Natasha Worrall: NGED Costs
Note on AE6: Lesley Giles: 50MW grid payment £1,500,000 20MW grid payment £200,000 both Q3 2023
Note on AG11: Natasha Worrall: 009030
Note on AH11: Natasha Worrall: 009222
Note on I12: Lesley Giles: Entrust planning desktop Cost 2021
Note on AC12: Lesley Giles: Centremaps
Note on AF14: Natasha Worrall: INV-2308-131
Note on AD20: Natasha Worrall: 015386
Note on AD21: Natasha Worrall: 83811 83812
Note on AE22: Natasha Worrall: 008591 Potentially covers some planning costs too
Note on AF24: Natasha Worrall: 30060011
Note on AG24: Natasha Worrall: 30066684
Note on AE25: Natasha Worrall: 784-B048497
Note on I26: Lesley Giles: Entrust planning desktop Cost 2021

## Bonsdale (Ragwhistle)
Ragwhistle Budget Cost | [12 empty] | Option signed | [6 empty] | Planning Submission | [5 empty] | Decision
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2021-09-30 | 2021-10-31 | 2021-11-30 | 2021-12-31 | 2022-01-31 | 2022-02-28 | 2022-03-31 | 2022-04-30 | 2022-05-31 | 2022-06-30 | 2022-07-31 | 2022-08-31 | 2022-09-30 | 2022-10-31 | 2022-11-30 | 2022-12-31 | 2023-01-31 | 2023-02-28 | 2023-03-31 | 2023-04-30 | 2023-05-31 | 2023-06-30 | 2023-07-31 | 2023-08-31 | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31
Grid | DNO Application | 8000 | 7880 |  | 7880 |  | 2022-01-31: 7880
| Consultant | 0 | 0 |  | 0
| Deposit/security | 50000 | 50000 |  | 50000 |  | 2022-01-31: 50000
| Third Party Wayleaves | 25000 | 15000 | 0 | 15000 |  | 2022-05-31: 5000; 2022-06-30: 5000; 2022-07-31: 5000
Lease/Option |  | 31000 | 34027 |  | 34027 | Walker Morris | 2021-11-30: 2015; 2022-04-30: 1012; 2022-05-31: 20000; 2022-06-30: 11000
Legal/Cooperation |  |  | 1184 |  | 1184 |  | 2021-10-31: 684; 2022-01-31: 500
Planning Application Fee |  | 150000 | 150000 |  | 150000 |  | 2022-09-30: 150000
Planning Consultant |  | 32000 | 31785 |  | 31785 | Lanpro | 2021-09-30: 907.5; 2021-10-31: 1531.25; 2022-05-31: 346.25; 2022-06-30: 4000; 2022-07-31: 4000; 2022-08-31: 4000; 2022-09-30: 4000; 2022-10-31: 4000; 2022-11-30: 4000; 2022-12-31: 1000; 2023-01-31: 1000; 2023-02-28: 1000; 2023-03-31: 2000
Planning Studies | Heritage Statement | 5000 | 5000 |  | 5000 | Lanpro | 2022-06-30: 3000; 2022-10-31: 2000
| ALC Classification | 3500 | 6500 | 3000 | 6500 | Land Research Associates | 2021-10-31: 3000; 2022-06-30: 3500
| Topographical Study | 5500 | 10480 | 5000 | 10480 | Sensat | 2021-09-30: 4980; 2022-06-30: 4500; 2022-10-31: 1000
| Flood Risk Assessment | 4000 | 6100 | 6100 | 6100 | Delta Simons | 2021-11-30: 2100; 2022-06-30: 3000; 2022-10-31: 1000
| Geophysical Survey | 17500 | 17500 | 13500 | 17500 |  | 2022-06-30: 17500
| Trial Trenching | 80000 | 60000 |  | 60000 |  | 2023-04-30: 20000; 2023-05-31: 20000; 2023-06-30: 20000
| Arboricutural Survey | 2500 | 2500 |  | 2500 |  | 2022-06-30: 1500; 2022-10-31: 1000
| Highways Survey | 5000 | 5500 |  | 5500 | TPA | 2021-09-30: 500; 2022-06-30: 3000; 2022-10-31: 1000; 2022-12-31: 1000
| Ecological Survey | 26500 | 24180 | 26500 | 24180 | Clarkson Woods | 2021-10-31: 3250; 2021-11-30: 575; 2022-01-31: 1725; 2022-03-31: 3825; 2022-04-30: 575; 2022-05-31: 730; 2022-08-31: 3500; 2022-09-30: 5000; 2022-10-31: 3000; 2022-11-30: 2000
| LVIA | 13500 | 13500 | 13500 | 13500 |  | 2022-06-30: 5000; 2022-07-31: 3000; 2022-08-31: 3000; 2022-10-31: 1500; 2022-12-31: 1000
| CTMP | 2000 | 2000 | 1750 | 2000 |  | 2022-06-30: 1500; 2022-10-31: 500
| Noise | 3000 | 2900 | 3000 | 2900 | TetraTech | 2022-08-31: 2900
| 3D model photomontage | 0 | 0 |  | 0 | 0
| Glint/Glare | 5500 | 5920 | 4500 | 5920 | Pager Power | 2021-12-31: 420; 2022-06-30: 4500; 2022-10-31: 1000
| Communications |  | 1320 |  | 1320 | Humbeat | 2021-12-31: 1320
| Utility Search |  | 1140 |  | 1140 | Centra Maps Live | 2021-10-31: 1140
| EIA | 10000 | 10000 |  | 10000 |  | 2022-06-30: 5000; 2022-07-31: 1000; 2022-08-31: 1000; 2022-09-30: 1000; 2022-10-31: 1000; 2022-11-30: 1000
Contingency | 10% of planning costs | 36550 | 0 | 7685 | N/A |  | 638.75 | 892.125 | 267.5 | 174 | 172.5 | 0 | 382.5 | 57.5 | 107.625 | 5600 | 800 | 1440 | 16000 | 1700 | 700 | 300 | 100 | 100 | 200 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  |  | 15000 |  | 15000 |  | 2022-05-31: 5000; 2022-06-30: 5000; 2022-07-31: 5000
Satisfaction of pre-commencement planning conditions |  | 15000 | 15000 | 15000 | 15000 |  | 2022-11-30: 5000; 2022-12-31: 5000; 2023-01-31: 5000
Transaction Cost |  | 15000 | 15000 | 15000 | 15000 |  | 2023-02-28: 5000; 2023-03-31: 5000; 2023-04-30: 5000
Total |  | 531050 | 509416 | 114535 | 509416 |  | 7026.25 | 10497.375 | 4957.5 | 1914 | 60277.5 | 0 | 4207.5 | 1644.5 | 31183.875 | 82600 | 18800 | 15840 | 176000 | 18700 | 12700 | 8300 | 6100 | 6100 | 7200 | 27000 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0
Installed capacity | 50
Total/MW |  | 10621 | 10188.32 | 2290.7 | 10188.32
Note on F16: Lesley Giles: £2,100 quoted for EIA
Note on F21: David Elvin: Including EIA

## Bodelwyddan
[11 empty] | Grid App | [47 empty] | App. Submitted | [10 empty] | Hearings 15-17th Aug |  | PINS Report | Decision Received 30th
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Variance on quote (remaining spend) | PO Raised? | Consultant | time axis 2021-01-01 to 2026-05-24
Grid | Application | 0 | 60663 | 71912.5 | 60663.33 | 11249.17 |  |  | 2021-03-01: 37000; 2023-12-01: -11249.17; 2024-06-01: 34912.5
| Consultant |  | 1800 | 1800 | 1800 | 0 |  | WSP | 2021-06-01: 1800
| Deposit/security |  | N/A | N/A | 472614.13 |  |  |  | 2022-03-01: 32415.56; 2022-09-01: 7734.85; 2023-03-01: 226312.58; 2023-09-01: 206151.14; 2024-03-01: 0; 2024-09-24: 0; 2025-03-24: 0; 2025-09-24: 0; 2026-03-24: 697419.5094
Lease/Option |  | 0 | 62320 |  | 0
Planning Lawyer |  |  | 55000 | 14500 | 0 |  | PO000999 | Ashfords
Planning Consultant |  |  | 106477.5 |  | 0 |  |  | Stantec
Planning Application Fee |  |  | 60000 |  | 0 | 0 |  | PINS Wales
Planning Studies | Desktop Planning Assessment () |  | 1200 | 1200 | 1200 | 0 | PO000813 | Entrust | 2024-07-24: 1200
| Planning Feasibility Study |  | 6000 |  | 0 | 0 |  | Stantec
EIA | EIA Co-ordination |  | 36200 |  | 0 | 0 |  | Stantec
| ES Climate Change Chapter |  | 8000 |  | 0 | 0 |  | Stantec
Ecology (PO000834) | Phase 1 Habitat Survey |  | 5600 | 5300 | 0 | 5300 | PO000834 | EDP
| Badger survey |  | 2500 | 2500 | 0 | 2500 | PO000834 | EDP
| Breeding bird surveys |  | 8000 | 2800 | 0 | 2800 | PO000834 | EDP
| Wintering bird surveys |  | 16500 | 8500 | 0 | 8500 | PO000834 | EDP
| Bat activity surveys |  | 31000 | 21700 | 0 | 21700 | PO000834 | EDP
| GCN surveys |  | 8450 | 2000 | 0 | 2000 | PO000834 | EDP
| Water vole survey |  | 5000 | 2500 | 0 | 2500 | PO000834 | EDP
| Ecological Baseline Report inc. design |  | 10000 |  | 0 | 0 |  | EDP
| ES Scoping |  | 2500 |  | 0 | 0 |  | EDP
| ES Ecology Chapter |  | 15000 |  | 0 | 0 |  | EDP
| Green Infrastructure Statement |  | 5000 |  | 0 | 0 |  | EDP
| Cumulative Assessment |  | 2000 |  | 0 | 0 |  | EDP
| Phase 1 survey of Cable route - circa 5km |  | 3500 |  | 0 | 0 |  | EDP
| BNG Assessment |  | 4500 |  | 0 | 0 |  | EDP
Landscape and visual | Baseline data collection |  | 10500 |  | 0 | 0 |  | EDP
| LVA Baseline |  | 15000 |  | 0 | 0 |  | EDP
| ES Scoping |  | 1500 |  | 0 | 0 |  | EDP
| Night time LVA |  | 5000 |  | 0 | 0 |  | EDP
| RVAA |  | 5000 |  | 0 | 0 |  | EDP
| ES Landscape Chapter and NTS |  | 15000 |  | 0 | 0 |  | EDP
| LEMP w/ ecology input |  | 6000 |  | 0 | 0 |  | EDP
| Photomontages / verified views |  | 10000 |  | 0 | 0 |  | EDP
| Landscape Strategy |  | 5000 |  | 0 | 0 |  | EDP
Heritage and Archaeology | DBA |  | 8400 |  | 0 | 0 |  | Cotswold
| Geophysical Survey |  | 39690 | 39690 | 0 | 39690 | TBC | AOC
| WSI |  | 950 |  | 0 | 0 |  | Cotswold
| ES Scoping |  | 2450 |  | 0 | 0 |  | Cotswold
| ES Heritage Chapter |  | 9000 |  | 0 | 0 |  | Cotswold
| Trial trenching |  | 425000 |  | 0 | 0 |  | Cotswold - TBC
| Geophys survey of Cable route - circa 5km |  | 3675 |  | 0 | 0 |  | AOC
Flood Risk | Stage 1 |  | 4200 |  | 0 | 0 |  | Calibro
| WFD |  | 5850 |  | 0 | 0 |  | Calibro
| Drainage Strategy and SAB |  | 3000 |  | 0 | 0 |  | Calibro
| Coastal Modelling |  | 18000 |  | 0 | 0 |  | Calibro
| Flood Consequence Assessment |  | 2500 |  | 0 | 0 |  | Calibro
| ES Scoping |  | 1000 |  | 0 | 0 |  | Calibro
| ES Flood Risk Chapter |  | 2500 |  | 0 | 0 |  | Calibro
Agricultural land | ALC survey |  | 6700 | 6700 | 0 | 6700 | PO000998 | LRA
| Soil Management Plan |  | 1500 |  | 0 | 0 |  | Kernon
| Detailed Agricultural Report |  | 3750 |  | 0 | 0 |  | Kernon
Transport | Transport Assessment and CTMP |  | 4750 |  | 0 | 0 |  | Pell Freischmann
| Trafic surveys |  | 1975 |  | 0 | 0 |  | Pell Freischmann
| Abnormal Load Route Survey and TMP |  | 6700 |  | 0 | 0 |  | Pell Freischmann
| ES Scoping and ES Chapter (if required) |  | 3945 |  | 0 | 0 |  | Pell Freischmann
| BESS access track design |  | 2450 |  | 0 | 0 |  | Pell Freischmann
Noise | Noise survey and report |  | 8600 |  | 0 | 0 |  | Tetra Tech
| ES Scoping and ES Chapter (if required) |  | 2800 |  | 0 | 0 |  | Tetra Tech
Arboricultural | Arboricutural Survey and Report |  | 8500 |  | 0 | 0 |  | EDP
Battery Safety | OBSMP |  | 4560 |  | 0 | 0 |  | ARC
Ground conditions | Geo-Environmental Phase I |  | 8000 |  | 0 | 0 |  | Stantec
Socio-economic | Socio-economic report |  | 10900 |  | 0 | 0 |  | Stantec / Wave Hill - TBC
Glint and Glare | Glint and Glare Assessment (fixed and trackers) |  | 25915 |  | 0 | 0 |  | Pager Power
| ES Scoping |  | 1495 |  | 0 | 0 |  | Pager Power
| ES Glint and Glare Chapter |  | 4995 |  | 0 | 0 |  | Pager Power
Outline CEMP | Main document |  | 2000 |  | 0 | 0 |  | Stantec
| Ecology input |  | 4000 |  | 0 | 0 |  | EDP
| Landscape input |  | 1000 |  | 0 | 0 |  | EDP
Outline Decommissioning Plan | Outline Decommissioning Plan |  | 5500 |  | 0 | 0 |  | Stantec
Topographical Survey | Topographical survey (drone) |  | 8445 |  | 0 | 0 |  | MJ Rees
Minerals | Minerals Impact Assessment |  | 3500 |  | 0 | 0 |  | Stantec
Collaborative Benefits Report | CBR |  | 3500 |  | 0 | 0 |  | Stantec / Thirty 4/7
Comms/PR | Comms |  | 90900 |  | 0 | 0 |  | Grasshopper
Utilities | Utilities search |  | 2555.8 |  | 0 | 0 |  | Centremaps Ltd
Land | Cable Routes |  | 60000 |  | 0 | 0 |  | Gateley Hamer
Post-submission / Examination | Planning |  | 28550 |  | 0 | 0 |  | Stantec
| Legals |  | 41000 |  | 0 | 0 |  | Ashfords
| Other consultants inputs (review/resposne to Inspectors questions, attendance at hearings etc) |  | 65000 |  | 0 | 0 |  | Various (EDP etc)
Contingency | 10% of planning costs |  | 141512.83 |  | N/A | N/A |  |  | 2024-08-24: 0; 2024-09-24: 0; 2024-10-24: 0; 2024-11-24: 0; 2024-12-24: 0; 2025-01-24: 0; 2025-02-24: 0; 2025-03-24: 0; 2025-04-24: 0; 2025-05-24: 0; 2025-06-24: 0; 2025-07-24: 0; 2025-08-24: 0; 2025-09-24: 0; 2025-10-24: 0; 2025-11-24: 0; 2025-12-24: 0; 2026-01-24: 0; 2026-02-24: 0; 2026-03-24: 0; 2026-04-24: 0; 2026-05-24: 0
Third Party Wayleaves |  |  | 400000 |  | 0 | 0
Satisfaction of pre-commencement planning conditions |  |  | 0 |  | 0 | 0
Transaction Cost |  |  | 0 |  | 0 | 0
Total |  | 0 | 2081424.13 | 181102.5 | 0 | 697419.5094 |  |  | 2021-01-01: 0; 2022-01-01: 0; 2024-08-24: 0; 2024-09-24: 0; 2024-10-24: 0; 2024-11-24: 0; 2024-12-24: 0; 2025-01-24: 0; 2025-02-24: 0; 2025-03-24: 0; 2025-04-24: 0; 2025-05-24: 0; 2025-06-24: 0; 2025-07-24: 0; 2025-08-24: 0; 2025-09-24: 0; 2025-10-24: 0; 2025-11-24: 0; 2025-12-24: 0; 2026-01-24: 0; 2026-02-24: 0; 2026-03-24: 697419.5094; 2026-04-24: 0; 2026-05-24: 0
Installed capacity | 143
Total/MW |  | 0 | 14555.4135 | 1266.451 | 0 | 4877.0595
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pre-submission fee £32k plus other legal advice £23k
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. £2,000 - £3,000 to review the position on Awel y Mor (DCO powers plus issues and risks to consider) 2. £1,000 - £1,500 to review a draft representation to the ExA, review relevant DCO submission material and flag any issues; advise on the approach to engage with the Examination into Mona. 3. £3,000 - £5,000 to advise on the approach with Mares and their applications. 4. £3,000 - £5,000 to advise on the approach to your generation licence for the development, as well as to review the application for submission to Ofgem
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Items 1 - 7 up until and including Submission (£99,500) plus expenses (£6,977.50)
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This covers pre-app, application and examination fees. Refer to Summary of DNS fees from Vincent for breakdown.
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EIA Scoping £4500, ES Prep and coordination assuming 4 x ES chapters scoped in £29,000, meetings £2,700
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Optional
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PO for £17,250 issued 14.06.24. Refer to EDP FRT dated 18.06.24 for breakdown of instructed items. PO uplifted by £34,550 02.08.24. Refer to e-mail from TG dated 31.07.24.
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Desk study review £1,000, Ph1 survey £2,500 inc. data charges £600, Site access arrangements £1,500
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3 surveys during April, May and June 2025. Might be possible to do 1 of these surveys in July 2025.
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6 visits during Nov 2024 - Feb 2025
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1) GLTA £2,500 - required. Provision scopes: 2) Nighttime walkover 3 visits ,4 pairs of surveys Aug and Oct 2024 and April 2025 £13,500 - may be required/scoped out. 3) Automated detector 7 surveys split across 2024-2025 £9,000 - may be required/scoped out 4) Data analysis - £3,000
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note - This item was originally £28,000 but EDP requested an additional £3,000 (e-mail 18.06.24) due to an error. PO needs to be increased by this amount, once other items are instructed
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes 1 on-site pond and 10 off-site ponds (within 250m). Survey mid-April to end of June. 2025 Possible to do 1 x survey of off-site pond in June 2024.
Note on C21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 visits required in Spring and late Summer, 1 x Sept 2024 and 1 x May 2024
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Baseline report £8000, design inputs £2000
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EDP suggested £5k for EIA for PAC and £10k for ES Chapter and NTS
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes ecology input £3000 and landscape input £2000 (EDP)
Note on E28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Excludes River Morph assessment (given BNG is optional) otherwise would be an additional £3,500
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Desktop study £1000, consultation on VP £500, site visit and photos day £5000 and night £4000
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design development £2,000, LV baseline £8000 and LVA for PAC £5000
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ES Chapter eand TS £10k plus cumulative £2k
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes 5 at Y1 and Y15
Note on C39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AOC - £245 per hax 162 ha (£39,690) Cotswold - £60,000 (based on 154ha)
Note on E43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £425k is based on a 2% trenching sample £370k (as below) plus 15% contingency to allow for more complex archaeology in greater concentrations being identified. Costs will be lower if 1% (as below). 2% trenching sample (equating to 344 trenches, each measuring 50m in length and 1.8m in width): £370,000 + VAT. 1% trenching sample (equating to 174 trenches, each measuring 50m in length and 1.8m in width): £215,000 + VAT.
Note on C45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: D1 Masterplan advice, D2 NRW engagement, D3 SAB engagement D5 Summary and D13 Meetings
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Breach modelling - unlikely to be required
Note on C52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kernon advised this isn't required as site is predominantly 3b. Phase 1 - £2,700 to do the pasture fields (w/c 22nd July or 29th July) Phase 2 - Late September for arable (£4,000).
Note on C55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed 3 x meetings £1350
Note on C62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tree survey £2,500, design inputs £1,000, Baseline report and tree constraints £2,500, AIA for PC/submission (assumed £2,500)
Note on C66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Item 5 G&G Assessment (Fixed and Tracker ) Item 7 Stakeholder Consultation and Support
Note on C75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CBR - optional.
Note on C76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total £62,650 plus £25k expenses. This includes: Stage 1 (excl. local community online social sentiment) £ 9,350 Stage 2 - EIA Scoping and Informal consultation £16,600 Stage 3 PAC £19,700 Stage 4 PAC report and application submission £6,800 5) Media - £2550 6) PM and Communty response desk £7,650
Note on E78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicative figure
Note on E79: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post-submission and Examination estimate (Items 8 - 11)
Note on E80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post-submission fee £41k
Note on E81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicative figure
Note on E83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £400k is worst case scenario, and the best case scenario for shortest route, at lower land value, came out at £275k.

## Lime Down (Melksham)
Melksham Solar Budget Cost | [17 empty] | PRE-APP | [11 empty] | PRE-APP | [11 empty] | PRE-APP | [23 empty] | SUBMITTED | [6 empty] | DECISION
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Variance on quote (remaining spend) | PO Raised? | Consultant | time axis 2021-01-01 to 2026-05-01
Grid | NGET Application | 59300 | 117950 | 59300 | 59300 |  | Item fully billed |  | 2021-03-01: 59300; 2024-05-01: 58650
| Deposit/security | 809743 | 809743 | 809743 | 679921.7 |  | Item fully billed |  | 2021-09-01: 77274.38; 2022-03-01: 206809.25; 2022-09-01: 253569.98; 2023-03-01: 142268.39; 2023-09-01: 66472.272; 2024-03-01: 41296.764; 2024-09-01: 21228.9; 2025-03-01: 822.984; 2025-09-01: 0
| Auxiliary connection applications |  |  |  | 0 |  | N/A no fee yet
| Network Rail BAPA | 120000 |  |  | 0 |  | N/A no fee yet
| Network Rail Easement Fee | 315000
Lease/Option |  |  | 15536.25 |  | 15536.25 |  | Item fully billed |  | 2023-06-01: 1345.25; 2023-08-01: 14191
Planning Consultant | Lanpro (Up to 30.06.24) | 375521.14 | 375521.14 | 679020 | 375521.14 | 303498.86 | Reconciling | Lanpro | 2023-07-01: 11863; 2023-08-01: 20120; 2023-09-01: 29846; 2023-10-01: 25785; 2023-11-01: 31388; 2023-12-01: 37092; 2024-01-01: 37092; 2024-02-01: 37299.86; 2024-03-01: 37204.56; 2024-04-01: 37092.86; 2024-05-01: 7552; 2024-06-01: 41092.86; 2024-07-01: 22093
| Aecom (From 20.05.24) | 508766 |  | 508766 | 70641.55 | 438124.45 | Yes | AECOM | 2024-05-01: 32093; 2024-06-01: 38548.55
| Scoping Report Finalisation | [6 empty] | AECOM
| Site Selection & DAS | [6 empty] | AECOM
Planning Application Fee | Planning Performance Agreement | 180000 |  | 180000 | 0 | 180000 | N/A no fee yet | Wiltshire Council
| Environment Agengy Advice | 20000 | 20000 | 20000 |  | 20000 | Awaiting PO | Envirnment Agency
| Planning Inspectorate | 600000 |  |  | 0 | 0 | N/A no fee yet | Planning Inspectorate
| Planning Inspectorate- Pre App advice | 68127 |  |  | 0 | 0 | N/A no fee yet | Planning Inspectorate
Expenses | Planning Constraints Report | 1152 | 1152 | 1152 | 0 | 1152 | Item fully billed | Entrust Services
| Mapping | 2329.51 | 2329.51 | 2329.51 | 0 | 2329.51 | Item fully billed | OS Mapping
Planning Studies | Topographical Study | 183400 | 51500 | 51500 | 49500 | 2000 | Yes | Survey Solutions | 2023-11-01: 250; 2024-01-01: 42500; 2024-02-01: 6750
| Geophysical Survey | 159000 | 159000 | 159000 | 169231.66 | -10231.66 | No but can be | WYAS (under Lanpro) | 2023-09-01: 650; 2023-10-01: 29211.66; 2023-11-01: 33120; 2023-12-01: 1650; 2024-01-01: 6975; 2024-02-01: 8775; 2024-03-01: 11475; 2024-04-01: 9087.5; 2024-05-01: 28125; 2024-07-01: 40162.5
| Geophysical Survey (cable route) | 100000 |  |  | 0 | 0 | N/A no fee yet | WYAS
| Arboricultural Survey | 45000 | 45000 | 45000 | 28245.92 | 16754.08 | Reconciling | Lanpro | 2023-08-01: 85; 2023-09-01: 1235; 2023-10-01: 1106; 2023-12-01: 2500; 2024-01-01: 2074; 2024-02-01: 3245.92; 2024-03-01: 3000; 2024-04-01: 3000; 2024-05-01: 5000; 2024-06-01: 5000; 2024-07-01: 2000
| Historic Environment | 270125 | 270125 | 270125 | 189022.93 | 81102.07 | Reconciling | Lanpro | 2023-07-01: 14632.5; 2023-08-01: 8645; 2023-09-01: 21705; 2023-10-01: 17695; 2023-11-01: 16912; 2023-12-01: 15434.51; 2024-01-01: 21670; 2024-02-01: 12165; 2024-03-01: 10905; 2024-04-01: 9595; 2024-05-01: 6683.12; 2024-06-01: 11897.5; 2024-07-01: 21083.3
| Trial Trenching | 500000 |  |  | 0 | 0 | N/A no fee yet | WYAS (through Lanpro)
| LVIA | 330000 | 330000 | 330000 | 143018.5 | 186981.5 | Reconciling | Lanpro | 2023-07-01: 1157; 2023-08-01: 5309.5; 2023-09-01: 7500; 2023-10-01: 12060; 2023-11-01: 22240; 2023-12-01: 14379; 2024-01-01: 5074; 2024-02-01: 5000; 2024-03-01: 13184; 2024-04-01: 4805; 2024-05-01: 15245; 2024-06-01: 23027.5; 2024-07-01: 14037.5
| Flood Risk Assessment | 45000 | 45522 | 45522 | 11272.23 | 34249.77 | Yes | Arcadis | 2023-09-01: 1035; 2023-10-01: 937.04; 2023-11-01: 2004.21; 2023-12-01: 1249.3; 2024-01-01: 485.68; 2024-02-01: 2682; 2024-04-01: 2879
| ALC Classification | 40000 | 34365 | 34365 | 15146.01 | 19218.99 | Yes | Reading Agri Consultants | 2023-10-01: 2902.2; 2023-12-01: 1805.58; 2024-01-01: 1775.16; 2024-02-01: 5675.91; 2024-03-01: 2987.16
| Transport Input | 111450 | 111450 | 111450 | 66806.4 | 44643.6 | Yes | TPA | 2023-08-01: 4050; 2023-09-01: 5000; 2023-10-01: 5995; 2023-11-01: 4233.15; 2023-12-01: 3730; 2024-01-01: 5313; 2024-02-01: 10643.75; 2024-03-01: 2546.5; 2024-04-01: 10625; 2024-05-01: 14670
| Abnormal loads | 7200 | 7200 | 7200 |  | 7200 | Yes | Wynns | 2024-02-01: 2950; 2024-03-01: 3150
| Air Quality | 46500 | 42000 | 42000 | 4253.73 | 37746.27 | Yes | Arcadis | 2024-01-01: 3422.25; 2024-02-01: 831.48
| Minerals & deposits | 10000 | 7000 | 7000 | 3230 | 3770 | Yes | Ted Clover | 2024-03-01: 3230
| Contaminated land | 18000 | 27900 | 27900 | 15472.5 | 12427.5 | Yes | Lucion Group (former DS) | 2023-10-01: 2187.5; 2023-11-01: 2492; 2024-02-01: 5393; 2024-07-01: 5400
| Climate change | 13000 | 8652 | 8652 | 1155 | 7497 | Yes | Bureau Veritas | 2024-04-01: 1155
| Socioeconomics | 15000 | 14895 | 14895 | 2960.5 | 11934.5 | Reconciling | Lanpro | 2024-07-01: 2960.5
| Ecological Surveys | 335855 | 391340 | 391340 | 277354 | 113986 | Yes | Clarkson & Woods | 2023-06-01: 50305; 2023-07-01: 11625; 2023-08-01: 12905; 2023-09-01: 18195; 2023-10-01: 7232.5; 2023-11-01: 16313; 2023-12-01: 2749; 2024-01-01: 26680; 2024-02-01: 11855; 2024-03-01: 2744; 2024-04-01: 60458; 2024-05-01: 50787.5; 2024-06-01: 5505
| *Site District Level Licensing | 0 | [5 empty] | Clarkson & Woods
| Ecological Surveys (Cable route) | 60000 |  |  | 0 | 0 | N/A no fee yet | Clarkson & Woods
| *Cable District Level Licensing | 0 | [5 empty] | Clarkson & Woods
| Environmental Masterplan | 55000 | 55000 | 55000 | 5749.5 | 49250.5 | Reconciling | Lanpro | 2023-12-01: 3025; 2024-01-01: 2724.5
| Noise | 27000 | 26700 | 26700 | 10902 | 15798 | Yes | Tetratech | 2023-12-01: 7362; 2024-02-01: 3540
| Glint/Glare | 32000 | 23671 | 23671 | 2856 | 20815 | Yes | Pager Power | 2024-02-01: 861; 2024-03-01: 1995
| GIS Support | 85000 | 85000 | 85180 | 41250.7 | 43929.3 | Reconciling | Lanpro | 2023-08-01: 2836; 2023-09-01: 2600; 2023-10-01: 720; 2023-11-01: 2459; 2023-12-01: 3160; 2024-01-01: 2424; 2024-02-01: 6564.22; 2024-03-01: 4514; 2024-04-01: 1885; 2024-05-01: 4800; 2024-07-01: 9288.48
Legal | Legal DCO drafting | 450000 | 450000 | 450000 | 114540.15 | 335459.85 | Yes | Pinsent Masons | 2023-09-01: 4824; 2023-10-01: 9429.6; 2024-01-01: 13754; 2024-02-01: 30398.75; 2024-05-01: 24555; 2024-06-01: 13403; 2024-07-01: 18175.8
Comms and Engagement | Consultation/PR/Website | 315000 | 313072.5 | 313072.5 | 84511.1 | 228561.4 | Reconciling | Counter Context | 2023-09-01: 13611; 2023-11-01: 25135; 2023-12-01: 10876.5; 2024-05-01: 13082.85; 2024-06-01: 21805.75
Engineering | Utilities Digitisation | 10000 |  |  | 0 | 0 | N/A no fee yet
| Cable route feasibility | 1600 | 1600 | 1545 |  | 1545 | Item fully billed | JSM | 2023-09-01: 1288.07; 2024-02-01: 1966; 2024-06-01: 155.88; 2024-07-01: 542.3
| Cable route engineering design | 45000 | 40960 | 40960 | 6748.5 | 34211.5 | Yes | Omnia | 2023-09-01: 311.86; 2023-10-01: 155.88; 2023-11-01: 1050.33; 2023-12-01: 311.76; 2024-01-01: 3331.15; 2024-02-01: 1213.52; 2024-07-01: 374
Other Deliverables | Funding Statement | 0 | 0 | 0 | 0 | 0 | N/A | IGP
| Statement of Need | 14000 | 13640 | 13640 | 0 | 13640 | Yes | Humbeat
| Utilities | 10000 |  |  | 6437.18 |  | Item fully billed | Centremaps | 2023-07-01: 5775; 2023-12-01: 662.18
| Electromagnetic fields | 2000 |  | 13015 | 5495 | 7520 | Yes | Pager Power | 2024-04-01: 5495
Agreements | Protective provisions third party legal costs | 90000 |  |  | 0 | 0 | N/A no fee yet | Pinsent Masons
| Co-operation agreement | 6000 |  |  | 0 | 0 | N/A no fee yet | Pinsent Masons
Professional services | Natural England DAS | 11500 | 11500 | 11500 | 0 | 11500 | Yes | Natural England
| Land Referencing and Land Agency | 336000 | 498000 | 498000 | 158039.11 | 339960.89 | Yes | Dalcour Maclaren/Atkins | 2023-08-01: 2145; 2023-09-01: 10088; 2023-10-01: 5399.29; 2023-11-01: 6735.29; 2023-12-01: 12515; 2024-01-01: 2957.7; 2024-02-01: 3404.25; 2024-03-01: 34645.52; 2024-04-01: 27991.55; 2024-05-01: 39896.01; 2024-06-01: 1130.75; 2024-07-01: 11130.75
| Cable route landowner discussions | 120000 |  |  | 0 | 0 | N/A no fee yet
| Cable route landowner payments | 650000 |  |  | 0 | 0 | N/A no fee yet
| Cable route legals | 100000 |  |  | 0 | 0 | N/A no fee yet
Contingency | 10% of planning costs | 500942.565 | 0 |  | N/A |  | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5030.5 | 4505.25 | 5395.05 | 10780.093 | 11541.738 | 15759.669 | 10598.683 | 17529.474 | 15781.041 | 9693.522 | 14607.736 | 20259.347 | 16043.604 | 13611.738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  | 200000 | 0 |  | 0 |  | N/A
Satisfaction of pre-commencement planning conditions |  | 30000 | 30000 |  | 0 |  | N/A
Accounting & admininstration, and bank charges |  | 20000 | 20000 |  |  |  | N/A
Transaction Cost |  | 30000 | 30000 |  | 0 |  | N/A
Total |  | 8490511.215 | 4487324.4 | 5338543.01 | 1413198.62 |  |  |  | 0 | 0 | 59300 | 0 | 0 | 0 | 0 | 0 | 77274.38 | 0 | 0 | 0 | 0 | 0 | 206809.25 | 0 | 0 | 0 | 0 | 0 | 253569.98 | 0 | 0 | 0 | 0 | 0 | 142268.39 | 0 | 0 | 56680.75 | 49557.75 | 75681.55 | 195141.295 | 132358.408 | 180091.649 | 129100.513 | 195781.914 | 176995.701 | 182571.026 | 188676.646 | 321398.827 | 177610.394 | 160859.868 | 0 | 21228.9 | 0 | 0 | 0 | 0 | 0 | 822.984 | 0 | 0
Installed capacity | 550
Total/MW |  | 15437.2931 | 8158.7716 | 9706.4418 | 2569.452
| Less Grid Costs | 7680768.215
Note on M4: Sam Aitchison: Invoice 80123594 Paid 09/03/21
Note on AY4: Sam Aitchison: Mod App to Change dates - 80323620
Note on D7: Natasha Worrall: Based on WB&C £30,000 per crossing, 4 crossings
Note on D8: Natasha Worrall: Easement fee based on £630 per MW
Note on AN9: Natasha Worrall: Carter Jonas for Sean Edwards land
Note on AP9: Natasha Worrall: Carter Jonas & Pellys agent fees/option agreement for Sean Richards
Note on D10: Will Threlfall: 679020
Note on E10: Will Threlfall: 679020
Note on AO10: Natasha Worrall: #008343
Note on AP10: Natasha Worrall: 008706
Note on AQ10: Natasha Worrall: 008772 Whole team site visit held this month so cost higher
Note on AR10: Natasha Worrall: 008975 009186
Note on AS10: Natasha Worrall: 09177 009390
Note on AT10: Natasha Worrall: 009375
Note on AU10: Natasha Worrall: 009563
Note on AV10: Natasha Worrall: 009766
Note on AW10: Natasha Worrall: 010229
Note on AX10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 010444
Note on AY10: Will Threlfall: 010454 Expenses feb 24- Apr24 £3552 010445 Incorprating BESS £4000
Note on AZ10: Will Threlfall: 010688 (Inc.BESS) 010687 (Planning Costs)
Note on BA10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Challended from £37k
Note on AY11: Will Threlfall: Pending PO aproval
Note on AZ11: Will Threlfall: 28565420- Scoping Report Fee included
Note on D14: Natasha Worrall: Update when final PPA agreed with Wiltshire
Note on F14: Natasha Worrall: Update when final PPA agreed with Wiltshire
Note on AS20: Natasha Worrall: Lanpro producrement of topo survey
Note on AU20: Natasha Worrall: 61467
Note on AV20: Natasha Worrall: 009779
Note on AQ21: Natasha Worrall: 008935
Note on AR21: Natasha Worrall: 008978
Note on AS21: Natasha Worrall: 009179
Note on AT21: Natasha Worrall: 009377
Note on AU21: Natasha Worrall: 009565
Note on AV21: Natasha Worrall: 009982
Note on AW21: Natasha Worrall: 010209
Note on AX21: Natasha Worrall: 009981
Note on AY21: Will Threlfall: 010450
Note on BA21: Will Threlfall: 010906
Note on AP23: Natasha Worrall: #008707
Note on AQ23: Natasha Worrall: 008765
Note on AR23: Natasha Worrall: 009180
Note on AT23: Natasha Worrall: 009378
Note on AU23: Natasha Worrall: 009572
Note on AV23: Natasha Worrall: 009783 + £129 for meeting
Note on AW23: Natasha Worrall: 009980
Note on AX23: Natasha Worrall: 010211
Note on AY23: Will Threlfall: 010451
Note on AZ23: Will Threlfall: 010693
Note on BA23: Will Threlfall: 010907
Note on AO24: Natasha Worrall: #8345
Note on AP24: Natasha Worrall: 008704
Note on AQ24: Natasha Worrall: 008768 008935
Note on AR24: Natasha Worrall: 008979 009185
Note on AS24: Natasha Worrall: 009179
Note on AT24: Natasha Worrall: 009377
Note on AU24: Natasha Worrall: 009571
Note on AV24: Natasha Worrall: 009779
Note on AX24: Natasha Worrall: 010210
Note on AY24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 010449
Note on AZ24: Will Threlfall: 010692
Note on BA24: Will Threlfall: 010905 010915
Note on AO26: Natasha Worrall: #8344
Note on AP26: Natasha Worrall: #008705
Note on AQ26: Natasha Worrall: 008767
Note on AR26: Natasha Worrall: 008976
Note on AS26: Natasha Worrall: 009178 009187
Note on AT26: Natasha Worrall: 009376
Note on AU26: Natasha Worrall: 009564 009570
Note on AV26: Natasha Worrall: 009773
Note on AW26: Natasha Worrall: 009983
Note on AX26: Natasha Worrall: 010223
Note on AY26: Will Threlfall: 010446- £14,000 010448-LVIA Incoorp BESS- £1,245
Note on AZ26: Will Threlfall: 010689 010691 (CJ Meetings) 010690 (Inc.BESS)
Note on BA26: Will Threlfall: 010903 010904
Note on AQ27: Natasha Worrall: 680023703
Note on AR27: Natasha Worrall: 680026301
Note on AS27: Natasha Worrall: 680028743
Note on AT27: Natasha Worrall: 680033038
Note on AU27: Natasha Worrall: 680033905
Note on AV27: Natasha Worrall: 680039022
Note on AX27: Natasha Worrall: 680043713
Note on AR28: Natasha Worrall: 10079/23/677/E
Note on AT28: Natasha Worrall: 10079/23/789/E
Note on AU28: Natasha Worrall: 10079/24/079/E
Note on AV28: Natasha Worrall: 100079/24/141/E
Note on AW28: Natasha Worrall: 10079/24/215/E
Note on AP29: Natasha Worrall: 015396
Note on AQ29: Natasha Worrall: 015528
Note on AR29: Natasha Worrall: 015681
Note on AS29: Natasha Worrall: 015766
Note on AT29: Natasha Worrall: 015919
Note on AU29: Natasha Worrall: 016044
Note on AV29: Natasha Worrall: 016239
Note on AW29: Natasha Worrall: 016353
Note on AX29: Natasha Worrall: 016418
Note on AY29: Natasha Worrall: 016597
Note on AV30: Natasha Worrall: 4060
Note on AW30: Natasha Worrall: 4079
Note on AU31: Natasha Worrall: 680036209
Note on AV31: Natasha Worrall: 680039018
Note on AW32: Natasha Worrall: LDS/001
Note on AR33: Natasha Worrall: 93799
Note on AS33: Natasha Worrall: 193024
Note on AV33: Natasha Worrall: 198710 198711
Note on BA33: Will Threlfall: 208919
Note on BA35: Will Threlfall: 101902
Note on AN36: Natasha Worrall: #83901
Note on AO36: Natasha Worrall: 83661
Note on AP36: Natasha Worrall: 83093 83662
Note on AQ36: Natasha Worrall: 8521 83094 85191 83664
Note on AR36: Natasha Worrall: 83095
Note on AS36: Natasha Worrall: 85192 83096 83665
Note on AT36: Natasha Worrall: 83666
Note on AU36: Natasha Worrall: 83097
Note on AV36: Natasha Worrall: 83098
Note on AW36: Natasha Worrall: 83099
Note on AX36: Natasha Worrall: 830910 87381 83667
Note on AY36: Will Threlfall: 87382 85193 83668 830911
Note on AZ36: Will Threlfall: 87383 83669
Note on AT40: Natasha Worrall: 009376
Note on AU40: Natasha Worrall: 009564
Note on AT41: Natasha Worrall: 30065910
Note on AV41: Natasha Worrall: 784-B049116
Note on AV42: Natasha Worrall: 709676
Note on AW42: Natasha Worrall: 709727
Note on AP43: Natasha Worrall: 008705
Note on AQ43: Natasha Worrall: 008767
Note on AR43: Natasha Worrall: 680026301
Note on AS43: Natasha Worrall: 009181
Note on AT43: Natasha Worrall: 009379
Note on AU43: Natasha Worrall: 009566
Note on AV43: Natasha Worrall: 010212
Note on AW43: Natasha Worrall: 009979
Note on AX43: Natasha Worrall: 009785
Note on AY43: Will Threlfall: 010694
Note on BA43: Will Threlfall: 010908 011095
Note on AQ44: Natasha Worrall: 6775547
Note on AR44: Natasha Worrall: 6784076
Note on AU44: Natasha Worrall: 6805834
Note on AV44: Natasha Worrall: 205269
Note on AY44: Natasha Worrall: 6821932
Note on AZ44: Will Threlfall: 6835101
Note on BA44: Will Threlfall: 6840389
Note on D45: Natasha Worrall: Costs will go up as a result of media reactivity required / amount of feedback received £75000-£100,000
Note on AQ45: Natasha Worrall: 204990 204992
Note on AS45: Natasha Worrall: 205061 205066
Note on AT45: Natasha Worrall: 205104
Note on AY45: Will Threlfall: 205418
Note on AZ45: Will Threlfall: 205512
Note on AQ47: Natasha Worrall: SI402527
Note on AV47: Natasha Worrall: To be invoiced
Note on AZ47: Will Threlfall: INV-13000600
Note on BA47: Will Threlfall:JSM- SL0677
Note on AQ48: Natasha Worrall: INV-2308-131
Note on AR48: Natasha Worrall: NV-2309-134
Note on AS48: Natasha Worrall: INV-2310-082
Note on AT48: Natasha Worrall: INV-2312-148
Note on AU48: Natasha Worrall: INV-2401-137
Note on AV48: Natasha Worrall: INV-2402-186
Note on BA48: Will Threlfall: INV-130000970
Note on D49: Natasha Worrall: Use WB&C
Note on J50: Natasha Worrall: si gillett
Note on AO51: Natasha Worrall: AT/08/23
Note on AT51: Natasha Worrall: AT/11/23
Note on AX52: Natasha Worrall: 709786
Note on J56: Natasha Worrall: DM will bill for Atkins utilities searches (outside of PO)
Note on AP56: Natasha Worrall: UK-CI-155292
Note on AQ56: Natasha Worrall: UK-CI-163074
Note on AR56: Natasha Worrall: UK-CI-171432
Note on AS56: Natasha Worrall: UK-CI-185592
Note on AT56: Natasha Worrall: UK-CI-179868
Note on AU56: Natasha Worrall: UK-CI-200316
Note on AV56: Natasha Worrall: UK-CI-210918
Note on AW56: Natasha Worrall: UK-CI-220386
Note on AX56: Will Threlfall: UK-CI-223986
Note on AY56: Will Threlfall: UK-CI-234498 Includes 13,015 Atkins Work
Note on BA56: Will ThrelfallUK-CI-242286

## Green Hill (Grendon)
Grendon Solar Budget Cost | [7 empty] | Assumed cost | [15 empty] | PRE-APP | [11 empty] | PRE-APP | [11 empty] | PRE-APP | [15 empty] | SUBMITTED | [9 empty] | DECISION
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Initial Quote Instructed (£) | Quote Update Dec 2023 (Site F) | Quote Update April 2024 (Site G) | Quote Update June 2024 (Site A.2) | Estimated cost during examination | Amount paid before Netsuites | PO amount | PO Number | PO Status | Total Invoiced Amount (£)/ As of last month | Consultant | time axis 2021-01-01 to 2029-12-01
Grid | NGET Application | 120950 | 120950 | 120950 | 120950 | 120950 | [6 empty] | 61650 |  | 2021-01-01: 59300; 2022-05-01: 70350; 2023-02-01: -70350; 2024-03-01: 3000; 2024-05-01: 58650
| Consultants | 1800 | 1800 | 1800 | 1800 | 1800 | [6 empty] | 0 |  | 2022-05-01: 1800
| Deposit/security | 0 | 1062356.9376 | 1062356.9376 | 1062356.9376 | 1062356.9376 | [6 empty] | 0 |  | 2026-03-01: 16202.2248; 2026-09-01: 19572.4584; 2027-03-01: 27641.0028; 2027-09-01: 14977.5144; 2028-03-01: 531548.7; 2028-09-01: 351353.61; 2029-03-01: 87720.9888; 2029-09-01: 13340.4384
| Auxiliary connection applications | [11 empty] | 0
| Network Rail BAPA | [11 empty] | 0
Lease/Option | [5 empty] | 321253.39 | [6 empty] | 10350 | Land Agents | 2023-07-01: 10000; 2023-10-01: 350
| National Grid Title Restriction |  |  | 15000 | 15000 | 15000 | 10000 | bar: 2023-07-01; 2023-10-01
Legal/Coorporate | [12 empty] | 0
Planning Consultant |  | 658100 | 658100 | 658100 | 637100 | 811136 | 826041.27 | 450000 |  | 489968 | PO000153 | Increase | 476008.24 | Lanpro | 2023-06-01: 1638.75; 2023-07-01: 11473; 2023-08-01: 18641.45; 2023-09-01: 20380; 2023-10-01: 25385; 2023-11-01: 40557.14; 2023-12-01: 34807; 2024-01-01: 35089.43; 2024-02-01: 44543.14; 2024-03-01: 42153.64; 2024-04-01: 46908.64; 2024-05-01: 53408.64; 2024-06-01: 60215.41; 2024-07-01: 40807
Planning Application Fee | Planning Performance Agreement | 180000 |  | 31351 |  | 31351 |  | 36341 |  |  |  |  | 0 | North Northants
| Planning Performance Agreement | [6 empty] | 70000 | [5 empty] | West Northants
| Planning Performance Agreement | [6 empty] | 70000 | [5 empty] | Milton Keynes
| Planning Inspectorate | 600000 |  |  |  | 600000 | [6 empty] | 0 | Planning Inspectorate
Expenses | Planning Constraints Report | 1152 | 1152 | 1152 |  | 1152 | [6 empty] | 0 | Entrust Services
| Utilities | 10000 | 8331.5 | 8331.5 |  | 8331.5 | [7 empty] | Centremaps | 2023-07-01: 8331.5
| Mapping | 1908 | 1908 | 2346.31 |  | 2346.31 | [6 empty] | 10420.05 | OS Mapping | 2023-09-01: 660.05; 2023-10-01: 9760
Planning Studies | Topographical Study | 100000 |  | 53940 | 53940 | 62690 | 67280 | - |  |  | PO000973 | Raised | 34075 | Survey Solutions | 2023-12-01: 3685; 2024-02-01: 25440; 2024-06-01: 4950
| Geophysical Survey | 189000 | 189000 | 189000 | 161325 | 199575 | 213996 |  |  | 149658 | PO000158 | Increase | 141507.25 | Lanpro | 2023-10-01: 36609.75; 2023-11-01: 160; 2024-02-01: 13950; 2024-03-01: 6750; 2024-04-01: 24075; 2024-05-01: 45112.5; 2024-06-01: 14850
| Geophysical Survey (cable route) | 100000 |  | 100000 | 100000 | 100000 | 100000 |  |  |  | TBC | TBC | 0 | WYAS
LiDAR assessment
| Arboricultural Survey | 45000 | 45000 | 45000 | 51920 | 56240 | 57735 |  |  | 37109 | PO000160 | Increase | 37624.33 | Lanpro | 2023-08-01: 577; 2023-09-01: 493.5; 2023-11-01: 4574; 2023-12-01: 6972.4; 2024-01-01: 3272.9; 2024-02-01: 2295.53; 2024-03-01: 8404; 2024-04-01: 5035; 2024-05-01: 1000; 2024-06-01: 5000
| Historic Environment | 300125 | 273875 | 273875 | 273875 | 298405 | 9485 | 70000 |  | 151269 | PO000158 | Increase | 220311.02 | Lanpro | 2023-06-01: 4732.5; 2023-07-01: 1985; 2023-08-01: 11505; 2023-09-01: 16033.25; 2023-10-01: 60860.61; 2023-11-01: 14905; 2023-12-01: 13785; 2024-01-01: 15770.38; 2024-02-01: 17090.5; 2024-03-01: 17985; 2024-04-01: 9000; 2024-05-01: 5357.5; 2024-06-01: 31301.28
| Trial Trenching | 500000 |  | 500000 | 500000 | 500000 |  |  |  | 287320 |  | Raised | 0 | Lanpro (Subcontractor: CFA
| LVIA | 290000 | 290000 | 290000 | 333000 | 383500 | 20500 | 180500 |  | 284122 | PO000159 | Increase | 155239.15 | Lanpro | 2023-07-01: 3634.5; 2023-08-01: 3594; 2023-09-01: 5780; 2023-11-01: 21053.17; 2023-12-01: 11073; 2024-01-01: 7033; 2024-02-01: 16685.93; 2024-04-01: 19467.5; 2024-05-01: 36880.55; 2024-06-01: 30037.5
| Environmental Masterplan | 55000 | 55000 | 55000 | 56100 | 68100 | 5500 |  |  |  | PO000159 | Increase | 31750 | Lanpro | 2023-12-01: 5500; 2024-01-01: 7250; 2024-02-01: 4750; 2024-04-01: 4750; 2024-05-01: 5000; 2024-06-01: 4500
| Flood Risk Assessment | 15000 | 14840 | 20150 | 23150 | 26150 | 29150 | 20000 | 7050 | 27200 | PO000228 | Raised | 26131.84 | Mabbett | 2023-06-01: 2100; 2023-11-01: 4950; 2024-02-01: 13020; 2024-03-01: 2670; 2024-04-01: 1391.84; 2024-05-01: 2000
| Hydrolic Modelling |  |  | 12720 |  |  | - |  |  |  | PO000230 | Raised | 1500 | Mabbett | 2024-06-01: 1500
| ALC Classification | 51300 | 51300 | 51300 | 159400 | 189505 | 203926 | 40600 |  |  | PO000739 | Increase | 56629.75 | Arcadis | 2024-02-01: 1869.92; 2024-05-01: 32233.14; 2024-06-01: 22526.69
| Highways | 150000 | 145260 | 123420 | 123420 | 132557 | 138355 | Included in costs |  | 138355 | PO000226 | Raised | 24622.34 | KMC Transport | 2023-12-01: 5704.59; 2024-04-01: 13032.25; 2024-05-01: 5885.5
| Traffic sureys |  |  |  | 14000 | 14450 | - |  |  | 17340 | PO000785 | Raised |  | KMC Transport (Subcontractor: Streetwise) | bar: 2023-12-01
| Abnormal Loads |  |  |  | 17000 | 17830 | - |  |  | 21396 | PO000787 | Raised |  | KMC Transport (Subcontractor: WYNNS) | bar: 2023-12-01
| Air Quality | 65000 |  | 38500 | 64800 | 65350 | 65900 | 1500 |  |  | PO000224 | Increase | 9060.41 | Arcadis | 2023-11-01: 1893.84; 2023-12-01: 849.16; 2024-02-01: 995.36; 2024-03-01: 573.04; 2024-04-01: 675.82; 2024-05-01: 1534.26; 2024-06-01: 2538.93
| Minerals & deposits | 8250 | 8250 | 7500 | 8000 | 9350 | 9600 |  | 0 | 6180 | PO001002 | Raised | 3420 | Ted Clover | 2024-04-01: 3420
| Ground Conditions & Contaminated land | 18000 | 18000 | 17500 | 26000 | 30000 | 33450 |  |  | 30000 | PO000225 | Raised | 15538.5 | Delta Simons | 2023-09-01: 2095.5; 2023-12-01: 2693; 2024-02-01: 8500; 2024-03-01: 2250
| Climate change | 13000 | 12885 | 9745 | 9745 | 9745 | 0 |  |  |  | PO000142 | Raised | 1155 | Bureau Veritas | 2024-03-01: 1155
| Socioeconomics | 15000 | 14895 | 14895 | 14895 | 14895 | 0 | [5 empty] | 2830 | Lanpro | 2024-04-01: 1080; 2024-05-01: 1750
| Ecological Surveys | 185000 | 184100 | 227010 | 465862.5 | 917903 | 975200 |  |  | 600000 | PO000223 | Increase | 400366 | Clarkson and Woods | 2023-11-01: 44931.5; 2023-12-01: 11532; 2024-01-01: 17328; 2024-02-01: 140743; 2024-03-01: 59780; 2024-04-01: 78909.5; 2024-05-01: 47142
| GCN District Level Licencing (DLL) |  |  |  |  | 10000 | - | [6 empty] | Nature Space
| Noise | 27000 | 26700 | 26700 | 30200 | 32050 | 34000 | 13000 |  |  | PO000229 | Increase | 6895 | Tetratech | 2024-03-01: 1950; 2024-04-01: 2995; 2024-06-01: 1950
| Glint/Glare | 20000 | 16980 | 16980 | 24450 | 27680 | 28930 | 9000 |  | 16238 | PO000230 |  | 15525 | Mabbett | 2023-11-01: 1150; 2023-12-01: 7062.5; 2024-02-01: 3700; 2024-03-01: 1500; 2024-05-01: 1401.25; 2024-06-01: 711.25
| GIS Support | 84020 | 84020 | 84020 | 83840 | 85820 | 0 |  |  |  | PO000161 | Increase | 32692.75 | Lanpro | 2023-11-01: 3430; 2023-12-01: 3234; 2024-01-01: 2269.33; 2024-03-01: 7965.5; 2024-04-01: 6193.92; 2024-05-01: 4800; 2024-06-01: 4800
| EMF |  |  |  | 13015 | 13015 | 19008 | [6 empty] | Pager Power | 2024-02-01: 895; 2024-04-01: 5495; 2024-05-01: 1325; 2024-06-01: 895.27
| UXO |  |  |  |  | 1150 | [7 empty] | Lucion Group | bar: 2023-12-01; 2024-02-01; 2024-04-01
Legal | Legal DCO drafting | 350000 |  | 100000 | 100000 | 350000 |  | 0 |  |  |  |  | 67129.84 | Pinsent Masons | 2023-11-01: 1605; 2023-12-01: 5994.8; 2024-02-01: 8704.8; 2024-03-01: 8379.5; 2024-04-01: 4219.8; 2024-05-01: 3882.24; 2024-06-01: 34343.7
Comms and Engagement | Consultation/PR/Comms | 325000 | 324082 | 324082 | 374596 | 404269 |  | 48900 |  |  |  | Costs not agreed | 220943.42 | Copper Consultancy | 2023-07-01: 7045; 2023-08-01: 10482; 2023-09-01: 11207.5; 2023-10-01: 14284.71; 2023-11-01: 19646; 2023-12-01: 11116.25; 2024-01-01: 25577.58; 2024-02-01: 43090.09; 2024-03-01: 28435.56; 2024-04-01: 32058.73; 2024-05-01: 18000
[14 empty] | CHECKING COPPERS INVOICES | 2023-10-01: 14284.71; 2023-12-01: 24217.5; 2024-01-01: 25577.58; 2024-02-01: 43090.09
| Comms Expenses/design | [12 empty] | Copper Consultancy | 2024-01-01: 3300; 2024-02-01: 5236; 2024-04-01: 2005; 2024-05-01: 120
Engineering | Utilities Digitisation | 10000 |  |  |  | 10000 | [5 empty] | 0 | 0
| Electrical Engineering | [10 empty] | 0 |  | Omnia | 2023-08-01: 155.88; 2023-10-01: 188.55; 2023-11-01: 1825.95; 2023-12-01: 3066.69; 2024-02-01: 1150.4; 2024-03-01: 1857.9; 2024-04-01: 596.71; 2024-05-01: 497.26; 2024-06-01: 1618.04
| Battery Safety Consultancy |  |  | 34560 | 34560 | 34560 |  |  |  |  | PO000411 | Raised |  | BST&T Consultancy | 2024-04-01: 3240; 2024-05-01: 2700
| Civils (cable route engineering design) | 25000 |  |  |  | 25000 | [6 empty] | 5558.29 | JSM | 2024-02-01: 1423.89; 2024-03-01: 1355; 2024-05-01: 2372.68; 2024-06-01: 406.72
| Cable route utilities | 20000 |  |  |  | 20000 | [5 empty] | 0 | 0 | IGP
Other Deliverables | Funding Statement | 9000 | 0 | 0 |  | 9000 | [5 empty] | 0 | 0 | Humbeat
| Statement of Need | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | IGP
| Electromagnetic fields | 2000 |  |  |  | 2000 | [5 empty] | 0 | 0
Agreements | Protective provisions third party legal costs | 90000 |  |  |  | 90000 | [5 empty] | 0 | 0
| Co-operation agreement | 6000 |  |  |  | 6000 | [5 empty] | 0 | 0 | Pinsent Masons
| Natural England DAS | 1000 |  |  |  | 1000 | [5 empty] | 0 | 0 | Natural England
Examination | Examination Phase Costs | [10 empty] | 0 | 0
Professional services | Land Referencing & Agency | 336000 |  | 219817.5 | 218004.5 | 218004.5 |  |  |  | 187740 | PO000231 | Raised | 73056.79 | Bruton Knowles | 2023-07-01: 429; 2023-10-01: 2472.67; 2023-11-01: 1256; 2023-12-01: 11921.51; 2024-01-01: 14184.83; 2024-02-01: 18582.25; 2024-03-01: 4077.25; 2024-04-01: 5105.75; 2024-05-01: 5857.17; 2024-06-01: 9170.36
[12 empty] | 0 | 0 | Bruton Knowles
| Cable route landowner discussions | 120000 |  |  |  | 120000 | [5 empty] | 0 | 0
| Cable route landowner payments | 650000 |  |  |  | 650000 | [5 empty] | 0 | 0
| Cable route legals | 100000 |  |  |  | 100000 | [5 empty] | 0 | 0
Contingency | 10% of planning costs | 435685.5 | 0 | [9 empty] | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 847.125 | 3246.9 | 4495.533 | 5664.98 | 16137.333 | 16068.16 | 15129.289 | 14246.82 | 39717.365 | 19316.414 | 26454.971 | 27240.252 | 22214.479 | 4080.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  | 200000 | 0 |  |  | 200000 | [5 empty] | 0 | 0
Satisfaction of pre-commencement planning conditions |  | 0 | 0 | [8 empty] | 0 | 0
Accounting & admininstration, and bank charges |  | 20000 |  |  |  | 20000 | [5 empty] | 0
Transaction Cost |  | 30000 | 0 |  |  | 30000 | [5 empty] | 0 | 0
Total |  | 6534290.5 | 3608785.4376 | 4737102.2476 | 3987198 |  |  | 8356204.7 |  |  |  | 0 | 1510504.89 |  | 59300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -70350 | 0 | 0 | 0 | 9318.375 | 46144.9 | 49450.863 | 62314.78 | 180333.333 | 178005.76 | 178343.689 | 170899.85 | 455473.265 | 219557.804 | 296110.431 | 364149.942 | 253529.629 | 44887.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 16202.2248 | 0 | 0 | [7 empty] | 0 | 0 | 27641.0028 | 0 | 0 | [7 empty] | 0 | 0 | 531548.7 | 0 | 0 | [7 empty] | 0 | 0 | 87720.9888 | 0 | 0
Installed capacity | 650 |  |  |  |  | 7346363.7
Total/MW |  | 10052.7546 | 5551.9776 | 7287.8496 | [7 empty] | 600.223 | 2323.8537
Note on Q4: Sam Aitchison: Invoice 80117122 Paid 03/02/21
Note on AG4: Sam Aitchison: Invoice No. 80198645 Paid 04/05/22
Note on BC4: Sam Aitchison: Novation Fee - 80310759
Note on BE4: Sam Aitchison: Mod App for Date change - 80323621
Note on H9: Lesley Giles: Total Option Fees plus Landowner Legal & Agent fees on Green Hill to date is £321,253.39 That covers the 7 Sites A-G, but which comprise 14 Option Agreements. As of 11/06/2024
Note on AU9: Natasha Worrall: 2111063 Gurney Option 2111061 Wilson Option
Note on AX9: Lesley Giles: 588100
Note on I10: Lesley Giles: legal fees in agreeing the release. £10k per acre will be agreed on the consented design
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: guestimate
Note on AT12: Natasha Worrall: #008346
Note on AU12: Natasha Worrall: 008702
Note on AV12: Lesley Giles: 008762
Note on AW12: Lesley Giles: 008971
Note on AX12: Lesley Giles: 009183
Note on AY12: Lesley Giles: 009363 009380 (Grendon West BESS cost)
Note on AZ12: Lesley Giles: 009558
Note on BA12: Lesley Giles: 009754
Note on BB12: Lesley Giles: INV 009977
Note on BC12: Lesley Giles: INV 010202
Note on BD12: Lesley Giles: 010432 010431
Note on BE12: Lesley Giles: 010685 010672 010673
Note on BF12: Lesley Giles: 010884 010882 010881 010883 010880
Note on AU18: Natasha Worrall: Centremaps C0517
Note on AW19: Lesley Giles: 008771
Note on AX19: Lesley Giles: 008972
Note on AZ20: Lesley Giles: 009367 009387 Grendon West BESS
Note on BB20: Lesley Giles: 102368
Note on BF20: Lesley Giles: 104706
Note on AX21: Lesley Giles: 008974
Note on AY21: Lesley Giles: 009182 Grendon West BESS
Note on BB21: Lesley Giles: 009978
Note on BC21: Lesley Giles: INV 010201
Note on BD21: Lesley Giles: 010438
Note on BE21: Lesley Giles: 010696
Note on BF21: Lesley Giles: 010898 010897
Note on AV24: Natasha Worrall: 008703
Note on AW24: Lesley Giles: 008761
Note on AY24: Lesley Giles: 009176
Note on AZ24: Lesley Giles: 009385
Note on BA24: Lesley Giles: 009366 009757
Note on BB24: Lesley Giles: INV 009987
Note on BC24: Lesley Giles: INV 010220 INV 010205
Note on BD24: Lesley Giles: 010442 010441
Note on BE24: Lesley Giles: 010682
Note on BF24: Lesley Giles: 010899
Note on AT25: Natasha Worrall: #008348
Note on AU25: Natasha Worrall: 008700
Note on AV25: Lesley Giles: 006764
Note on AW25: Lesley Giles: 008973 008980
Note on AX25: Lesley Giles: 009175
Note on AY25: Lesley Giles: 009365 009383 Grendon West BESS
Note on AZ25: Lesley Giles: 009560 009567 - Grendon West BESS
Note on BA25: Lesley Giles: INV 009756
Note on BB25: Lesley Giles: INV 009975
Note on BC25: Lesley Giles: INV 010219 INV 010204
Note on BD25: Lesley Giles: 010437 010681 010680
Note on BE25: Lesley Giles: 010679
Note on BF25: Lesley Giles: 010896 010909 010894 010453 010895
Note on AU27: Natasha Worrall: #008347
Note on AV27: Natasha Worrall: 008701
Note on AW27: Lesley Giles: 008763
Note on AY27: Lesley Giles: 009174 009184 Grendon West BESSS
Note on AZ27: Lesley Giles: 009364 500 added instead of subtracted 4,000 seems to be double counted in Environmental Master Plan
Note on BA27: Lesley Giles: 009559 minus £1500 for environmental masterplan, added below 500 added instead of subtracted 4,493 seems to have been counted in Dec & Jan 09755
Note on BB27: Lesley Giles: INV 009976 minus Envi masterplan
Note on BD27: Lesley Giles: INV 010218 inv 010215 INV 010203
Note on BE27: Lesley Giles: 010435 010434 010433 010678 010676 010675 010674 010684
Note on BF27: Lesley Giles: 010888 010891 010893 010892 010889 010885
Note on AZ28: Lesley Giles: 009364 £1500 taken from Invoice 009559
Note on BA28: Lesley Giles: 009759 009755
Note on BB28: Lesley Giles: INV 009976
Note on BD28: Lesley Giles: INV 010215
Note on BE28: Lesley Giles: 010674 010677
Note on BF28: Lesley Giles: 010890 010885
Note on AT29: Natasha Worrall: #183204 - Grendon West BESS cost
Note on AY29: Lesley Giles: 604735
Note on BB29: Lesley Giles: 605126 605378
Note on BC29: Lesley Giles: 605552
Note on BD29: Lesley Giles: 605790 605791
Note on BE29: Lesley Giles: 010677
Note on BF30: Lesley Giles: 606464
Note on BB31: Lesley Giles: 680046025
Note on BE31: Lesley Giles: 680045888 680046029
Note on BF31: Lesley Giles: 680048386
Note on E32: Natasha Worrall: Includes examination costs
Note on F32: Natasha Worrall: Includes examination costs
Note on G32: Natasha Worrall: Includes examination costs
Note on J32: Lesley Giles: Assumed cost already included for examination
Note on AZ32: Lesley Giles: INV-731
Note on BD32: Lesley Giles: INV-856
Note on BE32: Lesley Giles: INV-992
Note on G35: Lesley Giles: includes costs for TCPA and fire technical note
Note on AY35: Lesley Giles: 680028957
Note on AZ35: Lesley Giles: 680033037
Note on BB35: Lesley Giles: 680036215
Note on BC35: Lesley Giles: 680041809
Note on BD35: Lesley Giles: 680043703
Note on BE35: Lesley Giles: 680045883
Note on BF35: Lesley Giles: 680048385
Note on L36: Lesley Giles: £3,420 already invoiced in April before PO was raised so deducted from Quote amount
Note on BD36: Lesley Giles: GHS/001
Note on AW37: Lesley Giles: 189251
Note on AZ37: Lesley Giles: 194702 GRENDON WEST BESS
Note on BB37: Lesley Giles: 198707
Note on BC37: Lesley Giles: 200151
Note on BC38: Lesley Giles: 07/03/2024
Note on BD39: Lesley Giles: INV 010214
Note on BE39: Lesley Giles: 010686
Note on F40: Natasha Worrall: Lesley, increased on 15.09.23 to include additional costs provided by Clarkson and Woods for Otters, NE DAS etc.
Note on I40: Lesley Giles: Quote V7 without revisions budget
Note on AY40: Lesley Giles: 83082 85421 Grendon West BESS
Note on AZ40: Lesley Giles: 83083
Note on BB40: Lesley Giles: 83085
Note on BC40: Lesley Giles: 83087
Note on BD40: Lesley Giles: 83088
Note on BE40: Lesley Giles: 83089
Note on H41: Lesley Giles: £10k for stage one assessment, stage two costs will be between £300-600k
Note on BC42: Lesley Giles: 30081954
Note on BD42: Lesley Giles: 30081301
Note on BF42: Lesley Giles: 30097330
Note on AY43: Lesley Giles: 604734
Note on AZ43: Lesley Giles: 30065917 Tetra tech?
Note on BB43: Lesley Giles: 605415
Note on BC43: Lesley Giles: 605551
Note on BE43: Lesley Giles: 606399
Note on BF43: Lesley Giles: 606641
Note on AY44: Lesley Giles: 009367
Note on AZ44: Lesley Giles: 009561
Note on BA44: Lesley Giles: 009758
Note on BC44: Lesley Giles: INV 010206
Note on BD44: Lesley Giles: 010443
Note on BE44: Lesley Giles: 010683
Note on BF44: Lesley Giles: 010900
Note on BB45: Lesley Giles: 709657
Note on BD45: Lesley Giles: 709758
Note on BE45: Lesley Giles: 709864
Note on BF45: Lesley Giles: 709926
Note on AY47: Lesley Giles: 6784485
Note on AZ47: Lesley Giles: 6792039
Note on BB47: Lesley Giles: 6804283
Note on BC47: Lesley Giles: INV 6814939
Note on BD47: Lesley Giles: GP/700871/07000
Note on BE47: Lesley Giles: 6831181
Note on BF47: Lesley Giles: 6834978
Note on AV48: Lesley Giles: Solar 12521 BESS 12522
Note on AX48: Lesley Giles: 12681
Note on AY48: Lesley Giles: 12746
Note on AZ48: Lesley Giles: 12878
Note on BA48: Lesley Giles: 12879
Note on BB48: Lesley Giles: £37,374.09 is invoice 13013
Note on BC48: Lesley Giles: 13110 13111 13057
Note on BD48: Lesley Giles: 13201 13230
Note on BE48: Lesley Giles: 13244
Note on AX49: Lesley Giles: 12681
Note on AZ49: Lesley Giles: 12878 12877 12880 Grendon West BESS
Note on BA49: Lesley Giles: 12879
Note on BB49: Lesley Giles: £37,374.09 is invoice 13013
Note on BA50: Lesley Giles: 12938
Note on BB50: Lesley Giles: 13057
Note on BD50: Lesley Giles: 13202
Note on BE50: Lesley Giles: 13230
Note on AV52: Lesley Giles: INV-2307-172
Note on AX52: Lesley Giles: INV-2309-135
Note on AY52: Lesley Giles: INV-2310-083
Note on AZ52: Lesley Giles: INV-2311-041
Note on BB52: Lesley Giles: INV-2402-185
Note on BC52: Lesley Giles: INV-2403-168
Note on BD52: Lesley Giles: INV-2403-169
Note on BE52: Lesley Giles: inv-203-169
Note on BF52: Lesley Giles: INV-13000599
Note on BD53: Lesley Giles: 1548
Note on BE53: Lesley Giles: 1550
Note on BB54: Lesley Giles: SI404421
Note on BC54: Lesley Giles: SI404042
Note on BE54: Lesley Giles: SI405785
Note on BF54: Lesley Giles: S1406225
Note on D57: Natasha Worrall: Use WB&C
Note on H57: Natasha Worrall: Use WB&C
Note on D63: Natasha Worrall From chat with Eve
Note on F63: Lesley Giles: £1,813 HMLR data for cable route
Note on AU63: Lesley Giles: UAI-24-10537
Note on AX63: Lesley Giles: UAI-24-10963
Note on AY63: Lesley Giles: UAI-24-11214
Note on AZ63: Lesley Giles: UAI-24-11582
Note on BA63: Lesley Giles: UAI-24-11879
Note on BB63: Lesley Giles: UAI-24-12437
Note on BC63: Lesley Giles: UAI-24-13028
Note on BD63: Lesley Giles: UAI-24-13304
Note on BE63: Lesley Giles: UAI-24-13644
Note on BF63: Lesley Giles: UAI-24-13921

## Branxton
Branxton Budget Cost | [8 empty] | Grid App | [38 empty] | PRE-APP | [5 empty] | SUBMITTED | [5 empty] | DECISION
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Variance (remainind spend) | PO Raised? | Consultant | time axis 2021-09-01 to 2026-05-01
Grid | DNO Application |  | 60000 | 133212.5 | 133212.5 |  |  |  | 2022-05-01: 72650; 2024-06-01: 60562.5
| Consultant |  | 2000 | 1800 | 1800 |  |  |  | 2022-04-01: 1800
| Deposit/security |  | N/A | 0 | 2400000 |  |  |  | 2023-09-01: 1200000; 2024-03-01: 1200000; 2025-03-01: 3293040; 2026-03-01: 2093040
Lease/Option |  |  | 62000 |  | 0
Planning Consultant | David Bell Planning | 0 | 53700 | 0 | 0
Pre-app Fee |  |  | 10000
Planning Application Fee |  |  | 548000 |  | 0
Planning Studies | Planning Feasibility Study (PO000747) |  | 5500 | 5500 | 5500 | 0 | Item fully billed | David Bell Planning | 2023-10-01: 500; 2024-07-01: 5500
Project Management and EIA | Project management |  | 12125 | 6000 | 0 |  |  | ITPE | 2023-10-01: 2400
EIA Screening inputs
| EIA Scoping |  | 2980 |  |  |  |  | ITPE
| Gatecheck report |  | 1260 |  |  |  |  | ITPE
| EIA report and PM review |  | 8640 |  |  |  |  | ITPE
Ecology | Ecology PM and input to EIA screening/scoping |  | 3380 |  |  |  |  | ITPE
| Ecology survey and report (Option 1) |  | 4440 |  |  |  |  | ITPE
| Ecology survey and report (Option 2) |  | 3640 |  |  |  |  | ITPE
| EIA Biodiversity Chapter, HRA Stage 1, OBEMP |  | 11195 |  | 0 |  |  | ITPE
| SPP |  | 1705 |  | 0 |  |  | ITPE
| Outline BMP |  | 2130 |  | 0 |  |  | ITPE
| BNG |  | 1705 |  | 0 |  |  | ITPE
Agricultural land | Land Capability for Agriculture (LCA) (Option 1) |  | 3100 |  | 0 |  |  | LRA
| Land Capability for Agriculture (LCA) (Option 2) |  | 3900
Flood Risk | Flood Risk and Drainage Assessment and FMP |  | 6300 |  | 0 |  |  | Gondolin
| Option 1 or Option 2 constraints |  | 1200
| Earthworths |  | 2250
| ES Chapter (if required) |  | 5600
Transport | Transport Statement and CTMP |  | 3950 |  | 0 |  |  | Pell Freischmann
| Site visit and traffic survey data |  | 845
| Abnormal Indivisible Load (AIL) assessment |  | 3650 |  | 0
Landscape and visual | LVIA inc. photomontages |  | 12215 |  | 0 |  |  | Stephenson Halliday
| Site options review (Options 1 and 2) | 2880 | 2880
| ES Chapter (if required) | 780 | 780
Heritage and Archaeology | Heritage and Archaeology DBA |  | 5376.02 |  | 0 |  |  | Headland
| Geophysical survey (Option 1) |  | 6240 |  | 0 |  |  | Headland
| Geophysical survey (Opition 2) |  | 13250
| ES Chapter (if required) |  | 2832 |  |  |  |  | Headland
Noise | Noise survey (72 hr) and report (Options 1 and 2) |  | 7450 |  | 0 |  |  | Tetra Tech
| ES Chapter and EIA Scoping (if required) | 2800 | 3100
Topographical survey | Topographical survey |  | 7175 |  | 0 |  |  | Cain Tech
Arboricultural | Arboricutural Survey, AIA, AMS and TPP |  | 1470 |  | 0 |  |  | Caledon Tree Surveys
Survey for Option 2 land
Battery Safety | OBSMP |  | 4560 |  | 0 |  |  | ARC / Paul Gregory
CEMP | Outline CEMP |  | 2340 |  | 0 |  |  | ITPE
Contamination | Geo-Environmental Phase I |  | 3170 |  | 0 |  |  | ITPE
| Input to EIA Screening and Scoping |  | 1490
Socio-economic | Socio-economic report |  | 5720 |  | 0 |  |  | MKA c/o ITPE
Comms/PR | Comms/PR |  | 31080 |  | 0 |  |  | Kane Partnership
Land | Cable Routes |  |  |  | 0 |  |  | ???
Utilities | Utilites Survey |  | 1582.53 |  |  |  |  | Centremaps Ltd
Post-submission | Planning |  | 13500 |  |  |  |  | David Bell Planning
| Other reports |  | 25000 |  | 0 |  |  | Various
Contingency | 10% of planning costs | 646 | 85240.555 | [5 empty] | 2024-06-01: 0; 2024-07-01: 550; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Third Party Wayleaves |  |  | 0 |  | 0
Satisfaction of pre-commencement planning conditions |  |  | 0 |  | 0
Transaction Cost | to date (admin, accounts etc) |  | 0 |  | 0
Total |  | 7106 | 1061646.105 | 146512.5 | 2540512.5 |  |  |  | 2024-06-01: 60562.5; 2024-07-01: 6050; 2024-08-01: 0; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 3293040; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 2093040; 2026-04-01: 0; 2026-05-01: 0
Installed capacity/MW | 1000
Total/MW |  | 7.106 | 1061.6461 | 146.5125 | 2540.5125
0
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated - TBC
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: East Lothian Council 1https://www.eastlothian.gov.uk/info/210547/planning_and_building_standards/12775/discretionary_planning_charges_- _pre_application
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £264k non-EIA £548k EIA
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TBC with ITPE as it refers to contract mgt which is not required. PM (£9290), Site visit (£1300), pre app (£550) and design workshop (£985).
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ITPE costs for Scoping, although this could be David Bell. TBC.
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ITPE costs for GC report, although this could be David Bell. TBC
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: EIA report including front end and concluding chapters, PM review (£7,210) plus NTS (£1430)
Note on E17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task management £1270, input to EIA screening £740, input to EIA scoping £1,370
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Headland: Option 1 area calculated at 14.54 ha (£6,240) and option 2 area calculated at 41.5ha (£13,250)
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes survey, report, 2 x meetings and post-sub liaison with LPA
Note on E50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fee includes £17,600 (total of 22 days) suggested contingency budget of £7,200 for 3 months, Website £4,280, Expenses £2,000
Note on C51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cable route being delivered by SPEN. Consider including route within RLB?
Note on E52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Option 1 and 2 land
Note on E53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DB recommended £1,500 per month over a 9 month determination period (i.e. £13,500)
Note on E54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: An indicative figure to allow for potential scheme changes and updates to consultants' reports.

## Lullington (Resubmission)
Lullington Resubmission Budget Cost | [10 empty] | PRE-APP |  |  |  | SUBMITTED | [9 empty] | DECISION
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01
Grid | DNO Application |  | 0 |  | 0
| Consultant |  | 0 |  | 0
| Deposit/security |  | 0 |  | 0
Lease/Option |  |  | 0 |  | 0
Legal/Coorporate |  |  | 0 |  | 0
Planning Consultant |  |  | 0 |  | 0
Planning Application Fee |  |  | 0 |  | 0
Planning Studies | Heritage Statement |  | 0 |  | 0
| ALC Classification |  | 0 |  | 0
| Topographical Study |  | 0 |  | 0
| Flood Risk Assessment |  | 0 |  | 0
| Geophysical Survey |  | 0 |  | 0
| Trial Trenching |  | 0 |  | 0
| Arboricutural Survey |  | 0 |  | 0
| Highways Survey |  | 0 |  | 0
| Ecological Survey |  | 0 |  | 0
| LVIA |  | 0 |  | 0
| CTMP |  | 0 |  | 0
| Noise |  | 0 |  | 0
| 3D model |  | 0 |  | 0
| Glint/Glare |  | 0 |  | 0
| EIA |  | 0 |  | 0
| Planning Performance Agreement |  | 0 |  | 0
Contingency | 10% of planning costs |  | 0 |  | N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  |  | 0 |  | 0
Satisfaction of pre-commencement planning conditions |  |  | 0 |  | 0
Transaction Cost | to date (admin, accounts etc) |  | 0 |  | 0
Total |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installed capacity
Total/MW |  |  | #DIV/0! | #DIV/0! | #DIV/0!

## Whitehouse
Whitehouse Budget Cost | [12 empty] | PRE-APP | [5 empty] | SUBMITTED | [5 empty] | DECISION
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01
Grid | Application |  | 28250 |  | 28250 |  | 2023-06-01: 28250
| Consultant |  | 2000 |  | 2000 |  | 2023-06-01: 2000
| Deposit/security |  | 896400 |  | 896400 |  | 2023-06-01: 597600; 2024-03-01: 298800
Lease/Option |  |  | 0 |  | 0
Legal/Coorporate |  |  | 0 |  | 0
Planning Consultant |  |  | 0 |  | 0
Planning Application Fee |  |  | 0 |  | 0
Planning Studies | Planning Feasibility Study | 33100 | 33100 | 33100 | 0 | David Bell Planning | 2023-07-01: 4109.65; 2023-08-01: 1920; 2023-09-01: 2595
| Heritage Statement |  | 0 |  | 0
| ALC Classification |  | 0 |  | 0
| Topographical Study | 26500 | 26500 | 26500 | 26500 | Malcolm Hughs Land Surveyor
| Further Initial Flood Work | 3500 | 3500 | 3500 | 3500 | Pell Frischmann | 2023-12-01: 3500
| Flood Risk Assessment |  | 0 |  | 0
| Geophysical Survey |  | 0 |  | 0
| Trial Trenching |  | 0 |  | 0
| Arboricutural Survey |  | 355 |  | 355 |  | 2023-11-01: 355
| Highways Consultation Work | 355 | 355 | 355 | 0 | Pell Frischmann
| Highways Survey |  | 0 |  | 0
| Archaeological Walkover | 2475 |  | 2475
| Ecology | 22565 |  | 22565 | 6047.5 | ITPEnergised | 2024-01-01: 3047; 2024-02-01: 1033.5; 2024-03-01: 1967; 2024-04-01: 5497.8; 2024-06-01: 2440.88
| First Otter & Vole Survey | 3265 | 3265 | 3265 | 2862 | ITPEnergised | 2023-10-01: 2862; 2023-11-01: 403
| LVIA |  | 0 |  | 0
| CTMP |  | 0 |  | 0
| Further initial Noise modelling work | 4230 | 4230 | 4230 | 4230 | ITPEnergised | 2023-12-01: 4230
| Noise |  | 0 |  | 0
| 3D model |  | 0 |  | 0
| Glint/Glare |  | 0 |  | 0
| Utilities Survey | 1825 | 1825 |  | 1825 | Centremaps Ltd | 2023-10-01: 1825
| EIA |  | 0 |  | 0
| Cable Routes | 20000 |  |  |  | Dalcour Maclaren
| Planning Performance Agreement |  | 0 |  | 0
Contingency | 10% of planning costs | 11781.5 | 0 |  | N/A |  | 0 | 410.965 | 192 | 259.5 | 468.7 | 75.8 | 773 | 304.7 | 103.35 | 196.7 | 549.78 | 0 | 244.088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  |  | 0 |  | 0
Satisfaction of pre-commencement planning conditions |  |  | 0 |  | 0
Transaction Cost | to date (admin, accounts etc) |  | 0 |  | 0
Total |  | 129596.5 | 999780 | 95990 | 971969.5 |  | 627850 | 4520.615 | 2112 | 2854.5 | 5155.7 | 833.8 | 8503 | 3351.7 | 1136.85 | 300963.7 | 6047.58 | 0 | 2684.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installed capacity | 249
Total/MW |  | 520.4679 | 4015.1807 | 385.502 | 3903.492
Note on J11: Natasha Worrall: 210/2
Note on K11: Natasha Worrall: 210/1
Note on L11: Natasha Worrall: 210/3 (VAT excl.)
Note on D23: Samantha Jones: this includes some survey work so need to confirm with ITP - tbc

## New Deer
New Deer Budget Cost | [7 empty] | Grid App | [38 empty] | PRE-APP | [5 empty] | SUBMITTED | [5 empty] | DECISION
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | PO number | Consultant | time axis 2021-09-01 to 2026-05-01
Grid | Application | 33540 | 50000 | 34950 | 34950 |  |  | 2021-09-01: 34950
| Consultant |  | 2000 | 2000 | 2000 |  |  | 2021-09-01: 2000
| Deposit/security | 603846 | 0 | 0 | 1225696.656 |  |  | 2023-03-01: 277247.5; 2023-09-01: 247301.6; 2024-03-01: 701147.556; 2024-09-01: 0; 2025-03-01: 0; 2025-09-01: 0; 2026-03-01: 4049.352
Lease/Option |  |  | 62000 |  | 0
Planning Consultant |  | 47706 | 50700 | 0 | 0 |  | David Bell Planning
Planning Application Fee |  | 105000 | 180000 |  | 0 |  | ECU
Pre-app fee | Pre-app fee to ECU and LPA |  | 7200 |  | 0 |  | LPA
Planning Feasibility | Desktop Planning Assessment | 500 | 500 | 500 | 0 |  | Entrust | 2023-10-01: 500
| Planning Feasibility Study | 2400 | 2400 | 2400 | 0 |  | David Bell Planning | 2023-10-01: 2400
Project Management | Project Management |  | 13390 | 13390 | 664.5 | PO000936 | ITPE | 2024-08-01: 664.5
Ecology | Ecology surveys and PM | 22000 | 3320 | 3320 | 2830 | PO000774 | ITPE | 2024-08-01: 2830
| Ecology Report and data |  | 2670 | 2670 | 0 | PO000781 | ITPE
| SPP |  | 1705 |  | 0 | PO000937 | ITPE
| Outline BMP |  | 2130 |  | 0 | PO000939 | ITPE
| BNG |  | 1705 |  | 0 | PO000940 | ITPE
| Cable route walkover and updates to reports |  | 5470 |  | 0 | TBC | ITPE
Agricultural land | ALC | 3000 | 3750 |  | 0 | PO000942 | LRA
Flood Risk | Flood Risk and Drainage Assessment and FMP | 8000 | 4950 |  | 0 | PO000943 | Gondolin
Transport | Transport Statement and CTMP | 11000 | 6650 |  | 0 | PO000945 | Pell Frischmann
| Abnormal Indivisible Load (AIL) assessment |  | 3750 |  | 0 | TBC | Pell Frischmann
Landscape and visual | LVIA inc. photomontages | 15000 | 12500 |  | 0 | PO000946 | Pegasus
Heritage and Archaeology | Heritage and Archaeology DBA | 8000 | 5631 |  | 0 | PO000955 | Headland
0
Noise | Noise survey (72 hr) plus meetings | 8000 | 6850 |  | 0 | PO000941 | Tetra Tech
Topographical survey | Topographical survey | 4000 | 5600 |  | 0 | PO000944 | Cain Tech
| Cable route survey |  | 1250 |  | 0 | TBC | Cain Tech
Arboricultural | Arboricutural Survey, AIA, AMS and TPP | 6000 | 1370 |  | 0 | PO000956 | Caledon Tree Surveys
| Cable route survey |  | 1270 |  | 0 |  | Caledon Tree Surveys
Battery Safety | OBSMP | 3000 | 4560 |  | 0 | TBC | ARC
CEMP | Outline CEMP | 10850 | 2320 |  | 0 | PO000948 | ITPE
Contamination | Geo-Environmental Phase I | 6000 | 3310 |  | 0 | PO000947 | ITPE
Socio-economic | Socio-economic report | 3000 | 5720 |  | 0 | PO000949 | MKA c/o ITPE
Comms/PR | Comms/PR | 50000 | 23080 |  | 0 | TBC | Kane Partnership
Land Referencing | Cable Routes |  | 16350 |  | 0 |  | Dalcour McLaren
| Cable route landowner payments |  |  |  | 0
| Cable route legals |  | 7500 |  | 0
Utilities | Utilites Survey |  | 940 |  | 940 | PO000911 | Centremaps Ltd | 2024-08-01: 940
Post-submission | Planning |  | 13500 |  | 0 | TBC | David Bell Planning
| Other reports |  | 25000 |  | 0 |  | Various
Contingency | 10% of planning costs |  | 42704.1
Third Party Wayleaves |  | 15000 | [5 empty] | 2024-07-01: 0; 2024-08-01: 443.45; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-04-01: 0; 2026-05-01: 0
Discharge of pre-commencement planning conditions |  | 15000
Transaction Cost | to date (admin, accounts etc) | 15000
Total |  | 358456 | 583745.1 | 59230 | 1267081.156 |  |  | 2024-07-01: 0; 2024-08-01: 4877.95; 2024-09-01: 0; 2024-10-01: 0; 2024-11-01: 0; 2024-12-01: 0; 2025-01-01: 0; 2025-02-01: 0; 2025-03-01: 0; 2025-04-01: 0; 2025-05-01: 0; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 4049.352; 2026-04-01: 0; 2026-05-01: 0
Installed capacity/MW | 500
Total/MW |  | 716.912 | 1167.4902 | 118.46 | 2534.1623
Additional item Unlikely to be required | Sub-Item | Budget (£) | Comment |  |  |  | Consultant
Archaeology | Geophysical Survey (£9,130) | 10000 | Heritage consultants advised not required. |  |  |  | Cotswold / Headland
| Trial Trenching | 30000 | Trial trenching likely required post-determination |  |  |  | Cotswold / Headland
EIA | EIA | 14000 | Assuming not EIA but confirmed by EIA SO. |  |  |  | ITPE?
0
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PM fee - check no overlap with ITPE.
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £180k non-EIA but £336k for EIA
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: £4920 plus design workshop fee £985, EIA Screening figures £555 and Environmental Supporting Information Report ESIR £6,930.
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes: PEA Survey inc. PRA (bats), badger, otter and water vole (£2,570) and PM (£750)
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ecology report (£2,420) and data search (£250)
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allows for amendments following review by LPA if required (£170)
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allows for amendments following review by LPA if required (£170)
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated cost. TBC
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May not be required
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tetra tech - £5,970.00
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on purple route
Note on E36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fee includes £9600 (total of 12 days for 3 months) suggested contingency budget of £7,200 for 3 month, Website £4280, Expenses £2000
Note on C41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DB recommended £1,500 per month over a 9 month determination period (i.e. £13,500)
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: An indicative figure to allow for potential scheme changes and updates to consultants' reports.

## East Pye (Long Stratton)
Cost to date
Long Stratton Budget Cost | time axis 2024-04-01 to 2027-11-01
[16 empty] | Month |  | 2026-03-01: App submitted
| Item | Consultant | Sub-Item | Original Budget (£) | Initial Quote Instructed (£) | Updated Quote (July 24) | Invoices and forecast total (£) | Pre-submission total (£) | Post-submission total (£) | Variance | Quote 1 | Quote 2 | Quote 3 | Quote 4 | Total Invoiced Amount (£)/ As of last month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
| Grid |  | NGET Application | 67650 | [11 empty] | Month 1: 67650; Month 2: -36664.74
|  | Omnia | Consultants | 50000 | 49664 | [10 empty] | Month 1: 1600
|  |  | Deposit/security | [12 empty] | Month 1: 725039.42; Month 2: 752232.48; Month 3: 303614.876
|  |  | Auxiliary connection applications | 3660
Network Rail BAPA
| Lease/Option |  |  | 150000
| Planning Application Fee |  | Performance Agreements | 170000
|  |  | Planning Inspectorate | 725000
| Planning Consultant and EIA | Stantec | Stage 1 | 319829.69 | 319829.69 | [9 empty] | 34116.2 | Month 6: 34116.2
|  | Stantec | Stage 2 | 141419.4
|  | Stantec | Stage 3 | 176894.98
|  | Stantec | Stage 4 | 437184.36
| Pinsent Masons Project Management | Pinsent Masons |  | 100000
| Planning Studies | GHC | Heritage Statement | 100000 | 50000 | [5 empty] | 43250
|  |  | Areial Photoograhy | 20000
|  | Amet Property | ALC Classification | 50000 | 34200
|  | Tony | Agricultural circumstances | 45000
|  | Survey Solutions | Topographical Study | 75000 | 58050
|  | Stantec | Flood Risk Assessment | 36495 | 36495
4 |  | Magnitude | Geophysical Survey | 200000 | [10 empty] | 150428 | Month 3: 96363; Month 4: 54065
|  |  | Geophysical Survey (CR) | 50000
|  | TBC | Trial Trenching | 1000000
|  | Stantec | Air Quality | 12310.09
|  | Stantec | Minerals and deposits | 5905.35
|  | Stantec | Arboricultural Survey | 35474.83
|  | Stantec | Highways Survey | 40030.83
|  |  | Abnormal loads | 45000
|  | Stantec | Ecological Survey | 250000 | 187047 | 250000
|  | Stantec | Bats (Activity) | 151553
|  | Stantec | Invertebrate scoping survey | 14067
|  | Stantec | Ecology (cable route) | 40000
|  |  | Environmental Masterplan | 32000
|  | Stantec | LVIA | 217926.99
|  |  | CTMP | 10979.43
|  |  | Noise | 59658.2
|  |  | Socio -economic and land use | 12141.65
|  |  | Funding Statement | 0
|  |  | Glint/Glare | 54520
|  |  | Outline CEMP | 16544.76
|  |  | Outline Decomm Mgt Plan | 5632.72
|  |  | Outline Soils Mgt Plan | 3946.92
|  |  | Outline OEMP | 10422.39
|  | Pinsent Masons | Legal DCO drafting | 450000
|  |  | Examination phase costs | 105000
|  | Counter Context | Consultation / PR / website | 400000
|  | Humbeat | Statement of Need | 20000
|  |  | Cable route utilities search | 17782
|  |  | Electromagnetic fields | 3995
|  |  | Contaminated land | 18031.27
|  |  | Climate change | 5461.79
|  |  | Cable route engineering design | 41636
|  |  | Construction timescales/waste/worker numbers | 4300
|  |  | Protective provisions 3rd party legal costs | 90000
|  |  | Co-operation agreement | 6450
|  |  | Other - Protracted red line adjustments | 50000
|  |  | DAS Services | 75000
|  |  | Input from Battery Safety Expert (OBSMP and Examination) | 50000
| Professional services | Dalcour Maclaren | Land referencing | 120000
|  | Dalcour Maclaren | Land Agency | 148500
|  |  | Cable route landowner payments | 561000 | [11 empty] | App submitted 42: 220000
|  |  | Cable route legals | 113000 | [11 empty] | App submitted 42: 13200
| Contingency |  | 10% of planning costs | 500000
| Satisfaction of pre-commencement planning conditions |  |  | 0
| Accounting, admin, prof. fees & bank charges |  |  | 30000
| Third Party Wayleave |  |  | 0
| Transaction Cost |  |  | 30000
| Total |  |  | 7776403.65
| Installed Capacity |  | 500
| Total/MW | [5 empty] | 0
|  |  |  | 6648903.65 | [11 empty] | Month 14: Spend to date; Month 15: 0
|  |  | Deal Sheet budget | #REF!
0
|  |  | Disbursements | #REF!
60500.9365
planning costs
FALSE
Note on E10: Samantha Jones: 148k taken from completion statement
Note on M13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ARUP
Note on L18: Samantha Jones: GHC
Note on D20: Samantha Jones: Soil and Agri
Note on D27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Doesn't include full air quality assessment
Note on G32: Samantha Jones: Update allows for PEA results and additional land

## The Droves (Kings Lynn)
Cost to date
The Droves (Kings Lynn) Budget Cost |  | DWD/LDA - Planning and EIA Consultancy | time axis 2024-05-01 to 2027-11-01
[15 empty] | Month |  |  | 2026-03-01: App submitted
Item | Consultant | Sub-Item | Original Budget (£) | Initial Quote Instructed (£) | Updated budget (£) July 24 | Invoices and forecast total (£) | Pre-submission total (£) | Post-submission total (£) | Variance | Quote 1 | Quote 2 | Quote 3 | Quote 4 | Commissioned consultant work | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
Grid |  | NGET Application | 81180 | [11 empty] | Month 1: 67650
|  | Consultants | 44670 | [11 empty] | Month 1: 800
|  | Deposit/security | 1800000 | [11 empty] | App submitted 32: 2160.78; App submitted 38: 6482.316 |  | 20798.508
|  | Auxiliary connection applications | 3600
Lease/Option |  |  | 157693
Planning Application Fee |  | Planning Performance Agreements | 170000
|  | Planning Inspectorate | 724500
Planning Consultancy and EIA input | DWD | Stage 1; DCO Coordination and Management | 53420
|  | Stage 2; Inception and Pre-Application | 22420
|  | Stage 3; Scoping and Non-Stat and Stat Consultation | 76800
|  | Stage 4; Preparation of application and submission | 97620
|  | Stage 5; Examination and Decision | 99800
|  | All EIA, ES and PIER related inputs including scoping and consultation | 365010
DWD Project Management |  |  | 96120
Planning Studies up to Submission | GHC | Cultural Heritage | 31650
| Kernon | ALC Survey (detailed) | 28500
| Kernon | Soil Management Plan | 3000
| Kernon | Agricultural circumstances/Farm Assessment and input into scoping, PIER and ES | 16400
|  | Topographical Study | 24500
| Velocity | Flood Risk Assessment | 48900
| Headland | Geophysical Survey | 155045
|  | Trial Trenching | 750000
| Hoare Lee | Air Quality | 25250
|  | Minerals and deposits | 5905.35
| Tyler Grange | Arboricultural Survey | 18000
| Velocity | Highways Survey | Covered under TA and CTMP
| Velocity | Abnormal loads | Covered under TA and CTMP
| Aspect | Ecology Surveys and Assessment | 186980
|  | eDNA | 12450
| DTA | Topographical Study | 73605
| LDA | Masterplanning | 192780
| LDA | Landscape and Visual Assessments | 94395
| Velocity | Transport Assessment inlcuding CTMP | 75000
| LDA | Amenity and Recreation Assessment | 27720
| LDA | Residential Visual Amenity Asssessment | 23415
| Hoare Lee | Noise | 21300
| Volterra | Social Economic/Health | 136780
| IGP | Funding Statement | 0
| Pager Power | Glint/Glare | 52445
|  | Outline CEMP | 6500
|  | Outline OEMP | 6500
|  | Outline DEMP | 6500
| Pinsent Mason | Legal DCO drafting | 450000
|  | Examination phase costs | 100000
| Copper Consulting | Consultation / PR / website | 343000
| Si Gillet | Statement of Need | 5500
|  | Utilities search | 0
|  | Electromagnetic fields | 3995
|  | Contaminated land | 18031.27
| Bueno Vista | Climate change | 5461.79
| Viking | Construction timescales/waste/worker numbers | 4300
|  | SEUK NSIP Membership | 30000
|  | Protective provisions 3rd party legal costs | 30000
|  | Other - Protracted red line adjustments | 50000
|  | DAS Services | 75000
| Pual Gregory | Other - input from Battery Safety Expert (OBSMP and Examination) | 50000
Professional services |  | Land referencing (WSP) | 49553
Contingency |  | 10% of planning costs | 500000
Satisfaction of pre-commencement planning conditions |  |  | 0
Accounting, admin, prof. fees & bank charges |  |  | 30000
Third Party Wayleave |  |  | 0
Transaction Cost |  |  | 30000
Total |  |  | 7591194.41
Installed Capacity | 500 | 500
Total/MW |  |  | 15182.3888 |  | 0 | 0
[28 empty] | Spend to date | 0
|  | Deal Sheet budget 19/03/24 |  |  |  | 3904899
|  | Difference to total: |  |  |  | 3904899
7591194.41
7091194.41
Disbursements
26221.74
-500000
7591194.41
|  | Excluding Grid | 5791194.41
11582.3888
Note on E8: Harman Sond: As per the UK Grid Oveveiw/steer from Sam A. Not included in budget
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Swap out with Paul Gajos if not using on any other project. His fee is £31,650
Note on D21: Samantha Jones: Soil and Agri

## Grange (Stallingborough)
STALLINGBOROUGH
Item | Sub-Item | Consultant | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) |  | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01
Grid | Application |  |  | 28193.62 |  | 67650 | 2023-10-01: -39456.38
| Consultant |  |  | 0
| Deposit/security |  |  | 0
Lease/Option | Land Option |  |  | 0
| Cable route legals |  |  | 0
Legal/Coorporate |  |  |  | 0
Planning Consultant |  |  |  | 0
Screening Opinion | Screening Opinion Request |  | 0 | 0 | 0
| Landscape Assessment | AWScape Ltd | 5000 | 0 | 5000
| Ecological Assessment | Riverdale Ecology | 2600 | 0 | 2600
Pre-Application Consultation |  |  |  | 0
| Media relations, community consultation | Grasshopper | 45000 | 45000 | 45000 |  | 8745 | 1525 | 575 | 500 | 5355 | 15154.39 | 16408.81 | 5850 | 3390
| Community Consultation Phase 2 |  | 20000 | 0
Planning Application | Fee |  | 195423 | 0 | 195423
| Planning performance agreement |  |  | 0
Planning Application Technical Reports and Studies |  |  |  | 0
| Technical Design -H&S and Environment Compliance | DNV | 34000 |  | 34000
| Topographical Survey | ABOVE Surveying | 13500 | 9180.5 | 13500 |  | 2024-01-01: 9180.5
| LVIA, LEMP, Photomontages | AWScape Ltd | 23000 | 0 | 23000
| CTMP | Rappor | 5500 | 3610 | 5500 |  | 2024-01-01: 3610
| Archaeology Desk Based Assessment | Headland | 3800 | 4495.2 | 3800 |  | 2024-04-01: 4495.2
| Geophysical Survey | Headland | 50000 | 49310 | 50000 |  | 2024-01-01: 40460; 2024-04-01: 8850
| Heritage Assessment | Cotswold Archaeology | 2800 | 2895 | 2800 |  | 2024-02-01: 2895
| Heritage Assessment Report Update | Cotswold Archaeology | 2000
| ALC Survey | AMET Property | 11000 | 14425.75 | 11000 |  | 2024-04-01: 14425.75
| ALC Report | Kernon Countryside Consultants | 7000 |  | 7000
| Agricultural Viability Assessment | Kernon Countryside Consultants | 4000 | 0 | 4000
| Outline Soil Management Plan | Kernon Countryside Consultants | 1500 |  | 1500
| Glint and Glare | Wardell Armstrong | 4700 | 0 | 4700
| Noise | Wardell Armstrong | 5350 | 0 | 5350
| Flood Risk Assessment | JBA Associates | 2150 | 0 | 2150
| SUDS | JBA Associates | 5800 | 0 | 5800
| Ecology and surveys | Riverdale Ecology | 33092 | 0 | 33092
0
Contingency | 10% of planning costs |  | 35677 | 0 |  |  | 874.5 | 152.5 | 57.5 | 50 | 5860.55 | 1804.939 | 1640.881 | 3362.095 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Satisfaction of pre-commencement planning conditions |  |  |  | 0
Total |  |  | 512892 | 157110.07 | 455215 |  | 9619.5 | -37778.88 | 632.5 | 550 | 64466.05 | 19854.329 | 18049.691 | 36983.045 | 3729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installed capacity
Total/MW

## Light Valley S (Monk Fryston)
| 7965266.55 | Total Budget (Excl contingency & Grid) | [83 empty] | Start pre-exam |  |  |  |  | start exam
Monk Fryston Budget Cost | 7965802 | Total Forecast (Excl contingency & Grid)
| 2070540 | Total Grid | [11 empty] | 2021 | [12 empty] | 2022 | [18 empty] | 2023 | [12 empty] | 2024 | [12 empty] | 2025 | [12 empty] | 2026 | [12 empty] | 2027
[59 empty] | 0 | 0 | 0 | 24900 | 194422 | 66545 | 44687 | 116406.38 | 329250.6 | 202326 | 346037 | 315275 | 1639848.98
Item | Phase / Sub-category | Description | Consultant / Supplier | Status | Purchase Order No | PO Value / Paid | Revised budget | Invoiced to end last year | Invoiced / paid this year (end June) | Forecast / remaining | Total Forecast / Invoiced | Check | Variance | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2021 Total | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2022 Total | 2023 Total | Forecast 2024 | Forecast 2025 | Forecast 2026 | Forecast 2027 | Forecast 2028 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2023 Total | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2024 Total | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2025 Total | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2026 Total | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2027 Total | 2028-01-01
Land Assembly |  | IGP Agent's fees |  |  |  |  | ? | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Landowner - Escrick Agent's fees | ?? For escrick |  |  | 15000 | 15000 | 15000 | 0 | 0 | 15000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 15000 |  | 15000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Legal | Landowner - Escrick Legal fees | Greys for Escrick |  |  | 18000 | 18000 | 18000 | 0 | 0 | 18000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 18000 |  | 18000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Escrick Searches |  |  |  |  | ? | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Landowner - Hartleys Agent's fees |  |  |  |  | ? Agent used? | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Legal | Landowner - Hartleys Legal fees |  |  | 676 | 27000 | 27000 | 0 | 27000 | 27000 | 27000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 27000 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  |  |  |  | 27000 | [7 empty] | 27000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Legal | IGP Legal fees - Hartleys | Walker Morris |  |  |  | ? | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Legal | Hartley Searches |  |  |  | 522 | 522 | 0 | 522 | 522 | 522 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 522 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  |  |  |  | 522 | [7 empty] | 522 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Legal | CoT work | Walker Morris |  |  |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 20000 |  |  |  | 20000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Option Fee | Option Fees - Initial Fee. Payable year 4 |  |  |  |  | 328596 | 0 | 0 | 328596 | 328596 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 133967 | 158806 | 35823 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [9 empty] | 91647 |  | 42320 | 133967 |  |  |  | 46988 | [6 empty] | 111818 |  | 158806 | 35823
| Option Fee | Option Fees - Extension | [5 empty] | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Option Date variations. Legal fees |  |  |  |  | 15000 | 0 | 0 | 15000 | 15000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 5000 | 10000 | 0 | 0 | 0 | [12 empty] | 0 | [11 empty] | 5000 | 5000 | 10000 | [11 empty] | 10000 | [12 empty] | 0 | [12 empty] | 0
|  | Legal fees - assignment of Broxholme | [5 empty] | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Pre-emptive landscaping |  |  |  |  | 80000 | 0 | 0 | 80000 | 80000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 6000 | 47000 | 22000 | 5000 | 0 | [12 empty] | 0 | [8 empty] | 3000 |  | 3000 |  | 6000 | 7000 |  |  | 40000 | [8 empty] | 47000 |  |  |  | 22000 | [8 empty] | 22000 |  |  |  | 5000 | [8 empty] | 5000
[8 empty] | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
Property Total | [6 empty] | 504118 | 33000 | 27522 | 471118 | 504118 | 0 | [13 empty] | 0 | [12 empty] | 0 | 33000 | 58522 | 57000 | 155967 | 163806 | 35823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 0 | 33000 | 0 | 0 | 0 | 0 | 27522 | 0 | 0 | 0 | 23000 | 0 | 3000 | 5000 | 58522 | 17000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57000 | 0 | 0 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 91647 | 0 | 42320 | 155967 | 0 | 0 | 0 | 51988 | 0 | 0 | 0 | 0 | 0 | 0 | 111818 | 0 | 163806 | 35823
Planning & DCO Management |  | Stage 1; Mobilisation, Surveys Scoping Optioneering, Non Statutory Consutation input | Arup |  | 568 | 84900 | 84900 | 0 | 54900 | 84900 | 84900 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 84900 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  |  |  | 9900 | 25000 |  | 0 | 20000 | 20000 | 10000 |  |  | 84900 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Stage 2; Statutory Consultation, design freeze for submission of DCO and PIER | Arup | Committed | 573 | 63650 | 63650 | 0 | 0 | 63650 | 63650 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 21000 | 42650 | 0 | 0 | 0 | [12 empty] | 0 | [9 empty] | 2000 | 12000 | 7000 | 21000 | 7000 | 7000 | 7000 | 7000 | 7000 | 7650 | [6 empty] | 42650 | [12 empty] | 0 | [12 empty] | 0
|  | Stage 3; ES inputs and application Drafting and Submission | Arup | Committed | 574 | 146440 | 146440 | 0 | 0 | 146440 | 146440 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 146440 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  |  | 10000 | 10000 | 10000 | 19500 | 19500 | 19500 | 19500 | 19500 | 18940 | 146440 | [12 empty] | 0 | [12 empty] | 0
Environemtlat Studies to Submission |  | Stage 1; Mobilisation, Surveys Scoping Optioneering, Non Statutory Consutation input | Arup | Committed | 575 | 274750 |  | 0 | 101600 | 274750 | 274750 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 274750 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  |  |  | 15000 | 86600 |  | 0 | 55000 | 55000 | 63000 | 150 |  | 274750 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
Planning Studies up to Submission | General EIA Management | EIA - Coordination & management | Arup | Committed |  | 145129.52 | 145129.52 | 0 | 0 | [16 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| General EIA Management | EAI - design & integration | Arup | Committed |  | 27830.25 | 27830.25 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| General EIA Management | EIA -webgis | Arup | Committed | in 575 above | 25000 | 25000 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Scoping | Pre-scoping consultee engagement | Arup | Committed | in 575 above | 8500 | 8500 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Scoping | Natural England DAS | Arup | Committed | in 575 above | 1250 | 1250 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Scoping | Scoping | Arup | Committed | in 575 above | 42500 | 42500 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [38 empty] | 0
| Baseline | Baseline studies - arboriculture | Arup | Committed | in 575 above | 50000 | 50000 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Baseline | Baseline studies - cultural heritage | Arup | Committed | in 575 above | 15000 | 15000 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Baseline | Landscape and Visual Assessments | Arup | Committed | in 575 above | 19020 | 19020 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Baseline | Baseline - flood risk | Arup | Committed | in 575 above | 8000 | 8000 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Baseline | Baseline - traffic | Arup | Committed | in 575 above | 7950 | 7950 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Baseline | Baseline - noise | Arup | Committed | in 575 above | 8126.25 | 8126.25 | 0 | 0 | [48 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Natural England DAS - Ecology Input | TG | OOM estimate |  |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 3000 |  |  |  | 3000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Scoping | Ecology scoping input | TG | OOM estimate |  |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [10 empty] | 5000 |  | 5000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Baseline | HRA screening | TG | OOM estimate |  |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [10 empty] | 5000 | 5000 | 10000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Surveys | Ecology Surveys - first instruction | Tyler Grange | Committed | 503 | 162707 | 162707 | 0 | 16545 | 162707 | 162707 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 131207 | 31500 | 0 | 0 | 0 | [12 empty] | 0 |  |  |  |  | 3500 | 13045 | 41187 | 12674 | 17000 | 14326 | 10000 | 19475 | 131207 | 31500 | [11 empty] | 31500 | [12 empty] | 0 | [12 empty] | 0
|  | Ecology Survey - second quotation |  | OOM estimate |  |  | 25900 | 0 | 0 | 25900 | 25900 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 25900 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 9000 | 9000 | 7900 | [7 empty] | 25900 | [12 empty] | 0 | [12 empty] | 0
| Baseline | ecol phase 1 reporting |  | OOM estimate |  |  | 3000 | 0 | 0 | 3000 | 3000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 1500 |  |  | 1500 | 3000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Surveys | Other activities - surveys, NE liaison, Habs Regs, reporting now largely set out elsewhere |  | OOM estimate |  |  | 28754 | 0 | 0 | 28754 | 28754 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 6000 | 15754 | 7000 | 0 | 0 | [12 empty] | 0 | [8 empty] | 2000 | 2000 |  | 2000 | 6000 |  | 2000 |  | 3000 |  | 2754 |  | 3000 |  | 2000 |  | 3000 | 15754 |  | 3000 |  | 2000 |  | 2000 | [6 empty] | 7000 | [12 empty] | 0
| Surveys | Wintering birds (1 year) |  | OOM estimate |  |  | 100000 | 0 | 0 | 100000 | 100000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 36000 | 64000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [10 empty] | 18000 | 18000 | 36000 | 18000 | 18000 | 18000 | 10000 | [8 empty] | 64000 | [12 empty] | 0
| Surveys | Geophysical Survey including WSI | SUMO | Committed | 493 | 272500 | 272500 | 0 | 105300 | 272500 | 272500 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 255300 | 17200 | 0 | 0 | 0 | [12 empty] | 0 |  |  |  |  | 51800 | 53500 |  | 7500 | 40000 | 40000 | 32500 | 30000 | 255300 | 17200 | [11 empty] | 17200 | [12 empty] | 0 | [12 empty] | 0
| Surveys | Geophysical Survey (cable route overlap) |  | Budget |  |  | 100000 | 0 | 0 | 100000 | 100000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | 50000 | 50000 | [10 empty] | 100000 | [12 empty] | 0 | [12 empty] | 0
| Surveys | Trial Trenching |  | Budget |  |  | 500000 | 0 | 0 | 500000 | 500000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 200000 | 300000 | 0 | 0 | 0 | [12 empty] | 0 | [10 empty] | 100000 | 100000 | 200000 | 100000 | 100000 | 100000 | [9 empty] | 300000 | [12 empty] | 0 | [12 empty] | 0
| Surveys | ALC Survey |  | Budget |  |  | 67200 | 0 | 0 | 67200 | 67200 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 30000 | 37200 | 0 | 0 | 0 | [12 empty] | 0 | [9 empty] | 10000 | 10000 | 10000 | 30000 | [8 empty] | 10000 | 10000 | 10000 | 7200 | 37200 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Stage 2; Statutory Consultation, design freeze for submission of DCO and PIER | Arup | Committed | 576 | 257800 |  | 0 | 0 | 0 | 257800 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 90000 | 167800 | 0 | 0 | 0 | [12 empty] | 0 | [10 empty] | 60000 | 30000 | 90000 | 30000 | 30000 | 30000 | 30000 | 30000 | 17800 | [6 empty] | 167800 | [12 empty] | 0 | [12 empty] | 0
| PEIR | not tech summ | Arup | Committed | in 576 above | 9876.6 | 9876.6 | 0 | 0 | 9876.6 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | intro + end chapters | Arup | Committed | in 576 above | 9876.6 | 9876.6 | 0 | 0 | 9876.6 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Cumulative Impact | Arup | Committed | in 576 above | 9876.6 | 9876.6 | 0 | 0 | 9876.6 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | ag | Arup | Committed | in 576 above | 11087.63 | 11087.63 | 0 | 0 | 11087.63 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Climate Change | Arup | Committed | in 576 above | 20964.23 | 20964.23 | 0 | 0 | 20964.23 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Cultural Heritage | Arup | Committed | in 576 above | 11087.63 | 11087.63 | 0 | 0 | 11087.63 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | L&V | Arup | Committed | in 576 above | 20964.23 | 20964.23 | 0 | 0 | 20964.23 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Noise | Arup | Committed | in 576 above | 11087.63 | 11087.63 | 0 | 0 | 11087.63 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Operational noise | Arup | Committed | in 576 above |  | 13000 | 0 | 0 | 13000 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Social Economic/Health | Arup | Committed | in 576 above | 11087.63 | 11087.63 | 0 | 0 | 11087.63 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Transport Assessment | Arup | Committed | in 576 above | 14814.3 | 14814.3 | 0 | 0 | 14814.3 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | WR&FR | Arup | Committed | in 576 above | #VALUE! | 14814.3 | 0 | 0 | 14814.3 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | figures excl montages | Arup | Committed | in 576 above | 9876.6 | 9876.6 | 0 | 0 | 9876.6 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Environmental Masterplan | Arup | Committed | in 576 above | 16500 | 16500 | 0 | 0 | 16500 | 0 | [46 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Ecology | TG | OOM estimate |  |  | 30000 | 0 | 0 | 30000 | 0 | [14 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PEIR | Biodiversity Net Gain Assessment | TG | OOM estimate |  | 16500 | 16500 | 0 | 0 | 16500 | 0 | [14 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Agricultural circumstances/Farm Assessment and input into scoping, PIER and ES |  | Budget |  |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 5000 | [6 empty] | 15000 | 15000 | 15000 | 50000 | [12 empty] | 0 | [12 empty] | 0
| Excluded Env topics | Minerals and deposits | N/A |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Excluded Env topics | Amenity and Recreation Assessment | N/A |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Excluded Env topics | Residential Visual Amenity Asssessment | N/A |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Excluded Env topics | Air Quality | N/A |  |  |  |  | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | ecology |  | OOM estimate |  |  | 30000 | 0 | 0 | 30000 | 30000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 10000 | 20000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [11 empty] | 10000 | 10000 | 15000 | 5000 | [10 empty] | 20000 | [12 empty] | 0
| ES Prep | Biodiversity | TBC - budget from Arup proposal | OOM estimate |  | 8250 | 8250 | 0 | 0 | 8250 | 8250 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 8250 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 4000 | 4250 | [10 empty] | 8250 | [12 empty] | 0
| ES Prep | Stage 3; ES inputs & app Drafting & Submission | Arup | Committed | 589 | 247650 |  | 0 | 0 | 0 | 247650 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 247650 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [6 empty] | 42000 | 42000 | 42000 | 42000 | 42000 | 37650 | 247650 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | not tech summ | Arup | Committed | in 589 above | 4938.3 | 4938.3 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | intro + end chapters | Arup | Committed | in 589 above | 6149.33 | 6149.33 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | cumm | Arup | Committed | in 589 above | 4938.3 | 4938.3 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | ag | Arup | Committed | in 589 above | 6149.33 | 6149.33 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | CC | Arup | Committed | in 589 above | 9876.6 | 9876.6 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | CH | Arup | Committed | in 589 above | 6149.33 | 6149.33 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | L&V | Arup | Committed | in 589 above | 14814.9 | 14814.9 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | noise | Arup | Committed | in 589 above | 6149.33 | 6149.33 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | socio ec | Arup | Committed | in 589 above | 6149.33 | 6149.33 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | transport | Arup | Committed | in 589 above | 9876.6 | 9876.6 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | WR&FR | Arup | Committed | in 589 above | 9876.6 | 9876.6 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | figures excl montages | Arup | Committed | in 589 above | 9876.6 | 9876.6 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | env commitments register | Arup | Committed | in 589 above | 5000 | 5000 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | env masterplan | Arup | Committed | in 589 above | 10000 | 10000 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| ES Prep | photomontages | Arup | Committed | in 589 above | 80000 | 80000 | [50 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Arup - Extra Reports | Arup | Committed | TBC | 142700 |  |  |  |  | 142700 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 142700 | 0 | 0 | 0 | [25 empty] | 0 | [6 empty] | 25650 | 25650 | 25650 | 25650 | 25650 | 14450 | 142700
| Extra reports | Arboricultural Impact Assessment | Arup | Committed | will be included above |  | 14000 | 0 | 0 | 14000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Constr Dust | Arup | Committed | will be included above |  | 5000 | 0 | 0 | 5000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | FR | Arup | Committed | will be included above |  | 12000 | 0 | 0 | 12000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Major accidents & diasters - battery fire risk & strike | Arup | Committed | will be included above |  | 6200 | 0 | 0 | 6200 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Battery Safety Management Plan (outline) |  | Committed | will be included above |  | 5000 | 0 | 0 | 5000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline CEMP | Arup | Committed | will be included above |  | 14500 | 0 | 0 | 14500 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline CTMP | Arup | Committed | will be included above |  | 5000 | 0 | 0 | 5000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline DEMP | Arup | Committed | will be included above |  | 3000 | 0 | 0 | 3000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline LEMP | Arup | Committed | will be included above |  | 18500 | 0 | 0 | 18500 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline Materials Management Plan | Arup | Committed | will be included above |  | 6000 | 0 | 0 | 6000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline Pollution and Spillage Response Plan | Arup | Committed | will be included above |  | 5000 | 0 | 0 | 5000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | PRoW Management Plan | Arup | Committed | will be included above |  | 5000 | 0 | 0 | 5000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline Soil Resource Management Plan | Arup | Committed |  |  | 7000 | 0 | 0 | 7000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Outline Site Waste Management Plan | Arup | Committed |  |  | 6000 | 0 | 0 | 6000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Phase 1 Geotechnical and Geoenvironmental Desk Study | Arup | Committed |  |  | 7500 | 0 | 0 | 7500 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | Glint/Glare | Arup | Committed |  |  | 23000 | 0 | 0 | 23000 | [47 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Extra reports | BNG A |  | OOM estimate |  |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [11 empty] | 5000 | 5000 | [12 empty] | 0 | [12 empty] | 0
|  | Arup extra work / required post scoping |  | Budget |  |  | 200000 | 0 | 0 | 200000 | 200000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 160000 | 40000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  |  |  | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 160000 | 20000 | 20000 | [10 empty] | 40000 | [12 empty] | 0
Main Planning & Environmetnal Work to submission Total | [6 empty] | 2788665.55 | 0 | 278345 | 2515164.98 | 2789201 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114157 | 1535794 | 139250 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24900 | 166900 | 66545 | 41187 | 95174 | 138500 | 141326 | 234650 | 204975 | 1114157 | 235700 | 189000 | 151000 | 59000 | 74900 | 58204 | 107150 | 110150 | 117150 | 134150 | 150150 | 149240 | 1535794 | 57000 | 50250 | 18000 | 12000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 139250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Planning Applictino work | Not commissioned yet | Funding Statement | [23 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [25 empty] | 0
| Extra reports | Statement of Need if needed. See proposal for cost |  | Budget |  |  | 24900 | 0 | 0 | 24900 | 24900 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 7000 | 17900 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [11 empty] | 7000 | 7000 | 7500 |  | 1300 | 1300 | 1300 |  |  | 2600 |  | 2600 | 1300 |  | 17900 | [12 empty] | 0
|  | Generation Licence |  | Budget |  |  | 550 | 0 | 0 | 550 | 550 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 550 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 550 |  |  |  | 550 | [25 empty] | 0
Other studies in origial budget | Not commissioned yet | Topographical Study |  | Budget |  |  | 63000 | 0 | 0 | 63000 | 63000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 40000 | 23000 | 0 | 0 | 0 | [12 empty] | 0 | [10 empty] | 20000 | 20000 | 40000 | 23000 | [11 empty] | 23000 | [12 empty] | 0 | [12 empty] | 0
|  | Electromagnetic fields |  | Budget |  |  | 4000 | 0 | 0 | 4000 | 4000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [7 empty] | 4000 |  |  |  |  | 4000 | [12 empty] | 0 | [12 empty] | 0
|  | Cable route engineering design |  | Budget |  |  | 17000 | 0 | 0 | 17000 | 17000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 17000 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | 5500 | 5500 | 3500 |  |  |  |  | 2500 |  |  |  |  | 17000 | [12 empty] | 0 | [12 empty] | 0
|  | Electrical concept design | Fichtner | Committed | 957 | 23000 | 23000 | 0 | 0 | 23000 | 23000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 21000 | 2000 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 5500 | 5500 | 5500 | 4500 | 21000 | 2000 | [11 empty] | 2000 | [12 empty] | 0 | [12 empty] | 0
|  | Construction timescales/waste/worker numbers |  | Budget |  |  | 5000 | 0 | 0 | 5000 | 5000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 5000 | [9 empty] | 5000 | [12 empty] | 0 | [12 empty] | 0
|  | Blank line |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Protective provisions 3rd party legal costs |  | Budget |  |  | 90000 | 0 | 0 | 90000 | 90000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 40000 | 50000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 10000 | 10000 |  |  |  | 10000 | 10000 | 40000 | 15000 | 15000 | 10000 | 10000 | [8 empty] | 50000 | [12 empty] | 0
|  | National Grid property agreements | [5 empty] | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Batteries - Paul Gregory quote pre-submission |  | Budget |  |  | 20800 | 0 | 0 | 20800 | 20800 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 4000 | 4000 | 12800 | 0 | 0 | [12 empty] | 0 | [8 empty] | 4000 |  |  |  | 4000 |  |  |  | 4000 | [8 empty] | 4000 |  |  |  | 4000 |  |  | 4000 |  |  | 4800 |  |  | 12800 | [12 empty] | 0
|  | Other - Protracted red line adjustments |  | Budget |  |  | 50000 | 0 | 0 | 50000 | 50000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 25000 | 25000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [11 empty] | 25000 | 25000 | 25000 | [11 empty] | 25000 | [12 empty] | 0
Data | Data | Data Purchase |  | Budget |  |  | 57867.0167 | 0 | 0 | 57867.0167 | 57867.02 | -0.0033333 | [13 empty] | 0 | [12 empty] | 0 | 0 | 31000 | 26867.02 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 10000 | 10000 | 10000 | 1000 | 31000 |  | 10000 |  | 10000 | 6867.02 | [7 empty] | 26867.02 | [12 empty] | 0 | [12 empty] | 0
| Data | Cable route utilities search |  | Budget |  |  | 18800 | 0 | 0 | 18800 | 18800 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 18800 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 18800 |  |  |  | 18800 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Data | Utilities Digitisation |  | Budget |  |  | 10000 | 0 | 0 | 10000 | 10000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 10000 |  |  |  | 10000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| Data | OS Mapping | Centre Map | Committed | 958 | 2132.9833 | 2132.9833 | 0 | 0 | 2132.9833 | 2132.98 | 0.0033333 | [13 empty] | 0 | [12 empty] | 0 | 0 | 2132.98 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [7 empty] | 2132.98 |  |  |  |  | 2132.98
| Data | Mapping |  | Budget |  |  |  | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
[26 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
Other Pre-Planning Costs | [6 empty] | 387050 | 0 | 0 | 387050 | 387050 | -7.7307e-12 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127482.98 | 153867.02 | 105700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2132.98 | 48850 | 15500 | 35500 | 25500 | 127482.98 | 30500 | 15500 | 8500 | 14000 | 6867.02 | 10000 | 10000 | 6500 | 0 | 0 | 10000 | 42000 | 153867.02 | 47500 | 15000 | 11300 | 15300 | 1300 | 0 | 4000 | 2600 | 0 | 7400 | 1300 | 0 | 105700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Comms & Engagement |  | Project Management | Counter Context | Quotation |  |  | 124396 | 0 | 0 | 124396 | 124396 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 13600 | 81600 | 29196 | 0 | 0 | [12 empty] | 0 | [10 empty] | 6800 | 6800 | 13600 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 6800 | 81600 | 6800 | 6800 | 6800 | 6800 | 1996 | [7 empty] | 29196 | [12 empty] | 0
|  | Pre-launch | Counter Context | Committed | 986 | 22731 | 22731 | 0 | 0 | 22731 | 22731 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 22731 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [7 empty] | 8599.4 | 2400.6 | 5500 | 6231 |  | 22731 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Pre-consultation phase | Counter Context | Committed | 986 | 14856 | 14856 | 0 | 0 | 14856 | 14856 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 14856 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 5000 | 5000 | 4856 |  | 14856 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Non-Stat consultation |  | Quotation |  |  | 55557 | 0 | 0 | 55557 | 55557 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 45000 | 10557 | 0 | 0 | 0 | [12 empty] | 0 | [9 empty] | 5000 | 20000 | 20000 | 45000 | 10557 | [11 empty] | 10557 | [12 empty] | 0 | [12 empty] | 0
|  | SOCC |  | Quotation |  |  | 45699 | 0 | 0 | 45699 | 45699 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 45699 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 15000 | 15000 | 15699 | [8 empty] | 45699 | [12 empty] | 0 | [12 empty] | 0
|  | Stat Con |  | Quotation |  |  | 56156 | 0 | 0 | 56156 | 56156 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 56156 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  |  |  | 15000 | 15000 | 15000 | 11156 |  |  |  |  | 56156 | [12 empty] | 0 | [12 empty] | 0
|  | Consultation Report |  | Quotation |  |  | 29688 | 0 | 0 | 29688 | 29688 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 15000 | 14688 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [11 empty] | 15000 | 15000 | 14688 | [11 empty] | 14688 | [12 empty] | 0
|  | Postage, other printing costs etc |  | Budget |  |  | 40000 | 0 | 0 | 40000 | 40000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 10000 | 30000 | 0 | 0 | 0 | [12 empty] | 0 | [11 empty] | 10000 | 10000 | 10000 |  |  |  |  | 10000 | 10000 | [5 empty] | 30000 | [12 empty] | 0 | [12 empty] | 0
|  | Contingency - programme delay |  | Budget |  |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  | 7000 | 7000 | 6000 | [8 empty] | 20000 | [12 empty] | 0
Comms & Engagement Total | [6 empty] | 409083 | 0 | 0 | 409083 | 409083 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106187 | 239012 | 63884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8599.4 | 7400.6 | 15500 | 37887 | 36800 | 106187 | 27357 | 21800 | 21800 | 22499 | 21800 | 31800 | 31800 | 17956 | 6800 | 6800 | 6800 | 21800 | 239012 | 21488 | 13800 | 13800 | 12800 | 1996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning Legal | Pinsent Masons Project Management |  |  | Budget |  | initial £40k value for PO 0001014 | [19 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| PM - Fee agreement not seen | Legal DCO drafting | Pinsent Mason | Budget | 1014 |  | 1000000 | 0 | 0 | 1000000 | 1000000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 30000 | 260000 | 110000 | 0 | 600000 | [12 empty] | 0 | [7 empty] | 5000 | 5000 | 5000 | 7000 | 8000 | 30000 | 8000 | 5000 | 5000 | 10000 | 10000 | 25000 |  | 22000 | 25000 | 50000 | 50000 | 50000 | 260000 | 30000 | 30000 | 30000 | 20000 | [8 empty] | 110000 | [12 empty] | 0 | 600000
Planning Legal Total | [6 empty] | 1000000 | 0 | 0 | 1000000 | 1000000 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 260000 | 110000 | 0 | 600000 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 7000 | 8000 | 30000 | 8000 | 5000 | 5000 | 10000 | 10000 | 25000 | 0 | 22000 | 25000 | 50000 | 50000 | 50000 | 260000 | 30000 | 30000 | 30000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600000
Statutory Consutlee costs |  | PPA - NYC |  | Budget |  |  | 120000 | 0 | 0 | 120000 | 120000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 30000 | 0 | 90000 | 0 | 0 | [12 empty] | 0 | [8 empty] | 30000 |  |  |  | 30000 | [12 empty] | 0 | 90000 | [11 empty] | 90000 | [12 empty] | 0
|  | PPA - EA |  | Budget |  |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 25000 |  |  |  | 25000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | DAS - NE costs |  | Budget |  |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 15000 |  |  | 10000 | 25000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | DAS - HE costs |  | Budget |  |  | 20000 | 0 | 0 | 20000 | 20000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 20000 |  |  |  | 20000 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
[26 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
Planning Application Fee |  | Planning Inspectorate |  | Budget |  |  | 690000 | 0 | 0 | 690000 | 690000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 690000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 9000 | 45000 | 318000 |  |  |  | 318000 | [5 empty] | 690000 | [12 empty] | 0
|  | Planning Inspectorate - Pre-app advice - basic |  | Budget |  |  | 62350 | 0 | 0 | 62350 | 62350 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 62350 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  |  | 31175 | [5 empty] | 31175 |  |  | 62350 | [12 empty] | 0 | [12 empty] | 0
Application Fee & Stat Con Costs | [6 empty] | 942350 | 0 | 0 | 942350 | 942350 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 100000 | 62350 | 780000 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 10000 | 100000 | 0 | 0 | 0 | 31175 | 0 | 0 | 0 | 0 | 0 | 31175 | 0 | 0 | 62350 | 99000 | 45000 | 318000 | 0 | 0 | 0 | 318000 | 0 | 0 | 0 | 0 | 0 | 780000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Post submission fees | [7 empty] | 0 | 0 | 0 | 0 | 0 | [45 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Examination phase costs - putting to CC as not specified |  | Budget |  |  | 105000 | 0 | 0 | 105000 | 105000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 75000 | 30000 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  | 10000 |  | 5000 |  | 20000 |  | 20000 |  | 20000 |  | 75000 | 20000 |  | 10000 | [9 empty] | 30000
|  | Arup examination support |  | Budget |  |  | 300000 | 0 | 0 | 300000 | 300000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 270000 | 30000 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  |  | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 270000 | 15000 | 15000 | [10 empty] | 30000
|  | AV & venue |  | Budget |  |  | 175000 | 0 | 0 | 175000 | 175000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 130000 | 45000 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [5 empty] | 10000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 130000 | 20000 | 25000 | [10 empty] | 45000
|  | Other specialists at examination (assume DM in land below) PG / Si Gillett + |  | Budget |  |  | 75000 | 0 | 0 | 75000 | 75000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 60000 | 15000 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [8 empty] | 15000 | 15000 | 15000 | 15000 | 60000 | 15000 | [11 empty] | 15000
|  | Humbeat |  | Quotation |  |  | 26000 | 0 | 0 | 26000 | 26000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 10000 | 16000 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 |  |  |  |  | 10000 | [7 empty] | 10000 | 16000 | [11 empty] | 16000
Post Submission Costs | [6 empty] | 681000 | 0 | 0 | 681000 | 681000 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 545000 | 136000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 30000 | 45000 | 40000 | 70000 | 50000 | 85000 | 65000 | 85000 | 480000 | 960000 | 86000 | 40000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1096000 | 1232000
Land Referencing & Cable Route Priperty | No feel for | Land referencing (DM) |  | Quotation | 961 |  | 124000 | 0 | 0 | 124000 | 124000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 27000 | 70000 | 27000 | 0 | 0 | [12 empty] | 0 | [7 empty] | 2000 | 5000 | 20000 |  |  | 27000 |  |  |  |  | 20000 |  | 10000 |  | 20000 |  | 10000 | 10000 | 70000 | 7000 | 10000 | 10000 | [9 empty] | 27000 | [12 empty] | 0
|  | Land Agency - DM fee proposal |  | Quotation | 962 |  | 131000 | 0 | 0 | 131000 | 131000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 40500 | 55000 | 35500 | 0 | 0 | [12 empty] | 0 | [6 empty] | 3500 | 3500 | 3500 | 5000 | 20000 | 5000 | 40500 | 5000 | 5000 | 5000 | 5000 | 5000 |  | 10000 |  | 5000 |  | 15000 |  | 55000 |  | 18000 | 17500 | [9 empty] | 35500 | [12 empty] | 0
|  | Land agency / referencing expenses |  | Budget |  |  | 25000 | 0 | 0 | 25000 | 25000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 16000 | 9000 | 0 | 0 | 0 | [12 empty] | 0 | [8 empty] | 8000 |  | 8000 |  | 16000 |  | 9000 | [10 empty] | 9000 | [12 empty] | 0 | [12 empty] | 0
|  | Budget not allocated |  | Budget |  |  | 300000 | 0 | 0 | 300000 | 300000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 300000 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | 300000 | [11 empty] | 300000
| No feel for | Land referencing (Savills/Bruton Knowles) |  | Budget |  |  |  | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
| No feel for | Cable route landowner payments |  | Budget |  |  | 560000 | 0 | 0 | 560000 | 560000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 10000 | 160000 | 190000 | 200000 | 0 | [12 empty] | 0 | [11 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | 160000 | 10000 | 10000 | 10000 | 10000 | 10000 |  |  | 10000 | 10000 | 10000 | 10000 | 100000 | 190000 | 100000 | 100000 | [10 empty] | 200000
| No feel for | Cable route legals (developer costs) |  | Budget |  |  | 113000 | 0 | 0 | 113000 | 113000 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 10000 | 40000 | 43000 | 20000 | 0 | [12 empty] | 0 | [11 empty] | 10000 | 10000 |  |  | 10000 |  | 10000 |  | 10000 |  |  | 10000 |  |  | 40000 |  | 10000 |  |  | 10000 |  | 10000 |  | 3000 |  | 10000 |  | 43000 | 10000 |  | 10000 | [9 empty] | 20000
Land Refencing & Cable Route Property Total | [6 empty] | 1253000 | 0 | 0 | 1253000 | 1253000 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103500 | 334000 | 295500 | 520000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 5500 | 16500 | 25000 | 28000 | 25000 | 103500 | 15000 | 24000 | 25000 | 15000 | 45000 | 10000 | 40000 | 10000 | 35000 | 20000 | 35000 | 60000 | 334000 | 17000 | 48000 | 37500 | 10000 | 20000 | 0 | 10000 | 10000 | 13000 | 10000 | 20000 | 100000 | 295500 | 410000 | 100000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520000 | 0
Total - land assembly and planning | [6 empty] | 7965266.55 | 33000 | 305867 | 7658765.98 | 7965802 | -7.7307e-12 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 1639848.98 | 2642023.02 | 2195301 | 819806 | 635823 | [12 empty] | 33000 | 0 | 0 | 0 | 24900 | 194422 | 66545 | 44687 | 116406.38 | 329250.6 | 202326 | 346037 | 315275 | 1639848.98 | 333557 | 255300 | 211300 | 191674 | 158567.02 | 135004 | 188950 | 166606 | 183950 | 242125 | 251950 | 323040 |  | 271988 | 202050 | 438600 | 122100 | 68296 | 42000 | 402000 | 62600 | 98000 | 174047 | 106300 | 622320 |  | 496000 | 140000 | 20000 | 51988 | 0 | 0 | 0 | 0 | 0 | 0 | 111818 | 1096000 | 1915806 | 635823
Cummulative | [25 empty] | 0 | [12 empty] | 0 | 33000 | 1672848.98 | 4314872 | 6510173 | 7329979 | 7965802
Contingency |  | 10% of planning costs |  |  |  |  | 796526.655
Total budget pre-consent excluding grid |  | Costs excluding Grid |  |  |  |  | 8761793.205 | 33000 | 305867 | 7658765.98 | 7965802 | -7.7307e-12 | 0 | [32 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 0
[58 empty] | 0 | [12 empty] | 0
Grid |  | NGET Application |  |  |  | 71160 | 71160 | from fies / bank statement | [49 empty] | 0 | [12 empty] | 0
|  | NGET Mod App | NGESO | Committed | 696 | 58650 | 58650 | 0 | 58650 | 58650 | 58650 | 0 | [13 empty] | 0 | [12 empty] | 0 | 0 | 58650 | 0 | 0 | 0 | 0 | [12 empty] | 0 |  |  |  |  | 58650 | [7 empty] | 58650 | [12 empty] | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Consultants |  |  |  |  | 44670 | spent to date? Forward planning? |  |  | 0 | 44670 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Deposit/security | NGESO |  |  |  | 1500000 |  |  |  | 0 | 1500000 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Auxiliary connection applications |  |  |  |  | 3660 |  |  |  | 0 | 3660 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Purchase of Escrick grid connections |  |  |  | 362400 | 362400 |  |  |  | 0 | 362400 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0
|  | Network Rail BAPA |  |  |  |  | 30000 |  |  |  | 0 | 30000 | [13 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | [12 empty] | 0
Grid Total | [6 empty] | 2070540 | [21 empty] | 0 | [28 empty] | 0 | [12 empty] | 0
Satisfaction of pre-commencement planning conditions
Accounting, admin, prof. fees & bank charges
Transaction Cost
Total
Installed Capacity
Total/MW | [9 empty] | #DIV/0!
[28 empty] | Spend to date | 0
Deal Sheet budget 08/07/21
Difference to total:
Total costs excluding grid
Contingency (10%) included in above
Disbursements
26221.74
8761793.205
|  | Business plan budget |  |  |  |  | 8339736
|  | Headroom |  |  |  |  | -422057.205
Note on BN22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: June invoice & july credit note
Note on BO22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1156575 invoice 31/07
Note on BN25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: June invoice & july credit note
Note on BO25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1156575 invoice 31/07
Note on BO41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inv dated 30th July
Note on BO131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 205577

## Exeter
Exeter Budget Sheet | [19 empty] | Option signed | [16 empty] | Submission
Item | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote 1 | Quote 2 | Quote 3 | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Purchase Order Number | Consultant/Organisation | 2021-01-01 | 2022-01-01 | 2023-01-01 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Grid | DNO Application | 37000 | 37000 |  |  |  | 0 | 0 |  | National Grid ESO | 2021-01-01: 37000
| Deposit/security |  | 0 |  |  |  | 0 | 0 |  | National Grid ESO
| Consultant | 1800 | 1800 |  |  |  | 0 | 0 |  | WSP | 2021-01-01: 1800
Lease/Option |  | 24000 | 24000 |  |  |  |  | 0 |  | Trower and Hamlins LLP | 2023-01-01: 24000
Legal/Cooperation | [7 empty] | 0
Property Searches | [7 empty] | 0
Planning Application | Pre-application advice | 3000 | [5 empty] | 0 |  | East Devon District Council
| Application fee | 45000 | [5 empty] | 0 |  | East Devon District Council
Planning Consultant | General PM/coordination | 20000 | [5 empty] | 0
| Planning Statement | 8000 | [5 empty] | 0
| Design & Access Statement | 8000 | [5 empty] | 0
Planning Studies | Desktop Planning Assessment | 1200 | 1200 | 1200 |  |  | 1200 | 0 | PO001001 | Entrust | 2024-08-31: 1200
| EIA Screening | 2500 | [5 empty] | 0
| Topographical Study | 3000 | [5 empty] | 0
| Heritage and Archaeological DBA | 4000 | [5 empty] | 0
| Geophysical Survey | 7000 | [5 empty] | 0
| Trial Trenching | [6 empty] | 0
| ALC Classification | 2200 | 2200 | 2200 |  |  |  | 0 |  | Land Research Associates
| Ecological Survey - PEA | 3000 | [5 empty] | 0
| Ecological Survey - further surveys | 3000 | [5 empty] | 0
| Ecological Impact Assessment | 2500
| BNG Condition Assessment | 1500
| BNG Report | 2500 | [5 empty] | 0
| Arboricutural Survey | 3000 | [5 empty] | 0
| Flood Risk Assessment | 4000 | [5 empty] | 0
| Highways Survey | 5000 | [5 empty] | 0
| Transport Statement/Assessment | 8000 | [5 empty] | 0
| CTMP | 2500 | [5 empty] | 0
| AIL Study | 3000
| CEMP | 2500 | [5 empty] | 0
| Site Waste Management Plan | 1500 | [5 empty] | 0
| Outline BSMP | 5000 | [5 empty] | 0
| LVIA | 15000 | [5 empty] | 0
| Noise Assessment | 7000 | [5 empty] | 0
| Air Quality Statement | 5000 | [5 empty] | 0
| Green Infrastructure Plan | 2000 | [5 empty] | 0
| Health Impact Assessment | 2000 | [5 empty] | 0
| Lighting Report | 3000 | [5 empty] | 0
Comms/PR |  | 10000 | [5 empty] | 0
Land | Land | [6 empty] | 0
| Utilities | 1500 | [5 empty] | 0 |  | Centremaps
Contingency | 10% of planning costs | 13690 | 120 |  |  |  | 120 | N/A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Third Party Wayleaves |  |  | 0 |  |  |  |  | 0
National Trust Easement |  | 77500
Satisfaction of pre-commencement planning conditions |  |  | 0 |  |  |  | 15000 | 0
Transaction Cost |  |  | 0 |  |  |  | 15000 | 0
Total |  | 350390 | 66320 | 3400 | 0 | 0 | 31320 | 0 |  |  | 38800 | 0 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installed capacity/MW | 125
Total £/MW |  | 2803.12 | 530.56 | 27.2 | 0 | 0 | 250.56 | 0
1242000
Note on D10: Jamie Gleeson: £750 (ex. VAT) per request/meeting
Note on F10: Jamie Gleeson: Lanpro
Note on G10: Jamie Gleeson: DWD
Note on H10: Jamie Gleeson: Third Revolution Projects
Note on F15: Jamie Gleeson: Entrust
Note on F16: Jamie Gleeson: Lanpro
Note on F18: Jamie Gleeson: Lanpro
Note on F19: Jamie Gleeson: Lanpro
Note on F20: Jamie Gleeson: Lanpro
Note on F21: Jamie Gleeson: Land Research Associates
Note on F22: Jamie Gleeson: Clarkson Woods
Note on G22: Jamie Gleeson: Tyler Grange
Note on F27: Jamie Gleeson: Lanpro
Note on F36: Jamie Gleeson: Lanpro

## Phase 2 spends
Phase 2 Budget Cost
Project | Sub-Item | Budget (£) | Forecast Total Spend (£) | Quote Instructed (£) | Total Invoiced Amount (£)/ As of last month | Consultant | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01
Spittal | Bidwells agent fees |  |  |  | 10000 |  | 2024-07-01: 10000
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 0 | 0 | 0 | 10000 |  | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Installed capacity | 249
Total/MW |  | 0 | 0 | 0 | 40.1606
Note on D23: Samantha Jones: this includes some survey work so need to confirm with ITP - tbc